## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA)for Zone-I, II & Zone-V in different villages of Kumari, Boro-Jaragora, Dighi & Ankro-barakadam G.P. under command area of Manbazar-II Block (Part) Water Supply Scheme at Manbazar-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000333/2020-2021 | 243/PD | 10/02/2021 | 26/04/2021 | ANUP KUMAR SAHA | 285.06 | 152.55 | 53.52 | 92
2 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Shifting of distribution pipe line including making temporary diversion alone Boro-Jamtara road for construction of house pipe culvert by PW (Road) protectorate of Zone II Manbazar II Block (Part) water supply scheme (Tender No- 20/2021-22 of EE/PD) |  |  | VCH/000155/2022-2023 | BP-2022-23-13 | 07/04/2022 | 07/04/2022 | PINAKI RANJAN MUKHERJEE | 1.23 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Balance work for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area Zone I, Zone II & Zone V of Manbazar II Block (Part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub- Division, PHE Dte. (Part-I) (Tender No- 162/2022-23 of EE/PD) |  |  | VCH/001030/2022-2023 | BP-2022-23-347 | 30/09/2022 | 30/09/2022 | ANUP KUMAR SAHA | 28.06 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) for Zone- I, Zone- II & Zone- V in different village of Kumari, Boro Jaragora GP, Dighi GP & Ankro Barakadam GP under command area of Manbazar II block (part) water supply scheme of Manabazar II Block under Purulia Sadar Sub- Division, PHE Dte. under Purulia Division, PHE Dte. (Tender No- 34/2021-22 of SE/PMU/WBPWSP) |  |  | VCH/000882/2022-2023 | BP-2022-23-67 | 01/07/2022 | 01/07/2022 | ANUP KUMAR SAHA | 23.34 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Goverment Office ,Health Centre, ICDS Centre,SSK,MSK,Primary School ,High school at different habitation under command area Zone-I, Zone-II & Zone-V of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I, Part-I) | Assistant Engineer | Junior Engineer-3 | ORD/000613/2022-2023 | 510/PSD | 12/08/2022 | 26/09/2022 | ANUP KUMAR SAHA | 4.8 | 0 | 0 | 70
6 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA)for Zone-III & Zone-IV in different villages of Ankro-barakadam & Boro-Jaragora G.P. under command area of Manbazar-II Block (Part) Water Supply Scheme at Manbazar-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000334/2020-2021 | 244/PD | 10/02/2021 | 11/04/2021 | SADHAN GORAIN | 132.5 | 37.58 | 28.37 | 100
7 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : MANBAZAR (Part), BARKURI, BARTOR, BANDUR BERIYA & SHALPARA VILLAGE] | Assistant Engineer | Junior Engineer-3 | ORD/000303/2022-2023 | 836/PD | 19/05/2022 | 03/07/2022 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 43.61 | 0 | 0 | 100
8 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | New Sinking of 1 (One) Nos 200 mm dia river bed vertical tubewell (T/W No.- 1) alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Parbeliya W/S Scheme under Raghunathpur Sub Division, PHE Dte. |  |  | ORD/000399/2022-2023 | 357/RNP | 01/06/2022 | 21/06/2022 | ASHOK KUMAR CHATTERJEE | 1.76 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area Zone-III,Habitation-Ankro,GP- Ankro- Barakadam of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-II, Part-II) (Habitation-Ankro,GP- Ankro- Barakadam ) | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000608/2022-2023 | 517/PSD | 12/08/2022 | 21/09/2022 | SADHAN GORAIN | 3.51 | 0 | 0 | 100
10 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Goverment Office,Health Centre, ICDS Centre,SSK,MSK,Primary School ,High school at different habitation under command area Zone-III & Zone-IV of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I, Part-II) | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000614/2022-2023 | 511/PSD | 12/08/2022 | 26/09/2022 | SADHAN GORAIN | 2.43 | 0 | 0 | 100
11 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Continuation work for Soil Investigation work for proposed WTP at Manbazar-II Block within within Purulia Sadar Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/001001/2022-2023 | 110/A/PD | 20/01/2023 | 19/02/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
12 | PURULIA |  | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/08584 | Retrofitting | Laying of Loop Pipe Line for distribution System under command area Zone-I at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .-FromManikdih mor to Dhanda village Via Tilaboni Mor,)Punda,Govindpur, Tilaboni, Toparbad.) | Assistant Engineer | Junior Engineer-3 | ORD/000009/2023-2024 | 537/PD | 12/04/2023 | 27/05/2023 | MOONLIGHT HOUSE | 29.2 | 0 | 0 | 100
Total | [13 empty] | 558.3 | 190.14 | 34.06