## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | MODEL ESTIMATE FOR SKILLING OF MANPOWER TO GENERATE EMPLOYMENT OPPURTUNITIES AND TO SUPPORT IMPLEMENTATION OF JAL SWAPNA (For 5 nos Blocks Neturia,Para,Bagmundi,Raghunathpur-I,Puncha) | Assistant Engineer |  | ORD/000452/2020-2021 | 15/(S-6)/PR | 05/02/2021 | 12/02/2021 | KOUSHIK CHATTERJEE | 0.7 | 0 | 0 | 100
2 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | SKILLING OF MANPOWER TO GENERATE EMPLOYMENT OPPURTUNITIES AND TO SUPPORT IMPLEMENTATION OF JAL SWAPNA (For 5 nos Blocks Manbazar-I, Jhalda-I, Jhalda-II, Manbazar-II, Joypur) | Assistant Engineer |  | ORD/000451/2020-2021 | 15/(S-5)/PR | 05/02/2021 | 12/02/2021 | KOUSHIK CHATTERJEE | 3.49 | 3.49 | 100 | 100
3 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Jhalda-II Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000121/2022-2023 | 729/PD | 02/05/2022 | 16/06/2022 | MOONLIGHT HOUSE | 23.57 | 7.97 | 33.83 | 100
4 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000576/2022-2023 | 1131/PD | 25/07/2022 | 08/09/2022 | SINGHA ENTERPRISE | 94.88 | 91.39 | 96.32 | 100
5 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Barabazar Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2021-2022 | 469/PD | 24/03/2022 | 08/05/2022 | KOUSHIK CHATTERJEE | 23.43 | 12.67 | 54.07 | 60
6 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Barabazar Block (Part-F)of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000877/2022-2023 | 1855/PD | 13/12/2022 | 27/01/2023 | SANTANU BANERJEE | 74.42 | 26.91 | 36.16 | 100
7 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Manbazar-I Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000027/2022-2023 | 598/PD | 19/04/2022 | 03/06/2022 | ZAKIR HOSSIN MONDAL | 15.63 | 13.13 | 84.03 | 100
8 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001296/2022-2023 | 1151_/PD | 01/08/2022 | 15/09/2022 | WATER TECH | 158.37 | 17.78 | 11.23 | 100
9 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 1 nos AWC within Barabazar Block (Part-S), of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000801/2022-2023 | 1728/PD | 22/11/2022 | 06/01/2023 | PRATIK SAHA | 8.27 | 7.55 | 91.37 | 100
10 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Barabazar Block (Part-R) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000589/2022-2023 | 1156/PD | 01/08/2022 | 15/09/2022 | MANASH GHOSH | 197.96 | 25.62 | 12.94 | 100
11 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Extension of PVC & G.I pipe line in distribution system for Stand Post at different School & Offices of Purulia-II Block area to drinking water supply under Bongabari W/s Scheme. (Tender No.879/EE/PD of 2021-22) |  |  | VCH/000962/2021-2022 | BP-2021-22-280 | 03/03/2022 | 03/03/2022 | SOUVIK MANDAL | 2.65 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Withdrawing & lowering of 1M- II hand pump assembly for measurement of water level at different block of District Purulia (w.e.f. 01/09/2021 to 31/08/2022) [Name of block Hura, Kashipur, Neturia, Para, Raghunathpur-I, Raghunathpur-II, Santuri, Manbazar-I, Puncha, Purulia-II] (Tender No. 764/EE/PD of 2021-22) |  |  | VCH/000886/2022-2023 | BP-2022-23-78 | 01/07/2022 | 01/07/2022 | ANUDIP SAHA | 0.66 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Providing Functional Household Tap Connection (FHTC) at different AWC School and other allied works of Santuri Water Supply Scheme at Santuri Block of Raghunathpur Sub- Division under Purulia Division, PHE Dte. (Tender No- 392/2022-23 of EE/PD) |  |  | VCH/001014/2022-2023 | BP-2022-23-273 | 23/09/2022 | 23/09/2022 | MS MITRA SENGUPTA ENTERPRISES | 1.1 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Estimate for water supply arrangement of Bartoric High School in Neturia Block in the District Purulia under Purulia District, PHE Dte. (Tender No- 1028/2021-22 of EE/PD) |  |  | VCH/000881/2022-2023 | BP-2022-23-66 | 01/07/2022 | 01/07/2022 | INDRAJIT SARKAR | 1.59 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Extension of service connection from existing Distribution Main to Telkupi Baruni Ghat, Kastogora Pry. School, Dandahit Pry. School, Madhukunda Prathamik Vidyalaya and Bagalgoria Pry. School under Balitora improvement W/s Scheme. (Tender No.1/EE/PD of 2020-21) |  |  | VCH/000963/2021-2022 | BP-2021-22-278 | 03/03/2022 | 03/03/2022 | KOUSHIK CHATTERJEE | 1.81 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at various ICDS centre and schools and supply of drinking water through water tanker to various places from nearby headwork sites of different W/S Scheme to mitigate draught like situation under Bandwan Block of Purulia Sadar Sub- Division, PHE Dte. (Tender No- 56/2022-23 of EE/PD) |  |  | VCH/000905/2022-2023 | BP-2022-23-96 | 07/07/2022 | 07/07/2022 | BOSE CONSTRUCTION | 1.57 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Extension service connection from existing distribution main to Telkupi Baruni ghat, Kastogora Pry. School, Dandahit Pry. School, Madhukunda Prathamik Vidyalaya & Bagalgora Pry. School under Balitora Improvement Water Supply Scheme (Tender No- 01/2020-21 of EE/PD) |  |  | VCH/001151/2021-2022 |  | 03/03/2022 | 03/03/2022 | KOUSHIK CHATTERJEE | 1.81 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Estimate for water supply arrangement of Manbazar Girls Pry School, Manbazar Rajakpara Pry School & Manbazar Bauripara Pry School in Manbazar-I Block of the District Purulia under Purulia Division, PHE Dte. for [Estimate for Model 1 upto 200 students) (Tender No- 1018/2021-22 of EE/PD) |  |  | VCH/000887/2022-2023 | BP-2022-23-77 | 01/07/2022 | 01/07/2022 | KANAILAL PAL | 1.16 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | FHTC water tap connection in Schhol and health centre from existing distribution system with other allied works within scheme Jurisdiction of Lagda Piped W/s Scheme. (Tender No.825/EE/PD of 2021-22) |  |  | VCH/000961/2021-2022 | BP-2021-22-279 | 03/03/2022 | 03/03/2022 | M/S CHAKRABORTY CONSTRUCTION | 1.68 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Estimate for water supply arrangement at Mukundapur Prymary School Model-I (Upto 200 students) under Joypur Block. (Tender No.1017/EE/PD of 2021-22) |  |  | VCH/000152/2022-2023 | BP-2022-23-19 | 07/04/2022 | 07/04/2022 | AMAL KUMAR MUKHERJEE | 0.96 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 39 nos AWC within Raghunathpur -I Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000960/2022-2023 | 38_/PD | 09/01/2023 | 23/02/2023 | DILIP MISHRA | 21.67 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Raghunathpur-I Block (Part-B) & 6 nos AWC within Raghunathpur Block (Part-D-II) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001105/2022-2023 | 353/PD | 14/03/2023 | 28/04/2023 | PREMNATH MITRA | 148.86 | 86.57 | 58.15 | 49
23 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001297/2022-2023 | 22_/PD | 05/01/2023 | 19/02/2023 | WATER TECH | 165.38 | 94.75 | 57.29 | 100
24 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Model estimate for skilling of manpower to generate employment opportunities and to support implementation of Jal Swapna [ for 5 nos Blocks Kashipur, Raghunathpur-II, Hura, arsha, Santuri] (Tender No 789/2021-22 of EE/PD) |  |  | VCH/001535/2022-2023 | BP-2022-23-842 | 31/03/2023 | 31/03/2023 | MANATOSH SINGH | 3.48 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Model estimate for skilling of manpower to generate employment opportunities and to support implementation of Jal Swapna [For 5 nos block Purulia I, Balarampur, Bundwan, Purulia-II, Barabazar] (Tender No- 788/2021-22 of EE/PD) |  |  | VCH/001898/2022-2023 | BP-2023-24-52 | 19/04/2023 | 19/04/2023 | MANATOSH SINGH | 0.68 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Model estimate for skilling of manpower to generate employment opportunities and to support implementation of Jal Swapna [ for 5 nos Blocks Neturia, Para, Baghmundi, Raghunathpur-I, Puncha] (Tender No 330/2021-22 of EE/PD) |  |  | VCH/001534/2022-2023 | BP-2022-23-792 | 24/03/2023 | 24/03/2023 | KOUSHIK CHATTERJEE | 3.48 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Supply of stationery materials for office use |  |  | BILL/00988/2024-2025 | BP-2024-25-531 | 20/11/2024 | 20/11/2024 | KETIKA CONSUMERS CO-OPERATIVE STORES LTD | 2.49 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Regarding the expenses on the gram Sabha meeting for Har Ghar Jaal certification in Janardandi GP under Neturia Block on 01.03.2024. |  |  | BILL/00730/2024-2025 | BP-2024-25-395 | 19/09/2024 | 19/09/2024 | KOUSHIK CHATTERJEE | 0.56 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Work of Vendoring service service relating to E-return for Income-Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f 01.10.2023 to 30.09.2024) |  |  | BILL/00706/2024-2025 | BP-2024-25-356 | 11/09/2024 | 11/09/2024 | NIGAM CONSULTANCY SERVICES | 0.77 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Bill Payment for supply repairing & installation of computer related components for office purpose. |  |  | BILL/00935/2024-2025 | BP-2024-25-515 | 06/10/2024 | 06/10/2024 | SRI KRISHNA COMPUTER | 1.2 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | SM/08718 | Anganwadi | Reimbursement of the amount spent during the training program of pump operator & valve operator as per JJM guidelines on 31/01/2023 |  |  | BILL/00729/2024-2025 | BP-2024-25-396 | 19/09/2024 | 19/09/2024 | BOSE CONSTRUCTION | 0.57 | 0 | 0 | 0
Total | [13 empty] | 964.85 | 387.83 | 40.2