## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Extension of piped water supply (PWS) to source less schools located within the command area of PWSSs with in Purulia District as per the list of School Education Department. (30 Nos.) | SM/09028 | School | Providing necessary water supply arrangement within school with connection from exist collapsed Big-Dia D.T.H. Tube Well (200mm x 165mm) considering 200mt Dept and GI pipe of adequate dia and PVC pipes (medium duty confirming to the ASTMD-1785) and length where necessary 6 nos. alloy Iron with brass spindle bib cock/ stop cock at toilet and kitchen, gunmetal wheel valves, supplying submersible pumping machinery 1.0 HP of Crompton/ KSB or other renowned make conforming to latest BIS codes with all necessary electrical connections supplying PVC water storage tank of approved quality of total capacity of 1500ltr capacity.(3nos. 500ltrs tank) ( To be installed at roof top of school building ) all complete. | Assistant Engineer |  | ORD/001057/2022-2023 | 289/PD | 27/02/2023 | 13/04/2023 | PRINCE INDUSTRIES ( INDIA) | 6.53 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Extension of piped water supply (PWS) to source less schools located within the command area of PWSSs with in Purulia District as per the list of School Education Department. (30 Nos.) | SM/09028 | School | Water supply Tap Connection Arrangement for 2 nos AWC within Joypur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000141/2022-2023 | 725/PD | 02/05/2022 | 16/06/2022 | HUSSAIN CONSTRUCTION | 15.68 | 0 | 0 | 100
Total | [13 empty] | 22.21 | 0 | 0