## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-A : Water Supply through OHR at Baligara & Baghudi Mouza) | Assistant Engineer |  | ORD/000381/2021-2022 | 183/PD | 31/01/2022 | 17/03/2022 | GOUTAM CHAKRABORTY | 112.43 | 25.38 | 22.57 | 39
2 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of Augmantation of Lagda W/S Scheme. (Part-A W/S through OHR at Baligara @ Baghudi Mouza) (Tender No.16/SE/PMU of 2021-22) |  |  | VCH/000180/2022-2023 | BP-2022-23-45 | 02/05/2022 | 02/05/2022 | GOUTAM CHAKRABORTY | 16.95 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Providing FHTC in connection with JJM and JAL SWAPNA at different habitation and extension of distribution pipe line under command area of Augmentation of Lagda Water Supply Scheme of Purulia Sadar Sub- Division, PHE Dte. [Part-B water supply through direct pumping at Lagda mouza] (Tender No- 21/2021-22 of SE/PMU/WBPWSP(P) ) |  |  | VCH/000975/2022-2023 | BP-2022-23-145 | 22/07/2022 | 22/07/2022 | SADHAN GORAIN | 94.59 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-A : Water Supply through OHR at Baligara & Baghudi Mouza) (Tender No.16/SE/PMU of 2021-22) (Ad-interim) |  |  | VCH/000146/2022-2023 | BP-2022-23-37 | 28/04/2022 | 28/04/2022 | GOUTAM CHAKRABORTY | 50 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Continuation work for Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Lagda W/S Scheme & Barabazar W/S Scheme block-Purulia-I, Barabazar) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 848/2021-22 of EE/PD) |  |  | VCH/000939/2022-2023 | BP-2022-23-110 | 16/07/2022 | 16/07/2022 | INDRANIL DUTTA & ASSOCIATES | 1.91 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Lagda W/S Scheme & Barabazar W/S Scheme block-Purulia-I, Barabazar) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 357/2021-22 of EE/PD) |  |  | VCH/000938/2022-2023 | BP-2022-23-109 | 16/07/2022 | 16/07/2022 | INDRANIL DUTTA & ASSOCIATES | 1.05 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | New sinking of 2 (Two) nos 200 mm dia river bed tubewell (Horizontal) at Kasabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000294/2021-2022 | 1586/PD | 17/12/2021 | 16/01/2022 | MANATOSH SINGH | 11.25 | 5.7 | 50.66 | 55
8 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Laying of different dia distribution pipeline (Additional length) in connection with JJM and JAL SAPNA at different habitation under command area of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-A : Water Supply through OHR at Baligara & Baghudi Mouza) | Assistant Engineer |  | ORD/000632/2022-2023 | 1400/PD | 01/09/2022 | 16/10/2022 | GOUTAM CHAKRABORTY | 12.14 | 11.98 | 98.61 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Laying of distribution pipeline including placement of sluice valves at different places for providing 47 nos. Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at BALIGARA village under command area of Augmentation of LAGDA Water Supply Scheme of Purulia-I Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000864/2022-2023 | 1817/PD | 06/12/2022 | 06/03/2023 | M/S CHAKRABORTY CONSTRUCTION | 14.17 | 4.73 | 33.35 | 95
10 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Laying of 150 mm dia DI Rising Main in connection with Jal Jeevan Mission (JJM) for Augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001008/2022-2023 | 175/PD | 07/02/2023 | 09/03/2023 | M/S CHAKRABORTY CONSTRUCTION | 21.28 | 14.51 | 68.21 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Repairing of DI rising main pipeline & renovation of R.C.C. Elevated Reservoir of capacity 135 Cum (Intze Type), at headwork site of Lagda W/S Scheme including repairing of Pump house cum switch room (Unit-I&II) including other allied works in connection with Jal Jeevan Mission (JJM) for Augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001048/2022-2023 | 280/PD | 27/02/2023 | 29/03/2023 | M/S CHAKRABORTY CONSTRUCTION | 10.29 | 8.55 | 83.12 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Repairing of existing 200mm and 150 mm DI rising main pipeline and Providing Functinal household tap connection (FHTC) at Baligara Village and Laying of HDPE pipe and MS Casing Pipe and other allied works under Lagda W/S Scheme under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000657/2023-2024 | 1351/PD | 13/09/2023 | 13/10/2023 | GOUTAM CHAKRABORTY | 14.54 | 14.1 | 97.01 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 1507/PD | 13/12/2021 | 13/12/2021 | Resource Division | 51.27 | 0 | 0 | 0
14 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 610/PMD | 01/06/2023 | 01/06/2023 | Resource Division | 0.86 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. |  |  | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 02/08/2023 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Indian Railways Miscellaneous collection. |  |  | BILL/00077/2022-2023 | BP-2022-23-5171 | 02/01/2023 | 02/01/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.23 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Indian Railways Miscellaneous collection. |  |  | BILL/00090/2022-2023 | BP-2022-23-5177 | 02/01/2023 | 02/01/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 6.09 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. |  |  | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 02/08/2023 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Bank guarantee of Proposed Way Leave permission of Water pipe line Crossing for application ID No SER ADA-2022 WL 38, SER ADA-2022 WL 42. SER ADA 2022 WL 43, SER- ADA 2022 WL-55. SER-ADA-2022-WL-56. SER-ADA-2022 WL-60, SER ADA 2022 WL-61. |  |  | BILL/00175/2022-2023 |  | 08/02/2023 | 08/02/2023 | F.A & C.A.O /S.E.RLY /GARDEN REACH-43 | 5 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Kotshila Mouza) (Under Lagda W/S Scheme) |  |  | ORD/003970/2023-2024 | 514/PD | 16/03/2024 | 15/05/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 9.13 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Construction of pathway at Ajodhya Pump House under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. Length : 115.00 Mtr. Width : 2.40 Mtr.(Under Lagda W/S Scheme) |  |  | ORD/003953/2023-2024 | 495/PD | 16/03/2024 | 15/04/2024 | TUMPA GORAIN | 4.13 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Barudi Mouza) (Under Lagda W/S Scheme) |  |  | ORD/003968/2023-2024 | 512/PD | 16/03/2024 | 15/05/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 11.24 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chayadih Mouza) (Under Lagda W/S Scheme) | Assistant Engineer | Junior Engineer-3 | ORD/003972/2023-2024 | 516/PD | 16/03/2024 | 15/05/2024 | SABYASACHI MISHRA | 7.82 | 6.05 | 77.35 | 70
24 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-B : Water Supply through direct pumping at Lagda Mouza) | Assistant Engineer | Junior Engineer | ORD/000400/2021-2022 | 217/PD | 08/02/2022 | 25/03/2022 | SADHAN GORAIN | 237.24 | 129.52 | 54.6 | 100
25 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Lagda Water Supply scheme Block Purulia-I under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000079/2021-2022 | 164/PMD | 07/03/2022 | 06/04/2022 | ASHUTOSH DAS AND CO. | 20.5 | 20.5 | 100 | 90
26 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works in connection with Jal Jeevan Mission (JJM) and JAL SAPNA for Augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000831/2022-2023 | 1721/PD | 22/11/2022 | 02/03/2023 | SWASTIK ENTERPRISE | 16.82 | 10.43 | 62.03 | 65
27 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply delivery and installation of voltage stabilizer at OHR site of Lagda W/S under PMD PHE dte in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000368/2022-2023 | 210/PMD | 28/02/2023 | 31/12/2024 | TUSHAR GHOSH | 7.07 | 7.07 | 100 | 90
28 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply delivery and installation of voltage stabilizer at Augmentation of Lagda W/S under PMD PHE dte in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000468/2022-2023 | 308/PMD | 16/03/2023 | 15/04/2023 | GOUTAM CHAKRABORTY | 11.85 | 11.85 | 100 | 70
29 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Lagda river site for Augmentation of Lagda W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 573/PD | 19/04/2023 | 18/07/2023 | SWASTIK ENTERPRISE | 14.23 | 14.13 | 99.28 | 80
30 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Construction of meter room, panel room,undercut pump house & surface drain with other allied works at Lagda OHR Site for Augmentation of Lagda W/S Scheme under Purulia sader Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000036/2023-2024 | 554/PD | 13/04/2023 | 28/05/2023 | CHITTARANJAN MAJHI | 13.87 | 13.84 | 99.79 | 100
31 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Providing internal and external illumination arrangement at existing at OHR site of Lagda W/S under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000154/2023-2024 | 650/PMD | 08/06/2023 | 07/08/2023 | TUSHAR GHOSH | 6.13 | 5.44 | 88.85 | 90
32 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply & delivery DI Specials for Newly Laying of Rising Main (DI-K9) Pipe line LagdaRiversite Pump House to 100 Cum Capacity CWR at Lagda OHR Site under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001313/2023-2024 | 1706/PD | 04/12/2023 | 03/01/2024 | M/S CHAKRABORTY CONSTRUCTION | 1.46 | 1.46 | 100 | 100
33 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Puncha OHR Site (Bahadurpur) for Augmentation of Lagda W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/004345/2023-2024 | 662_PD | 17/05/2023 | 01/11/2024 | ASHOKE ADHIKARY | 14.24 | 13.79 | 96.87 | 60
34 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Making bypass arrangement & other allied works at lagda OHR site of Lagda W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000348/2024-2025 | 1378/PD | 25/07/2024 | 23/09/2024 | M/S CHAKRABORTY CONSTRUCTION | 4.32 | 3.25 | 75.07 | 100
35 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supplying & laying Parallel HDPE pipe and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and other allied works of Puncha W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte.( under Lagda Water Supply Scheme ) | Assistant Engineer | Junior Engineer-3 | ORD/003495/2023-2024 | 346/PD | 04/03/2024 | 06/09/2024 | JAYANTA KUMAR MONDAL | 21.97 | 5.55 | 25.24 | 100
36 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Cleaning & Fencing at Ajodhya Pump House Site under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Under Lagda W/S Scheme) | Assistant Engineer | Junior Engineer | ORD/003955/2023-2024 | 497/PD | 16/03/2024 | 30/04/2024 | SARKAR ENTERPRISE | 1.08 | 0.96 | 89.41 | 100
37 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and Laying of Branch distribution Pipeline of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Goaladih Mouza] (Under Lagda W/S Scheme) | Assistant Engineer | Junior Engineer-3 | ORD/003969/2023-2024 | 513/PD | 16/03/2024 | 15/05/2024 | SOUMITRA CHAKRABORTY | 4.43 | 1.58 | 35.74 | 100
38 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Uparbatri Mouza) (Under Lagda W/S Scheme) | Assistant Engineer | Junior Engineer-3 | ORD/003971/2023-2024 | 515/PD | 16/03/2024 | 15/05/2024 | SOUVIK MANDAL | 5.55 | 5.15 | 92.92 | 100
39 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | New connection for Augmentation OHR site of Lagda W/S |  |  | BILL/00866/2023-2024 | BP-23-24-301 | 05/03/2024 | 05/03/2024 | WBSEDCL PURULIA | 7.04 | 0 | 0 | 0
40 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | New connection for Augmentation of River site of Lagda W/S, block- Purulia |  |  | BILL/00863/2023-2024 | BP-23-24-298 | 05/03/2024 | 05/03/2024 | WBSEDCL PURULIA | 7.63 | 0 | 0 | 0
41 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply of stationery materials for office use |  |  | BILL/00988/2024-2025 | BP-2024-25-531 | 20/11/2024 | 20/11/2024 | KETIKA CONSUMERS CO-OPERATIVE STORES LTD | 2.49 | 0 | 0 | 0
42 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply and lowering of submersible pump motor sets at at newly constructed River Bed Tube well with supply of necessary substitutes at Lagda w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000345/2022-2023 | 130/PMD | 20/02/2023 | 01/01/2026 | SANTANU BANERJEE | 26.09 | 13.58 | 52.04 | 40
43 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum at Puncha OHR site of Lagda W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001013/2021-2022 | 527_PD | 30/03/2022 | 08/07/2022 | SOUVIK MANDAL | 10.83 | 0 | 0 | 0
44 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Repairing of DI rising main pipeline & repairing of FHTC & construction of pathway including other allied works of existing godown, store room, pump room & buildings at Purulia Sadar Sub-Division under Augmentation of Lagda Water supply scheme of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000214/2024-2025 | 1082/PD | 07/06/2024 | 06/08/2024 | SIKHA ENTERPRISE | 43.73 | 0 | 0 | 100
45 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Continuation of work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. w.e.f. 14/09/2025 to 15/03/2025 |  | Junior Engineer-3 | ORD/000548/2025-2026 | 515/PSD | 11/09/2025 | 13/03/2026 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0 | 0
46 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (w.e.f 14/09/2025 to 15/03/2025) |  | Junior Engineer-3 | ORD/000551/2025-2026 | 523/PSD | 11/09/2025 | 13/03/2026 | SHIVA ENTERPRISES | 0.9 | 0 | 0 | 0
47 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | New sinking of 3 (Three) nos 200 mm dia river bed tubewell (Horizontal) at Kasabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Lagda W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000293/2021-2022 | 1585/PD | 17/12/2021 | 16/01/2022 | KOUSHIK CHATTERJEE | 17.14 | 11.02 | 64.33 | 55
48 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum at Puncha river site pump house of Lagda W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000490/2021-2022 | 526/PD | 30/03/2022 | 16/10/2022 | KM ENTERPRISES | 10.81 | 0 | 0 | 100
49 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, Flowmeter with necessary substitutes and allied electrical panel at Lagda w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000346/2022-2023 | 131/PMD | 20/02/2023 | 21/01/2025 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 69.89 | 67.69 | 96.85 | 70
50 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Interconnection of new & old DI rising main with new pump house & other allied works for direct supply & pathway of Lagda Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/001062/2024-2025 | 2123/PD | 05/12/2024 | 19/01/2025 | M/S CHAKRABORTY CONSTRUCTION | 9.77 | 9.18 | 93.95 | 100
51 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply, delivery and installation of Submersible Pump motor and other related works for Augmentation work of Lagda w/s scheme (OHR Site) under Purulia Mechanical Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000387/2023-2024 | 373/PMD | 04/03/2024 | 01/08/2025 | GOUTAM CHAKRABORTY | 4.73 | 3.47 | 73.34 | 50
52 | PURULIA |  | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Withdrawing and relaying of collecting line from river bed tubewel and inter connection between existing collecting line under Lagda W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/001075/2024-2025 | 2170/PD | 13/12/2024 | 27/01/2025 | M/S CHAKRABORTY CONSTRUCTION | 2.89 | 2.87 | 99.12 | 100
53 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply, Delivery and fixing of Cable, Internal wiring and others additional work at Lagda w/s scheme ( River site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000678/2024-2025 | 1690/PMD | 06/12/2024 | 04/02/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.47 | 2.41 | 97.28 | 80
54 | PURULIA |  | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | SM/09036 | Augmentation | Supply, delivery and installation of Centrifugal pumping machinery with other allied work at Lagda OHR Site of Augmentation of Lagada water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000100/2024-2025 | 1058/PMD | 28/06/2024 | 01/02/2025 | NUPUR CHANDRA HALDER | 21.35 | 11.35 | 53.16 | 70
Total | [13 empty] | 1083.8 | 457.11 | 42.18