## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Supply, Delivery and installation of two nos. submersible pumping machineries in newly constructed river bed tube well, voltage stabilizer with allied cable line and other allied works for augmentation of Satra w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000095/2022-2023 | 521/PMD | 05/08/2022 | 04/09/2022 | NUPUR CHANDRA HALDER | 22.86 | 21 | 91.85 | 92
2 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-A) | Assistant Engineer |  | ORD/000215/2020-2021 | 10/PSD | 13/01/2021 | 27/02/2021 | GYANRANJAN SEN | 4.66 | 0 | 0 | 65
3 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of capacity 100 cum with other allied works at Satra boosting pump house campus of Satra W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No. 862/EE/PD of 2021-22) |  |  | VCH/000959/2022-2023 | BP-2022-23-130 | 19/07/2022 | 19/07/2022 | SUBODH PRAMANIK | 11.52 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Laying of UPVC pipe as distribution main (loop line) from Misirdih More near Canel to Jhunjka village including PWD Road Crossing (Tamna-Arsha Road) by Jack pushing for drinking water supply through FHTC to meet up the water crisis at Jhunjka Village of Satra W/s Scheme under JJM. (Tender No.871/EE/PD of 2021-22) |  |  | VCH/001139/2021-2022 | BP-2021-22-293 | 09/03/2022 | 09/03/2022 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 18.23 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Additional work for Extension of water supply pipe line towards Pitchkapahali, Garamthana, Lalbandh, Kishor Bharati Public School Adjacent to Patuara village from existing Satra W/s Scheme to meet up the water crisis under Jal Swapna Program. (Tender No.976/EE/PD of 2021-22) |  |  | VCH/000149/2022-2023 | BP-2022-23-33 | 20/04/2022 | 20/04/2022 | SUBODH PRAMANIK | 12.45 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | providing Functional household tap Connection FHTC in connection with Jal Jeevan Mission (JJM & Jalswapna) at Ramjibanpur Jhunjka, Layardih of Hensla G.P. under command area of Satra W/S Scheme at Arsha block under Purulia Sadar Sub- Division (Tender No- 277/2020-21 of EE/PD) |  |  | VCH/001179/2021-2022 | BP-2021-22-312 | 22/03/2022 | 22/03/2022 | KANTILAL SAO | 20.32 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Laying of UPVC pipe as distribution main from Misirdih More to East-West along the Tamna-Arsha Road for drinking water supply through FHTC to meet up the water crisis at Satra W/s Scheme under Jal Swapna Program. (Tender No.06/EE/PD of 2022-23) |  |  | VCH/000173/2022-2023 | BP-2022-23-55 | 19/05/2022 | 19/05/2022 | DEBASISH CHAKRABORTY | 4.41 | 0 | 0 | 0
8 | PURULIA |  | Purulia Mechanical | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | SUPPLY DELIVERY & INSTT OF TWO NOS SUBMERSIBLE PUMP MOTOR SETS IN NEW CONSTRUCTED RIVERBED TUBE WELL AND LAYING OF DEPARTMENTALLY SUPPLIED CABLE LINE WITH OTHER ALLIED WORKS FOR SATRA W/S SCHEME UNDER PMD PHE DTE.(TR.NO 326/21-22) |  |  | VCH/000113/2022-2023 | C052221499438 | 11/05/2022 | 11/05/2022 | NUPUR CHANDRA HALDER | 2.4 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | providing Functional household tap Connection FHTC (leftout household) in connection with Jal Jeevan Mission (JJM & Jalswapna) at Misirdih village of Chatu Hansa G.P. under command area of Satra W/S Scheme at Arsha block under Purulia Sadar Sub- Division (Tender No- 877/2021-22 of EE/PD) |  |  | VCH/001178/2021-2022 | BP-2021-22-305 | 14/03/2022 | 14/03/2022 | BHAGABANDAS KUMAR | 6.11 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC)(leftout household) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.866/2021-22 of EE/PD) |  |  | VCH/001028/2022-2023 | BP-2022-23-336 | 29/09/2022 | 29/09/2022 | SUBODH PRAMANIK | 8.57 | 0 | 0 | 0
11 | PURULIA |  | Purulia Mechanical | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, augmentation of MCC panel, Flow meter and other allied works for augmentation of Satra (River side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000344/2022-2023 | 129/PMD | 20/02/2023 | 21/04/2023 | NUPUR CHANDRA HALDER | 36.75 | 36.26 | 98.67 | 51
12 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Laying of UPVC Pipe line from Satra OHR site towards Satra Village & Extension of PVC pipe line in distribution system for Stand Post at different School & ICDS Centre of Arsha Block to supply drinking water of command area of Satra Water Supply Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000017/2023-2024 | 546/PD | 12/04/2023 | 12/05/2023 | SUBODH PRAMANIK | 7.41 | 7 | 94.44 | 0
13 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Repairing and renovation of the Over Head reservoir (OHR) of 350 m3 Capacity, Staging Height 20 mtr. at Satra W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000284/2021-2022 | 1578/PD | 17/12/2021 | 17/03/2022 | SUBODH PRAMANIK | 10.25 | 9.05 | 88.27 | 90
14 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC)(leftout household) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000289/2021-2022 | 1583/PD | 17/12/2021 | 31/01/2022 | SUBODH PRAMANIK | 10.76 | 0.53 | 4.88 | 100
15 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Laying of 150 mm dia DI pipe line for clear water rising main from Medical hall at Misirdih to Boosting pump house at Satra Water Supply Scheme of Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000281/2021-2022 | 1575/PD | 17/12/2021 | 17/03/2022 | ANUDIP SAHA | 9.62 | 3.22 | 33.52 | 55
16 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Repairing & restoration of different works viz. Valve Chamber with replace of valve at OHR campus, Road cutting & restoration by concreting & Moorum spreading including M.S. Pipe placing as casing at different place of Satra W/S Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000280/2021-2022 | 772/PD | 13/12/2021 | 12/01/2022 | M/S SAWDESH ENTERPRISE | 3.52 | 3.3 | 93.91 | 95
17 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Laying of UPVC pipe as distribution main (loop line) from Satra Junior High School to Satra Uppar Para for drinking water supply through FHTC to meet up the water crisis at Satra W/S Scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000288/2021-2022 | 1582/PD | 17/12/2021 | 17/03/2022 | SUBODH PRAMANIK | 9.87 | 1.39 | 14.11 | 65
18 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Functional House hold Tap Connection (FHTC) & pipe line laying of different dia. Pipe in connection of Jal Jeevan Mission (JJM & Jal Swapna) Programme at Satra Village Uppar Para and adjacent area of Arsha Block to drinking water supply under augmentation at Satra Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000626/2022-2023 | 1396/PD | 01/09/2022 | 16/10/2022 | SUBODH PRAMANIK | 18.74 | 16.77 | 89.45 | 100
19 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Additional work for Grouting on inside & outside of cell wall for repairing and renovation of the Over Head reservoir (OHR) of 350 m3 Capacity, Staging Height 20 mtr. of Satra W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000792/2022-2023 | 1639/PD | 03/11/2022 | 18/12/2022 | M/S SAWDESH ENTERPRISE | 3.41 | 3.37 | 98.98 | 100
20 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Repairing, renovation & restoration of Pump house and Meter room including roof treatment & Boundary wall at satra river site & Boosting pump station of Satra W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000923/2022-2023 | 1930/PD | 22/12/2022 | 20/02/2023 | SUBODH PRAMANIK | 12.92 | 11.59 | 89.72 | 100
21 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Repairing of 200 mm dia Vertical and Horizontal Tubewell & 100 mm dia G.I. collecting line upto M.S. Manifold with allied works due to flash flood of Satra W/S Scheme of Purulia Sadar Sub-Division, Under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001055/2022-2023 | 287/PD | 27/02/2023 | 29/03/2023 | M/S SAWDESH ENTERPRISE | 2.69 | 2.68 | 99.82 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 1504/PD | 13/12/2021 | 13/12/2021 | Resource Division | 58.03 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 392/PD | 11/03/2022 | 11/03/2022 | Resource Division | 1.28 | 0 | 0 | 0
24 | PURULIA |  | Purulia Mechanical | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 620/PMD | 01/06/2023 | 01/06/2023 | Resource Division | 1.55 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-A) (Tender No- 287/2020-21 of EE/PD) |  |  | VCH/001088/2022-2023 | BP-2022-23-219 | 24/08/2022 | 24/08/2022 | GYANRANJAN SEN | 0.7 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | New sinking of 02 (Two) No. 200 mm dia river bed tube well (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI collecting line with all allied works at Satra river site of Satra Water Supply Scheme under Purulia Division, PHE Dte. Phase-1 (Tender No- 870/2021-22 of EE/PD) |  |  | VCH/000909/2022-2023 | BP-2022-23-92 | 07/07/2022 | 07/07/2022 | SUBODH PRAMANIK | 17.23 | 0 | 0 | 0
27 | PURULIA |  | Purulia Mechanical | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Satra Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000078/2021-2022 | 163/PMD | 07/03/2022 | 06/04/2022 | DEY ENTERPRISE | 20.5 | 12.28 | 59.88 | 85
28 | PURULIA |  | Purulia Mechanical | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Supply, Delivery and installation of submersible pumping machineries for river bed tube well with allied cable line and other allied works for Satra w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000687/2024-2025 | 1699/PMD | 06/12/2024 | 05/01/2025 | NUPUR CHANDRA HALDER | 3.31 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-F) | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000234/2020-2021 | 17/PSD | 13/01/2021 | 27/02/2021 | RAKSHIT ENTERPRISE | 4.48 | 0.86 | 19.27 | 100
30 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC)(leftout household) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Misirdih village of Chatu Hansa G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000290/2021-2022 | 1592/PD | 17/12/2021 | 31/01/2022 | BHAGABANDAS KUMAR | 7.17 | 0.09 | 1.23 | 100
31 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Laying of UPVC pipe as distribution main from Misirdih more to East-West along the Tamna-Arsha road for drinking water supply through FHTC to meet up the water crisis at Satra W/S Scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000286/2021-2022 | 1580/PD | 17/12/2021 | 17/03/2022 | DEBASISH CHAKRABORTY | 6.73 | 1.14 | 16.9 | 100
32 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Construction of pump house for accommodating centrifugal pump for pumping of water from Satra Boosting Pump House site CWR to distribution zone of Satra water supply scheme under Purulia Sadar Sub-Division of Purulia Division, P.H.E. Dte. Purulia. | Assistant Engineer | Junior Engineer | ORD/000863/2022-2023 | 1816/PD | 06/12/2022 | 05/01/2023 | M/S SAWDESH ENTERPRISE | 16.77 | 14.52 | 86.6 | 100
33 | PURULIA |  | Purulia Division | Augmentation of Satra Water Supply Scheme | SM/09038 | Augmentation | Repairing of damage pipe line including House Connection arrangement for the works related to JICA Assisted West Bengal Pipped Water Supply Project(Purulia) of Satra Water Supply Scheme under Arsha Block. | Assistant Engineer | Junior Engineer-4 | ORD/000339/2024-2025 | 1365/PD | 25/07/2024 | 23/09/2024 | SUBODH PRAMANIK | 5.46 | 5.46 | 100 | 100
Total | [13 empty] | 380.67 | 150.52 | 39.54