## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of SonathaliWater Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No. 17/SE/PMU of 2021-22) |  |  | VCH/000960/2021-2022 | BP-2021-22-267 | 28/02/2022 |  | M/S S & P CONSTRUCTION | 35.45 | 0 | 0 | 0
2 | PURULIA |  | Purulia Mechanical | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | SUPPLY DELIVERY & INSTT. OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF SNATHOL W/S SCHEME KASHIPUR BLOCK UNDER PMD PHE DTE.(TR.NO 342 OF 2021-22) |  |  | VCH/000586/2021-2022 | C032262583160 | 28/03/2022 |  | R.N.S. TRADING | 13.71 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of Sonathali Water Supply Scheme at Kashipur Block. (Tender No.17/SE/PMU of 2021-22) |  |  | VCH/000179/2022-2023 | BP-2022-23-46 | 02/05/2022 |  | S AND P CONSTRUCTION | 16.37 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Construction of Boundary wall, RCC pillar, barbed wire & other allied works under Sonathali W/S Scheme (Tender No-930/2021-22 of EE/PD) |  |  | VCH/000190/2022-2023 | BP-2022-23-57 | 20/05/2022 |  | TOTAL INFRA | 3.35 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Sinking of 08 (Eight) No. 200 mm dia river bed tube well horizontal at Darkeswar river (Kalapathar Ghat) along with laying of 100 mm dia GI collecting line with all allied works under Sonatholi Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 02/2022-23 of EE/PD) |  |  | VCH/000945/2022-2023 | BP-2022-23-115 | 16/07/2022 |  | KOUSHIK CHATTERJEE | 18.97 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 441/PD | 23/03/2023 |  | Resource Division | 32.08 | 0 | 0 | 0
7 | PURULIA |  | Purulia Mechanical | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Supply delivery and installation of Vertical multistage centrifugal pump motor sets ,Pannel , Flow meter and all electro mechanical equipment's at Augmentation of Sonathali High Lift Water supply scheme for direct pumping Block :Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000513/2022-2023 | 100/PMD | 09/02/2023 | 10/04/2023 | R.N.S. TRADING | 45.25 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Additional work by Providing functional Household Tap Connection (FHTC) at different AWC ,School and other allied works of Madandih & Sonathali W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000172/2022-2023 | 789/PD | 05/05/2022 | 19/06/2022 | MADHU SUDAN RAKSHIT | 6.23 | 6.21 | 99.72 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Additional work for Construction of Pump House building at Head work Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000581/2022-2023 | 494/RNP | 02/08/2022 | 16/09/2022 | SUBHAS CHANDRA MAHATO | 4.45 | 4.41 | 99.02 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000388/2021-2022 | 209/PD | 01/02/2022 | 18/03/2022 | M/S S & P CONSTRUCTION | 158.98 | 13.64 | 8.58 | 65
11 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Construction of Pump House at Head work site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000317/2021-2022 | 29/PD | 07/01/2022 | 21/02/2022 | SUBHAS CHANDRA MAHATO | 5.03 | 5.02 | 99.9 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Construction of G.I. Shed at 1st Floor of Raghunathpur Sub-Divisional office buiding under Aug. of Sonathol W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000844/2022-2023 | 1747/PD | 22/11/2022 | 06/01/2023 | MANATOSH SINGH | 4.3 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Construction of G.I shed at 1st floor of Raghunathpur Sub- Divisional office building under Aug. of Sonathali W/S Scheme within Raghunathpur Sub- Division, PHE Dte. [Tender No 941/2022-23 of EE/PD] |  |  | VCH/001901/2022-2023 | BP-2023-24-85 | 16/05/2023 |  | MANATOSH SINGH | 4.17 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Construction of Pump House Building at OHR Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Related to JJM & Jal swapna programme) | Assistant Engineer |  | ORD/000845/2022-2023 | 1748/PD | 22/11/2022 | 20/02/2023 | MADHU SUDAN RAKSHIT | 10.31 | 10.29 | 99.78 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of Capcaity 60000 Galon and other allied works under Sonathali W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000318/2021-2022 | 30/PD | 07/01/2022 | 08/03/2022 | MADHU SUDAN RAKSHIT | 10.25 | 8.56 | 83.54 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at OHR Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000224/2021-2022 | 725/RNP | 06/12/2021 | 06/03/2022 | MADHU SUDAN RAKSHIT | 4.21 | 3.91 | 93 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Laying PVC Pipe ,Mending good damage of road, Eath work in filling of Para & Sonathali W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000051/2023-2024 | 675/PD | 17/05/2023 | 16/07/2023 | ZEST INFRACON | 15.56 | 15.54 | 99.9 | 100
18 | PURULIA |  | Purulia Mechanical | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sonathol Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000064/2021-2022 | 109/PMD | 28/02/2022 | 30/03/2022 | R.N.S. TRADING | 20.48 | 6.38 | 31.15 | 100
19 | PURULIA |  | Purulia Mechanical | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Supply delivery and installation of Submersible pump motor ,cable line,Kiosk , MCC allied electro mechanical equipments at Augmentation of sonatholi Water supply scheme Block: kashipur, Under Purulia Mechanical Division PHE Dte. Dist-Purulia. |  | JUNIOR ENGINEER | ORD/000286/2022-2023 | 78/PMD | 01/02/2023 | 02/04/2023 | SUMIT KR. CHAKRABORTY | 25.34 | 15.54 | 61.31 | 20
20 | PURULIA |  | Purulia Mechanical | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Internal and external illumination arrangement at Augmentation Sonathali low lift and High lift Water supply scheme Block: Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000472/2022-2023 | 312/PMD | 16/03/2023 | 15/04/2023 | NUPUR CHANDRA HALDER | 5.13 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 963/PD | 21/06/2022 |  | Resource Division | 33.65 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at Head Work Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000223/2021-2022 | 724/RNP | 06/12/2021 | 06/03/2022 | MADHU SUDAN RAKSHIT | 4.21 | 1.99 | 47.3 | 0
23 | PURULIA |  | Purulia Mechanical | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Providing And Installation of 2 M.T. capacity manually operated curved monorail for Low Lift Pump House and High Lift Pump House under Augmentation of Sonathali Water Supply Scheme, Block: Kashipur, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER |  | ORD/000546/2023-2024 | 379/PMD | 04/03/2024 | 03/05/2024 | S. PATHAK & CO. | 10.22 | 0 | 0 | 0
24 | PURULIA |  | Purulia Mechanical | Augmentation of Sonathali W/S Scheme | SM/09210 | Augmentation | Supply delivery and installation of Horizontal split casing centrifugal pump motor, MCC , Flow meter and All electro mechanical equipments , with allied works for Augmentation Sonathali low lift Water supply scheme Block: Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000287/2022-2023 | 79/PMD | 01/02/2023 | 02/04/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 37.16 | 10.66 | 28.68 | 50
Total | [13 empty] | 524.85 | 102.15 | 19.46