## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bathanbari Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000075/2021-2022 | 160/PMD | 07/03/2022 | 06/04/2022 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 20.5 | 0 | 0 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No-935/2021-22 of EE/PD) |  |  | VCH/000182/2022-2023 | BP-2022-23-65 | 24/05/2022 | 24/05/2022 | KHITISH CHANDRA PATHAK | 4.04 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | SUPPLY DELIVERY & INSTT OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BATHANBARI WATER SUPPLY SCHEME UNDER PMD PHE DTE.(TR.NO 347 OF 2021-22) |  |  | VCH/000087/2022-2023 | C042211590242 | 08/04/2022 | 08/04/2022 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 12.27 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Repairing & renovation of RCC elevated reservoir of capacity 33000 Galon and other allied works under Bathanbari W/ S Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 936/2021-22 of EE/PD) |  |  | VCH/000942/2022-2023 | BP-2022-23-103 | 16/07/2022 | 16/07/2022 | KHITISH CHANDRA PATHAK | 9.76 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.935/EE/PD of 2021-22) |  |  | VCH/001144/2021-2022 | BP-2021-22-300 | 09/03/2022 | 09/03/2022 | KHITISH CHANDRA PATHAK | 33.31 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Construction of swtich room cum chlorine Room at OHR site of Bathanbari W/S Scheme within Raghunathpur Sub- Division (Tender No- 828/2021-22 of EE/PD) |  |  | VCH/000178/2022-2023 | BP-2022-23-54 | 19/05/2022 | 19/05/2022 | KHITISH CHANDRA PATHAK | 4.18 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A (Mouza- Bathanbari,Bhurkundabari under Gunyarae G.P). (1029 Nos.) | Assistant Engineer | Junior Engineer | ORD/000270/2020-2021 | 155/PD | 01/02/2021 | 18/03/2021 | DEBAKI RANJAN SARKAR | 52.24 | 0 | 0 | 0
8 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply Delivery and installation of Submersible pumping machinery, MCC Panel, Voltage stabilizer, flow meter, ilumination arrangement with allied works for augmentation of Bathanbari PWSS under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000092/2022-2023 | 518/PMD | 05/08/2022 | 04/10/2022 | COMBINE ENTERPRISES | 46.66 | 0 | 0 | 82
9 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply delivery and installation of fabricated M.S. structure barge with others allied works at Augmentation of Bathanbari w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000210/2022-2023 | 192/PMSD (W/S) | 22/06/2022 | 13/07/2022 | COMBINE ENTERPRISES | 4.27 | 0 | 0 | 80
10 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply of Tender register, HR (Materials) & contractor ledger (Including Printing & Binding complete set). |  |  | BILL/00831/2023-2024 | BP-2023-24-532 | 07/10/2023 | 07/10/2023 | SOMA PRINTING HOUSE | 0.1 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Additional work by providing Functional Household Tap Connection (FHTC) and other allied works of Bathanbari W/S Scheme of Neturia Block Raghunathpur Sub- Division, PHE Dte. (Tender No-348/2022-23 of EE/PD) |  |  | VCH/001096/2022-2023 | BP-2022-23-192 | 11/08/2022 | 11/08/2022 | KHITISH CHANDRA PATHAK | 4.06 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. |  |  | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 02/08/2023 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
13 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply delivery and installation of 1kg/hr gaseous chlorination system of Aug. of Bathanbari water supply scheme.(Tr.no 347 of 2021-22) |  |  | VCH/000512/2022-2023 | C112206903482 | 10/11/2022 | 10/11/2022 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 3.84 | 0 | 0 | 0
14 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply delivery and installation of 1 kg/hr gaseous chlorination system at Baram High lift for augmentation of Baram Water supply scheme under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000459/2023-2024 | 439/PMD | 11/03/2024 | 10/05/2024 | PINTU DEY | 25.09 | 0 | 0 | 50
15 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Execution of the yield test at Joradih GP in Raghunathpur-II Block within the district of Purulia under code SM10250 under PMD, PHE, Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000330/2022-2023 | 26/PMSD (Drilling) | 02/02/2023 | 17/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
16 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Execution of the yield test at Udyeshpur GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000325/2022-2023 | 24/PMSD (Drilling) | 01/02/2023 | 16/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
17 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Execution of the yield test at Dubra, Para GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000327/2022-2023 | 19/PMSD (Drilling) | 31/01/2023 | 15/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
18 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Execution of the yield test at Lagda, Dimdiha, Sonaijuri GP in Purulia-I Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000324/2022-2023 | 23/PMSD (Drilling) | 01/02/2023 | 16/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Continuation work Order for the work of "Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/01/2023 to 31/12/2023)" | Assistant Engineer | Junior Engineer | ORD/001292/2022-2023 | 699/PD | 20/12/2022 | 20/12/2023 | NIRUPAMA DEY | 1.86 | 0 | 0 | 100
20 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply & delivery of submersible pumping machinery at Bathanbari w/s scheme under PMD, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000263/2023-2024 | 1234/PMD | 08/11/2023 | 23/11/2023 | COMBINE ENTERPRISES | 0.68 | 0 | 0 | 100
21 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply and delivery of submersible pump motor sets at Bathanbari W/S scheme under PMD P.H.E Dte. in the District of Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000481/2023-2024 | 197/PMD | 16/02/2024 | 02/03/2024 | PINTU DEY | 0.6 | 0 | 0 | 100
22 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply and delivery of submersible pump motor sets at Bathanbari w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000495/2023-2024 | 343/PMD | 28/02/2024 | 14/03/2024 | S PATHAK AND CO | 0.6 | 0 | 0 | 100
23 | PURULIA |  | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Supply delivery and installation of Hose pipes and other works at Bathanbari w/s scheme under Purulia Mechanical Division, PHE Dte. in the district Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000531/2023-2024 | 436/PMD | 11/03/2024 | 10/05/2024 | ANUP KUMAR SAHA | 15.88 | 0 | 0 | 50
24 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Xerox copy of original DPR, drawings, mouza map etc for office purpose |  |  | BILL/00557/2024-2025 | BP-2024-25-319 | 20/08/2024 | 20/08/2024 | DUTTA XEROX CENTRE | 1.45 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Bathanbari W/S Scheme | SM/09211 | Augmentation | Hiring charges of broadband at Assistant Engineer, Purulia Sadar Sub- Division, PHE Office |  |  | BILL/00583/2024-2025 | BP-2024-25-334 | 27/08/2024 | 27/08/2024 | PURULIA CABLE & BRODBAND PARISEVA | 0.13 | 0 | 0 | 0
Total | [13 empty] | 247.77 | 0 | 0