## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Distribution system of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub- Division under Purulia Division, PHE Dte (Tender No- 965/2021-22 of EE/PD) |  |  | VCH/000973/2022-2023 | BP-2022-23-143 | 21/07/2022 | 21/07/2022 | ASHOK KUMAR CHATTERJEE | 25.34 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Repairing & renovation of existing pump house cum store room & boundary wall of Lachhyara Piped Water Supply Scheme (Tender No- 968/2021-22 of EE/PD) |  |  | VCH/000154/2022-2023 | BP-2022-23-12 | 07/04/2022 | 07/04/2022 | ASHOK KUMAR CHATTERJEE | 1.12 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Rig Board Tubewell by DTH Method of Lachhiyara piped W/s Scheme. (Tender No.958/EE/PD of 2021-22) |  |  | VCH/001167/2021-2022 | BP-2021-22-362 | 28/03/2022 | 28/03/2022 | ASHOK KUMAR CHATTERJEE | 16.91 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Distribution System of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Tender No.965/EE/PD of 2021-22) |  |  | VCH/000131/2022-2023 | BP-2022-23-9 | 05/04/2022 | 05/04/2022 | ASHOK KUMAR CHATTERJEE | 23.96 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Rig Bored Tubewell by DTH Method of Lachhyara Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | ORD/000322/2021-2022 | 34/PD | 05/01/2022 | 19/02/2022 | ASHOK KUMAR CHATTERJEE | 19.43 | 2.52 | 12.99 | 100
6 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dubra W/S Scheme, Block ¿ Para, & Lachhiyara W/S Schem, Block ¿ Raghunathpur - II) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000442/2020-2021 | 357/G/PD | 25/02/2021 | 27/03/2021 | STEELCONC AND ASSOCIATES | 4.78 | 2.84 | 59.44 | 65
7 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 391/PD | 11/03/2022 | 11/03/2022 | Resource Division | 22.76 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 980/PD | 22/06/2022 | 22/06/2022 | Resource Division | 45.39 | 0 | 0 | 0
9 | PURULIA |  | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Lachayara Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000091/2021-2022 | 189/PMD | 14/03/2022 | 30/12/2024 | M/S ESTERN INDIA SALES AND SERVICE | 20.62 | 19.99 | 96.91 | 80
10 | PURULIA |  | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries, MCC panel with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000302/2022-2023 | 91/PMD | 03/02/2023 | 04/04/2023 | MAHADEV ENTERPRISE | 51.57 | 29.3 | 56.82 | 35
11 | PURULIA |  | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Supply, Delivery and installation of 60KVA oil cooled voltage stabilizer and allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000304/2022-2023 | 92/PMD | 03/02/2023 | 04/04/2023 | EMCON | 6.79 | 5.02 | 73.99 | 75
12 | PURULIA |  | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Supply delivery and installation submersible pumping machineries at new deep tube well and laying of cable line, with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000301/2022-2023 | 90/PMD | 03/02/2023 | 11/01/2025 | KOUSHIK CHATTERJEE | 32.79 | 15.41 | 46.99 | 50
13 | PURULIA |  | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Supply,delivery and installation of Submersible pumping machineries and Al. Armoured cables for Augmentation of Lachhiyar W/S scheme under PMD Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000069/2024-2025 | 997/PMD | 21/06/2024 | 20/08/2024 | M/S UJJAL DIESEL SERVICE | 2.83 | 1.97 | 69.71 | 74
14 | PURULIA |  | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Supply and installation of 30KVA oil cooled voltage stabilizer(at OLD Pump house) and Double tank dosing system Miscellaneous works at under Lachhiyara W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000639/2024-2025 | 1571/PMD | 14/11/2024 | 13/01/2025 | TAPAN KUMAR DEY | 6.97 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Construction of Switch Room Cum Chlorine Room of Lachhyara Pipe Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000338/2021-2022 | 54/PD | 13/01/2022 | 23/04/2022 | ASHOK KUMAR CHATTERJEE | 4.89 | 4.7 | 95.99 | 100
16 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Construction of Pump house for accommodating centrifugal pump for pumping of water including Panel room & Chlorination room at Lachhiyara OHR Site of Lachhiyara W/S Scheme under Raghunathpur Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000853/2022-2023 | 1746/PD | 22/11/2022 | 20/02/2023 | TOTAL INFRA | 19.83 | 17.79 | 89.73 | 100
17 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Lachhiyara OHR campus of Lachhiyara W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000854/2022-2023 | 1752/PD | 22/11/2022 | 22/12/2022 | ASHOK KUMAR CHATTERJEE | 18.32 | 18.31 | 99.96 | 100
18 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Detail Cost Estimate for Over Head Reservoir of capacity 100 cum of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub-Diviasion under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000927/2022-2023 | 1933/PD | 22/12/2022 | 18/09/2023 | KM ENTERPRISES | 60.72 | 47.85 | 78.81 | 100
19 | PURULIA |  | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Yard lighting arrangement with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000186/2023-2024 | 1176/PMD | 03/11/2023 | 02/01/2024 | MOUSUMI BENERJEE | 5.02 | 4.59 | 91.37 | 76
20 | PURULIA |  | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Quotation for new connection |  |  | BILL/00454/2023-2024 | BP-23-24-223 | 05/12/2023 | 05/12/2023 | WBSEDCL PURULIA | 1.87 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | SM/09212 | Augmentation | Distribution System of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000339/2021-2022 | 55/PD | 13/01/2022 | 01/08/2026 | ASHOK KUMAR CHATTERJEE | 85.67 | 10.72 | 12.51 | 82
Total | [13 empty] | 477.57 | 181.01 | 37.9