## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Baram Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2021-2022 | 112/PMD | 28/02/2022 | 30/03/2022 | A G ENTERPRISE | 20.48 | 0 | 0 | 99
2 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Installation of new staircase spiral for OHR & other allied works at Baram W/S Scheme (Tender No-365/EE/PD of 2021-22) |  |  | VCH/000193/2022-2023 | BP-2022-23-48 | 17/05/2022 | 17/05/2022 | SOUMITRA CHAKRABORTY | 3.06 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Repairing of 1 no. horizontal tube well with changing of collecting line and other allied works at Torang river side of Baram W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 239/2022-23 of EE/PD) |  |  | VCH/000994/2022-2023 | BP-2022-23-158 | 27/07/2022 | 27/07/2022 | SOUMITRA CHAKRABORTY | 2.17 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Mankiary,Gundligora,Matkampiri, Torang) (Tender No.875/EE/PD of 2021-22) |  |  | VCH/000187/2022-2023 | BP-2022-23-59 | 20/05/2022 | 20/05/2022 | SOUMITRA CHAKRABORTY | 5.88 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Baram,Thakurshima,Briddhitanr,Jaratanr) (Tender No.874/EE/PD of 2021-22) |  |  | VCH/000186/2022-2023 | BP-2022-23-58 | 20/05/2022 | 20/05/2022 | SOUMITRA CHAKRABORTY | 19.28 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Mankiyari, Torang, Matkompiri, Raipur, Jibandih & Gundligora) Part-B | Assistant Engineer | Junior Engineer-3 | ORD/000111/2020-2021 | 1240/PD | 01/12/2020 | 15/01/2021 | SOUMITRA CHAKRABORTY | 29.89 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Supply and delivery of ferric alum at different water supply scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000436/2021-2022 | 382/PD | 11/03/2022 | 21/03/2022 | ROY CONSTRUCTION | 5.71 | 0 | 0 | 20
8 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Repairing and Renovation of Baram Pump house and Torang Pump House ,riverside) under Purulia Sadar Sub Division under Purulia Division ,PHE .DTE | Assistant Engineer |  | ORD/000064/2022-2023 | 167/PSD | 18/04/2022 | 18/05/2022 | AKUL SUTRADHAR | 4.85 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Construction of 5.0 x 3.0 mtr size Guard Room , approach road, plinth protection, surface drain etc. complete at Mankiyari OHR site for Baram W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000058/2022-2023 | 166/PSD | 18/04/2022 | 18/05/2022 | SOUMITRA CHAKRABORTY | 4.71 | 0 | 0 | 75
10 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Repairing 1 no Horizontal Tubewell at Kansai River at Torang Riverside and other allied works Baram W/S Scheme under Purulia Sadar Sub Division under Purulia Division , PHE Dte.(T/W no-3) | Assistant Engineer |  | ORD/000857/2022-2023 | 1808/Pd | 06/12/2022 | 05/01/2023 | SOUMITRA CHAKRABORTY | 1.73 | 0 | 0 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Supply delivery fitting & fixing of sign board (ACP Sheet) at 10nos site within Purulia District under RWS Purulia Sub-Division PHE Dte.( Part-C) SL NO. 07 | Assistant Engineer |  | ORD/001076/2022-2023 | 97/PR | 28/02/2023 | 30/03/2023 | MRINAL KANTI GORAI | 0.65 | 0 | 0 | 100
12 | PURULIA |  | Purulia Mechanical | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Supply delivery and installation of 100 KVA voltage stabilizer for Augmentation of Baram(River Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000409/2022-2023 | 237/PMD | 03/03/2023 | 02/05/2023 | S. PATHAK & CO. | 10.86 | 0 | 0 | 65
13 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Extension of PVC pipe line in distribution system from Deolghata Pump House to River site Smashan Ghat ( Burning Ghat) with construction of a Stand post for met up the drinking water crisis under Joypur Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000189/2023-2024 | 4681/PSD | 27/07/2023 | 06/08/2023 | APEX TRADERS | 0.29 | 0 | 0 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Withdrawing of 150 mm dia.G.I. damaged Collecting line & newly laying of 160 mm dia HDPE Pipe line as Collecting line and 40 mm dia G.I. Guard Pilling at river bed of Kansai near Deolghata of Joypur Water Supply Scheme at Joypur Block under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000184/2023-2024 | 4674/PSD | 27/07/2023 | 06/08/2023 | APEX TRADERS | 0.78 | 0 | 0 | 100
15 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) | Assistant Engineer |  | ORD/001298/2022-2023 | 308-PR | 29/06/2022 | 29/06/2023 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
16 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) | Assistant Engineer |  | ORD/001299/2022-2023 | 309_PR | 29/06/2022 | 29/06/2023 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
17 | PURULIA |  | Purulia Mechanical | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 619/PMD | 01/06/2023 | 01/06/2023 | Resource Division | 1.55 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Bill paid for due to awareness program in the ocation of Independence Day organised by DPMU. |  |  | BILL/01228/2023-2024 | BP-2023-24-715 | 13/12/2023 | 13/12/2023 | ANUDIP SAHA | 0.54 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Bill payment to Sri Krishna Computer against bill no.010/2023-24 to 017/2023-24 |  |  | BILL/00996/2023-2024 | BP-2023-24-629 | 17/10/2023 | 17/10/2023 | SRI KRISHNA COMPUTER | 0.63 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Construction of 5.0 x 3.0 mtr size Guard Room, plinth protection, surface drain etc.complete at Sirkabad OHR Site for Sirkabad W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. |  |  | ORD/001811/2023-2024 | 35/PD | 08/01/2024 | 17/04/2024 | KABERI DUTTA | 5.05 | 0 | 0 | 0
21 | PURULIA |  | Purulia Mechanical | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Supply delivery and installation of 1 kg/hr gaseous chlorination system at Baram High lift for augmentation of Baram Water supply scheme under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000459/2023-2024 | 439/PMD | 11/03/2024 | 10/05/2024 | PINTU DEY | 25.09 | 0 | 0 | 50
22 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | New sinking of 01 (One) nos. 200 mm dia river bed tubewell (Horizontal) at Kansai river alongwith laying of 100 mm dia G.I. collecting line with all allied works at Baram W/S Scheme under Purulia Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer-3 | ORD/000837/2022-2023 | 1739/PD | 22/11/2022 | 22/12/2022 | SOUMITRA CHAKRABORTY | 8.91 | 0 | 0 | 100
23 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | New sinking of 02 (Two) nos. 200 mm dia river bed tubewell (Horizontal) at Kansai river alongwith laying of 100 mm dia G.I. collecting line with all allied works at Baram W/S Scheme under Purulia Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer-3 | ORD/000836/2022-2023 | 1738/PD | 22/11/2022 | 22/12/2022 | SOUMITRA CHAKRABORTY | 18.35 | 0 | 0 | 100
24 | PURULIA |  | Purulia Mechanical | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Baram(River Side) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000408/2022-2023 | 236/PMD | 03/03/2023 | 02/05/2023 | SUMIT KR. CHAKRABORTY | 11.33 | 0 | 0 | 20
25 | PURULIA |  | Purulia Division | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Computer service & spare parts supply bill paid. |  |  | BILL/01379/2023-2024 | BP-2023-24-750 | 05/01/2024 | 05/01/2024 | SRI KRISHNA COMPUTER | 0.65 | 0 | 0 | 0
26 | PURULIA |  | Purulia Mechanical | Augmentation of Baram Water Supply Scheme | SM/09213 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Baram(River Side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2023-2024 | 522/PMD | 05/05/2023 | 01/01/2025 | P K ENGINEERING | 39.21 | 0 | 0 | 100
Total | [13 empty] | 227.36 | 0 | 0