## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation - Balitora (112 Nos.) | Assistant Engineer |  | ORD/000206/2020-2021 | 23/RNP | 11/01/2021 | 26/01/2021 | TUMPA GORAIN | 4.78 | 0.26 | 5.35 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Bakuliashota, Habitation -Bakulia (16 Nos.), Mouza- Shunuri, Habitation - Uppardi (46 Nos.), Mouza- Ektira, Habitation -Berakural-(1),Ektira (48 Nos.), Mouza- Kashtagora Habitation -Chapabera Chak-(1) | Assistant Engineer | Junior Engineer | ORD/000227/2021-2022 | 729/RNP | 06/12/2021 | 26/12/2021 | MS MITRA SENGUPTA ENTERPRISES | 1.09 | 0.44 | 40.04 | 100
3 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Probable estimate for shifting of under ground HDPE & DI pipe line including supplying & laying HDPE & DI pipe of Distribution line with allied works from Kapashdanga Village end to Mokra Pry. School through Jagannathdih & Saluni Village under Zone-II of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/000330/2021-2022 | 38/PD | 07/01/2022 | 30/06/2025 | KHITISH CHANDRA PATHAK | 34.11 | 0 | 0 | 75
4 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Repairing and Renovation of 3 (three) Nos. Over Head Reservoir (Capcaity 180cum at Bakulia, 70 cum near Mokra and 120 cum at Barsal) and other allied works under Balitora W/S scheme (Zone-I, II & III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000334/2021-2022 | 42/PD | 07/01/2022 | 08/03/2022 | SANTANU BANERJEE | 13.21 | 10.56 | 79.94 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Shifting of Rising Main of underground DI pipe line including supplying & laying of DI pipe from Jagannathdih more to boundary wall of Barshal OHR (Zone-III) of Balitora W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000871/2022-2023 | 1839/PD | 12/12/2022 | 26/01/2023 | M/S SAYAK BHATTACHARYA | 23.27 | 13.24 | 56.87 | 30
6 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Providing FHTC & Supplying & laying different dia HDPE pipe line of distribution linewith allied works from OHR (zone-1) site to Mathorgoria village More & Balitora bauripara end to bramhan para of Balitora village under zone-I of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Mouza- Balitora, Habitation :-Balitora) | Assistant Engineer | Junior Engineer | ORD/000328/2021-2022 | 36/PD | 07/01/2022 | 08/03/2022 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 37.4 | 21.2 | 56.69 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Mokra village more to Jadudi village under (zone-II) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000329/2021-2022 | 37/PD | 07/01/2022 | 06/02/2022 | SANDIP KUMAR DUBEY | 7.54 | 0 | 0 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Dandahit Bauro para to Danesdih village & end of Batka village to Syaldanga village &Kastagora village (zone-II1) site under (zone-III) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000332/2021-2022 | 40/PD | 07/01/2022 | 06/02/2022 | M/S. S.P CONSTRUCTION | 10.77 | 0.43 | 3.98 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Repairing and renovation of existing structure excluding OHR under Balitora W/S Scheme (Zone-I, II & III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000333/2021-2022 | 41/PD | 07/01/2022 | 08/03/2022 | SANTANU BANERJEE | 14.26 | 11.3 | 79.24 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution line with allied works from Dandahit Bauri Para to Danesdih Village & end of Batka Village to Siyaldanga Village & Kastagora Village (Zone-III) of Balitora W/S Scheme under Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000594/2022-2023 | 488/RNP | 28/07/2022 | 17/08/2022 | M/S. S.P CONSTRUCTION | 4.81 | 4.78 | 99.34 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Functional House Hold Tap Connection (FHTC) at Deuli and supplying & laying different dia HDPE pipe line of distribution line with allied works at Sunuri & Upardih village (Zone-1) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000388/2022-2023 | 346/RNP | 01/06/2022 | 21/06/2022 | AMIT PATHAK | 3.87 | 3.79 | 97.86 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 957/PD | 20/06/2022 | 20/06/2022 | Resource Division | 26.31 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 977/PD | 22/06/2022 | 22/06/2022 | Resource Division | 143.77 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Additional work for Functional House Hold Connection (FHTC) in connection with other allied works of Baltora W/s Scheme at Santuri Block (Mouza- Sunuri, Habitation-Sunuri) [Part-I] (Tender No.908/EE/PD of 2021-22) |  |  | VCH/001020/2021-2022 | BP-2021-22-263 | 28/02/2022 | 28/02/2022 | RAHIBUDDIN MONDAL | 3.75 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block at Mouza- Dandahit Habitation-Batka, Dandahit (Tender No- 855/2021-22 of EE/PD) |  |  | VCH/001182/2021-2022 | BP-2021-22-327 | 22/03/2022 | 22/03/2022 | ROY CONSTRUCTION | 0.54 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supplying and laying different dia HDPE pipe line of Distribution line with allied works from Makra village more to Jadudih village under (Zone-II) Balitora W/s Scheme. (Tender No.995/EE/PD of 2021-22) |  |  | VCH/001121/2021-2022 | BP-2021-22-384 | 28/03/2022 | 28/03/2022 | SANDIP KUMAR DUBEY | 5.73 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Deuli, Hab-Deuli, Mouza-Suburi, Hab-Santuri. (Tender No- 803/EE/PD of 2021-22) |  |  | VCH/001198/2021-2022 | BP-2021-22-321 | 22/03/2022 | 22/03/2022 | SK ABBAS | 4.28 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Deuli, Habitation - Deuli (70 Nos.), Mouza-Sunuri, Habitation - Sunuri (42 Nos.) (Tender No.348/EE/PD of 2020-21) |  |  | VCH/000160/2022-2023 | BP-2022-23-25 | 07/04/2022 | 07/04/2022 | SK ABBAS | 1.01 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Providing FHTC supplying & laying different dia HDPE pipe line under zone-I of Balitora W/S Scheme (Tender No- 934/2021-22 of EE/PD) |  |  | VCH/000035/2022-2023 | BP-2022-23-20 | 07/04/2022 | 07/04/2022 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 9.81 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub- Division, PHE Dte. at Mouza- Balitora, Habitation- Begergoria (24) Balitora (88) Nos. (Tender No:- 281/EE/PD of 2020-21) |  |  | VCH/000980/2022-2023 | BP-2022-23-147 | 25/07/2022 | 25/07/2022 | SUDHANSHU OJHA | 0.26 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Probable estimate for sifting of ground HDPE & DI pipe line including supplying & DI pipe of Distribution line with allied works from Kapasdanga Village end to Mokra Pry. School through Jagannathdih & Saluni Village under Zone-II of Balitora W/s Scheme. (Tender No.937/EE/PD of 2021-22) |  |  | VCH/001161/2021-2022 | BP-2021-22-363 | 28/03/2022 | 28/03/2022 | KHITISH CHANDRA PATHAK | 16.39 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Balitora, Habitation- Bagergoria (24) Nos. Balitora (88) Nos. (Tender No:- 802/EE/PD of 2021-22) |  |  | VCH/000976/2022-2023 | BP-2022-23-146 | 25/07/2022 | 25/07/2022 | SUDHANSHU OJHA | 1.29 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tubewell (T/W No.- 5 & 6) alongwith necessary 100 mm dia GI collecting line in connection with FHTC from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Balitora under Balitora W/S Scheme under Raghunathpur Sub Division, under Purulia Division PHE Dte. PHE Dte. (Tender No.404/EE/PD of 2020-21) |  |  | VCH/001010/2021-2022 | BP-2021-22-252 | 25/02/2022 | 25/02/2022 | ASHOK KUMAR CHATTERJEE | 19.66 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation - Balitora (112 Nos.) (Tender No- 804/EE/PD of 2021-22) |  |  | VCH/001197/2021-2022 | BP-2021-22-338 | 25/03/2022 | 25/03/2022 | TUMPA GORAIN | 2.14 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Additional work for Functional Household Tap Connection FHTC including other allied works of Balitora Water supply Scheme at Santuri Block part- II [Tender No- 907/2021-22 of EE/PD) |  |  | VCH/001150/2021-2022 | BP-2021-22-276 | 03/03/2022 | 03/03/2022 | RAHIBUDDIN MONDAL | 0.93 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supplying and laying different dia HDPE pipe line of distribution line with allied works from Dandahit Bauro Para to Danesdih village & end of Batka village to Syaldanga village & kastagora village (Zone-III) site under (Zone-III) of Balitora W/S Scheme of Raghunathpur Sub- Division under Purulia Division PHE Dte. (Tender No- 948/2021-22 of EE/PD) |  |  | VCH/000884/2022-2023 | BP-2022-23-80 | 01/07/2022 | 01/07/2022 | M/S. S.P CONSTRUCTION | 10.16 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Balitora Water Supply Scheme of Santuri Block of Raghunathpur Sub- Division under Purulia Division, PHE Dte. at mouza- Balitora, Habitation- Balitora (108) nos. (Tender No- 288/20-21 of EE/PD) |  |  | VCH/000987/2022-2023 | BP-2022-23-152 | 26/07/2022 | 26/07/2022 | NANIGOPAL DEY | 0.36 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Shifting of under ground HDPE & DI pipe line including supplying & laying HDPE & DI pipe of distribution line with allied works from Manpur Pry. School to Ektira Village end under Zone-III of Balitora W/S Scheme of Raghunathpur Sub-Division, PHE Dte. (Tender No. 923/EE/PD of 2021-22) |  |  | VCH/000949/2022-2023 | BP-2022-23-111 | 16/07/2022 | 16/07/2022 | BASANTA KUMAR SINGHADEO | 7.33 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Mokra village more to Jadudi village under (zone-II) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Tender No.995/EE/PD of 2021-22) |  |  | VCH/001015/2022-2023 | BP-2022-23-295 | 23/09/2022 | 23/09/2022 | SANDIP KUMAR DUBEY | 1.79 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Potable estimate for Shifting of under ground HDPE & DI pipe line including supplying & laying HDPE & DI pipe of distribution line with allied works from Kapasdanga village end to Mokra Pry. School through Jagannathdih & Saluni village under Zone-II of Balitora W/S Scheme of Raghunathpur Sub-Division, PHE Dte. (Tender No. 937/EE/PD of 2021-22) |  |  | VCH/000988/2022-2023 | BP-2022-23-153 | 26/07/2022 | 26/07/2022 | KHITISH CHANDRA PATHAK | 5.49 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Dandahit Bauro para to Danesdih village & end of Batka village to Syaldanga village &Kastagora village (zone-II1) site under (zone-III) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (T/N-948/21-22) |  |  | VCH/000241/2022-2023 |  | 05/07/2022 | 05/07/2022 | M/S. S.P CONSTRUCTION | 10.16 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | FHTC including other allied works of Baltora W/S Scheme at Santuri block (Tender No- 262/2020-21 of EE/PD) |  |  | VCH/000194/2022-2023 | BP-2022-23-47 | 17/05/2022 | 17/05/2022 | MADHU SUDAN RAKSHIT | 4.62 | 0 | 0 | 0
33 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Additional works for Functional Household Tap Connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block Raghunathpur Sub_Division under Purulia Division PHE Dte. Mouza- Dandahit, Hab-Dandahit (112 Nos) (Tender No.823/EE/PD of 2021-22) |  |  | VCH/001131/2021-2022 | BP-2021-22-317 | 22/03/2022 | 22/03/2022 | SIKHA ENTERPRISES | 2.01 | 0 | 0 | 0
34 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Shifting of underground HDPE & DIpipe line including supplying & laying HDPE & DI pipe of Distribution line with allied works from Manpur Pry. School to Ektira Village end under Zone-III of Balitora W/s Scheme. (Tender No.923/EE/PD of 2021-22) |  |  | VCH/001163/2021-2022 | BP-2021-22-349 | 28/03/2022 | 28/03/2022 | BASANTA KUMAR SINGHADEO | 14 | 0 | 0 | 0
35 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation - Balitora (112 Nos.) (Tender No.804/EE/PD of 2021-22) |  |  | VCH/000597/2022-2023 | BP-2022-23-311 | 26/09/2022 | 26/09/2022 | TUMPA GORAIN | 0.97 | 0 | 0 | 0
36 | PURULIA |  | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supply delivery and installation of 125 KVA voltage stabilizer for Augmentation of Balitora water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000404/2022-2023 | 232/PMD | 03/03/2023 | 02/05/2023 | ASHOKE ADHIKARY | 12.85 | 12.85 | 100 | 80
37 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | New Sinking of 4 (Four) Nos 200 mm dia river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line in connection with FHTC from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Balitora under Balitora W/S Scheme under Raghunathpur Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001195/2022-2023 | 467/PD | 28/03/2023 | 12/05/2023 | KHITISH CHANDRA PATHAK | 15.93 | 5.18 | 32.5 | 100
38 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Chowkage clearence of Distribution line at Deuli village and shifting of DI, GI, MS Pipe from Manbazar Pump house site to Balitora Zone-I OHR campus under Balitora W/S Scheme (Zone-I) Raghunathpur Sub-Divn, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000501/2023-2024 | 396/RNP | 05/09/2023 | 20/09/2023 | M/S SAYAK BHATTACHARYA | 0.96 | 0.95 | 99.13 | 100
39 | PURULIA |  | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Balitora w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000133/2023-2024 | 648/PMD | 08/06/2023 | 07/08/2023 | PREMNATH MITRA | 12.15 | 11.87 | 97.73 | 91
40 | PURULIA |  | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, MCC panel Flowmeter and other allied works for augmentation of Balitora water supply scheme under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000033/2023-2024 | 438/PMD | 19/04/2023 | 18/06/2023 | PREMNATH MITRA | 46.28 | 46.21 | 99.84 | 90
41 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. |  |  | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 02/08/2023 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
42 | PURULIA |  | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Enhancement of contractual demand from 71 KVA to 0.4 KV to 120/120/120/120/120 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o The Ex.Engg PMD PHE Dte.(Consumer ID : 950006038) to their premises at Balitora Water Supply Scheme |  |  | BILL/00042/2022-2023 |  | 28/02/2023 | 28/02/2023 | WBSEDCL PURULIA | 6.74 | 0 | 0 | 0
43 | PURULIA |  | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Miscellaneous collection for Indian Railways against invoice ID No.WL00000000038190 dt.02-03-2024. |  |  | BILL/01880/2023-2024 | BP-2023-24-867 | 08/03/2024 | 08/03/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
44 | PURULIA |  | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Payment of new Electric service connection charge to WBSEDCL ,Santuri CCC at Santuri Mouja ( O.H.R. No.2 under Balitora W.S.Scheme ) ,application no.- 2004753984 , Ref. Id.- 204318171 , Contact Demand - 1330 watt . |  |  | BILL/00173/2024-2025 | BP-24-25-41 | 02/07/2024 | 02/07/2024 | SANTURI CCC | 0.05 | 0 | 0 | 0
45 | PURULIA |  | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Payment for New Electric connection charge at Madhukunda O.H.R. Site , Mouja : Madhukunda under Augmentation of Balitora Water Supply to Santuri CCC of WBSEDCL . |  |  | BILL/00147/2024-2025 | BP-24-25-26 | 11/06/2024 | 11/06/2024 | SANTURI CCC | 0.94 | 0 | 0 | 0
46 | PURULIA |  | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Payment for New Service Connection charge at Manpur , JL - 31 , Plot - 479 under Purulia Mechanical Division P.H.E. Dte. to WBSEDCL , Purulia , Santuri CCC . |  |  | BILL/00177/2024-2025 | BP-24-25-42 | 02/07/2024 | 02/07/2024 | SANTURI CCC | 3.6 | 0 | 0 | 0
47 | PURULIA |  | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme | SM/09214 | Augmentation | Enhancement of the contract demand from 71 KVA at 0.4 KV to 120/120/120/120/120 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Balitora Water Supply |  |  | BILL/00867/2023-2024 | BP-23-24-310 | 21/03/2024 | 21/03/2024 | WBSEDCL PURULIA | 11.11 | 0 | 0 | 0
Total | [13 empty] | 561.88 | 143.04 | 25.46