## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Baghmundi W/S Scheme Ajodhya W/s Scheme, Block Baghmundi) to be Augmentation / Rejuvenation under Purulia Division P.H.E. Dte. (Tender No.361/EE/PD of 2021-22) |  |  | VCH/001213/2021-2022 | BP-2021-22-370 | 30/03/2022 | 30/03/2022 | ROY CHOWDHURY ASSOCIATES | 2.34 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_ Division under Purulia Division PHE Dte. (Part-B: Water supply through direct pumping) (Tender No.18/SE/PMU of 2021-22) |  |  | VCH/001172/2021-2022 | BP-2021-22-344 | 28/03/2022 | 28/03/2022 | KOUSHIK CHATTERJEE | 34.28 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | SUPPLY DELIVERY & INSTTALATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BAHGMUNDI W/S SCHEME , BAGHMUNDI BLOCK UNDER PMD PHE DTE.(TR.NO 344 OF 2021-22) |  |  | VCH/000100/2022-2023 | C042249065860 | 29/04/2022 | 29/04/2022 | COMBINE ENTERPRISE | 3.54 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-A : Water supply through OHR) |  |  | VCH/000714/2022-2023 |  | 12/10/2022 | 12/10/2022 | NIBHAS SINHA | 39.62 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-A : Water supply through OHR) (Tender No.19/SE/PMU of 2021-22) |  |  | VCH/000135/2022-2023 | BP-2022-23-4 | 05/04/2022 | 05/04/2022 | NIBHAS SINHA | 44.89 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-B : Water supply through OHR) (Tender No- 19/2021-22 of SE/PMU/WBPWSP(P) ) |  |  | VCH/001049/2022-2023 | BP-2022-23-393 | 19/10/2022 | 19/10/2022 | NIBHAS SINHA | 39.62 | 0 | 0 | 0
7 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | SUPPLY DELIVERY AND INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BAGHMUNDI WATER SUPPLY SCHEME UNDER PMD PHE DTE.(TR.NO 344 OF 2021-22) |  |  | VCH/000083/2022-2023 | C042211560768 | 08/04/2022 | 08/04/2022 | COMBINE ENTERPRISE | 12.25 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_ Division under Purulia Division PHE Dte. (Part-B : Water supply through direct pumping) | Assistant Engineer | Junior Engineer | ORD/000380/2021-2022 | 182/PD | 31/01/2022 | 17/03/2022 | KOUSHIK CHATTERJEE | 146.44 | 0 | 0 | 65
9 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Laying of 150 mm dia DI Rising Main in connection with Jal Jeevan Mission (JJM) for Augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001151/2022-2023 | 425/PD | 21/03/2023 | 05/05/2023 | KOUSHIK CHATTERJEE | 20.22 | 0 | 0 | 55
10 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supplying delivery fitting& fixing 20 Nos of Sign board (ACP Sheet)at different solar tubewell site within Bagmundi Block in Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001227/2022-2023 | 249/PSD | 31/03/2023 | 05/04/2023 | R.K ENTERPRISE | 0.46 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Repairing and Renovation of Boundary wall including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000170/2023-2024 | 941/PD | 19/07/2023 | 18/08/2023 | ROY CONSTRUCTION | 6.72 | 0 | 0 | 32
12 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Baghmundi Water Supply scheme Block Baghmundi under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000065/2021-2022 | 110/PMD | 28/02/2022 | 30/03/2022 | COMBINE ENTERPRISE | 20.48 | 0 | 0 | 100
13 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supply delivery and installation of external lighting and other allied works for Baghmundi (High Lift) water supply scheme under PMD PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000185/2022-2023 | 755/PMD | 07/11/2022 | 07/12/2022 | SUBRATA DUTTA | 4.01 | 0 | 0 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supplying delivery fitting& fixing 30 Nos of Sign board (ACP Sheet)at different solar tubewell site within Bagmundi Block in Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001226/2022-2023 | 248/PSD | 31/03/2023 | 05/04/2023 | R.K ENTERPRISE | 0.68 | 0 | 0 | 100
15 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Augmentation of Barge and floating walkway with required MS work by necessary supply of materials and other allied works for Augmentation of Bagmundi W/S scheme under PMD PHE Dte in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000051/2023-2024 | 520/PMD | 05/05/2023 | 04/07/2023 | ASHOKE ADHIKARY | 19.46 | 0 | 0 | 21
16 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(Intake Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000075/2023-2024 | 562/PMD | 16/05/2023 | 15/07/2023 | H K DAS AND CO | 16.75 | 0 | 0 | 100
17 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Repairing & Restoration work including supplying & laying of HDPE Piped Distribution Main with other allied work under Baghmundi W/S Scheme under Purulia Sadar Sub-Divn, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000190/2023-2024 | 4682/PSD | 27/07/2023 | 11/08/2023 | SB CONSTRUCTION | 0.96 | 0 | 0 | 100
18 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 1508/PD | 13/12/2021 | 13/12/2021 | Resource Division | 82.12 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 395/PD | 11/03/2022 | 11/03/2022 | Resource Division | 4.32 | 0 | 0 | 0
20 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Load Enhancement for Augmentation of Baghmundi |  |  | BILL/00250/2023-2024 | BP-2023-24-152 | 14/09/2023 | 14/09/2023 | WBSEDCL PURULIA | 3.86 | 0 | 0 | 0
21 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | New Connection for Augmentation of Baghmundi |  |  | BILL/00249/2023-2024 | BP-2023-24-153 | 14/09/2023 | 14/09/2023 | WBSEDCL PURULIA | 6.08 | 0 | 0 | 0
22 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(CWR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000402/2022-2023 | 230/PMD | 03/03/2023 | 02/05/2023 | SUBRATA DUTTA | 40.32 | 0 | 0 | 75
23 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Shifting of distribution pipeline and existing 95 Nos FHTC due to widening & strengthening work of PWDte along Gobondapur to Ajodhya More under Baghmundi water supply scheme at Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001325/2023-2024 | 1711/PD | 04/12/2023 | 02/02/2024 | NIBHAS SINHA | 13 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 185 Cum (Intze Type) including other allied works at OHR site of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000258/2021-2022 | 1531/PD | 13/12/2021 | 11/06/2022 | MANATOSH SINGH | 6.22 | 0 | 0 | 100
25 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000459/2021-2022 | 421/PD | 17/03/2022 | 25/06/2022 | ANIL GORAI | 13.72 | 0 | 0 | 100
26 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Baghmundi WTP site for Augmentation of Baghmundi W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001216/2022-2023 | 504/PD | 31/03/2023 | 29/06/2023 | ROY CONSTRUCTION | 13.76 | 0 | 0 | 100
27 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Baghmundi OHR site for Augmentation of Baghmundi W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000011/2023-2024 | 539/PD | 12/04/2023 | 21/07/2023 | TOTAL INFRA | 13.85 | 0 | 0 | 100
28 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Bagmundi w/s scheme( WTP and OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000128/2023-2024 | 866/PMD | 21/07/2023 | 19/09/2023 | ASHOKE ADHIKARY | 3.05 | 0 | 0 | 100
29 | PURULIA |  | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-A : Water supply through OHR) | Assistant Engineer |  | ORD/000386/2021-2022 | 208/PD | 01/02/2022 | 18/03/2022 | NIBHAS SINHA | 148.62 | 0 | 0 | 100
30 | PURULIA |  | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | SM/09215 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000401/2022-2023 | 229/PMD | 03/03/2023 | 02/05/2023 | PINTU DEY | 22.94 | 0 | 0 | 70
Total | [13 empty] | 784.56 | 0 | 0