## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supply delivery and installation of Submersible pumping machineries with all ancillaries & auxiliaries for augmentation of Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000094/2022-2023 | 520/PMD | 05/08/2022 | 04/09/2022 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 31.83 | 31.18 | 97.96 | 100
2 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries,with all ancillaries & auxiliaries including allied works for augmentation of Ajodhya Water Supply Scheme,under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000100/2022-2023 | 527/PMD | 05/08/2022 | 04/09/2022 | SWAPAN ENTERPRISE | 9.45 | 8.8 | 93.12 | 100
3 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Baghmundi W/S Scheme & Ajodhya W/S Scheme block-Baghmundi) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 361/2021-22 of EE/PD) |  |  | VCH/000936/2022-2023 | BP-2022-23-107 | 16/07/2022 | 16/07/2022 | ROY CHOWDHURY ASSOCIATES | 2.18 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-I) (Tender No- 921/2021-22 of EE/PD) (Ad- Interim Payment) |  |  | VCH/000158/2022-2023 | BP-2022-23-21 | 07/04/2022 | 07/04/2022 | TUMPA GORAIN | 5.36 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-I) (Tender No- 921/2021-22 of EE/PD) |  |  | VCH/000159/2022-2023 | BP-2022-23-22 | 07/04/2022 | 07/04/2022 | TUMPA GORAIN | 2.18 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 cum with other allied works at Ajodhya W/s Scheme. (Tender No.859/SE/PMU of 2021-22) |  |  | VCH/001173/2021-2022 | BP-2021-22-346 | 28/03/2022 | 28/03/2022 | TUMPA GORAIN | 9.64 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supplying and Laying and extention of distribution pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-II) (Tender No- 176/2022-23 of EE/PD) |  |  | VCH/001062/2022-2023 | BP-2022-23-415 | 28/10/2022 | 28/10/2022 | SADHAN GORAIN | 67.17 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Laying of Collecting main Line From TubeWell to Main Rising Main of Ajodhya W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000611/2022-2023 | 508/PSD | 12/08/2022 | 21/09/2022 | TUMPA GORAIN | 4.85 | 4.82 | 99.5 | 0
9 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Ajodhya Water Supply scheme Block Baghmundi under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000021/2022-2023 | 320/PMD | 17/05/2022 | 16/06/2022 | ALPHA ENTERPRISES | 20.5 | 20.49 | 99.96 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Laying of PVC Line For CRPF Camp& Ajodhya Girls Hostel & Shifting of GI Line For Construction New CWR at OHR Campus of Ajodhya W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000618/2022-2023 | 515/PSD | 12/08/2022 | 26/09/2022 | TUMPA GORAIN | 1.68 | 1.67 | 99.41 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Construction of Tank plateform, parapet wall, repairing & renovation gr floor staff room and sanitary Plumbing work of Ajodhya Bunglow under Ajodhya W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. under JJM & Jal Sapna. | Assistant Engineer |  | ORD/000616/2022-2023 | 513/PSD | 12/08/2022 | 26/09/2022 | TUMPA GORAIN | 2.09 | 0 | 0 | 85
12 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Electrification and Rectification of lighting arrangement at pump house with other allied works for Augmentation at Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia . | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000285/2022-2023 | 76/PMD | 01/02/2023 | 02/04/2023 | BISHWANATH NANDI | 5.77 | 5.66 | 98.09 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Pushing of 600mm dia RCC pre cast pipe and 100 mm dia GI . water carrier pipe by hydraulic jacking method across Sirkabad-Ajodhya- Baghmundi PWD Road for laying Distribution Main for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) Near Ajodhya OHR site, Bagandi mor and Matakamdi PWD branch Road Junction for Ajodhya W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/001058/2022-2023 | 290/PD | 27/02/2023 | 13/04/2023 | MS GORAIN CONCERN | 19.12 | 19.05 | 99.64 | 100
14 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Ajodhya W/S Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000061/2021-2022 | 107/PMD | 28/02/2022 | 30/03/2022 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 20.4 | 20.37 | 99.84 | 100
15 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supplying hoisting & placing of PVC tank (10000 ltr 2 nos) over MS structural OHR and other allied work at Ajodhya OHR site of Ajodhya W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 870/PD | 30/06/2023 | 30/07/2023 | SARKAR ENTERPRISE | 2.43 | 2.37 | 97.71 | 100
16 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Construction of tank platform, parapet wall, repairing & renovation Ground floor staff and sanitary plumbing work of Ajodhya Bunglow under Ajodhya W/S Scheme of Purulia Sadar Sub- Division, PHE Dte. under JJM & Jalswapna [Tender No 550/2022-2023 of EE/PD] |  |  | VCH/001533/2022-2023 | BP-2022-23-834 | 27/03/2023 | 27/03/2023 | TUMPA GORAIN | 1.63 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. |  |  | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 02/08/2023 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
18 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supply delivery and installation of submersible pumping machinery for Direct Pumping with Flow meter for Augmentation of Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000136/2023-2024 | 903/PMD | 04/08/2023 | 03/09/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 7.54 | 6.47 | 85.74 | 90
19 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Laying of dedicated distribution line for providing FHTC at kotalmara habitation, bursabera habitation & chhatni habitation under Augmentation of Ajodhya water supply scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001327/2023-2024 | 1712/PD | 04/12/2023 | 02/02/2024 | TUMPA GORAIN | 31.22 | 25.58 | 81.94 | 100
20 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | New Construction of Boundary wall & Repairing of DI Rising Main at Ajodhya Pump House Site under Purulia Sadar Sub-Division under Purulia Division,PHE Dte. | Assistant Engineer(HQ) | Junior Engineer-1 | ORD/001872/2023-2024 | 97/PD | 15/01/2024 | 16/03/2025 | BOSE CONSTRUCTION | 15.05 | 2.21 | 14.68 | 40
21 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supply, delivery and installation of Open well Submersible pumping machinery, MCC Panel with others electro-mechanical work at Manbazar Baludih for Augmentation of Manbazar PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000052/2024-2025 | 970/PMD | 20/06/2024 | 19/08/2024 | M/S D. PALIT & CO. | 11.74 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-I) | Assistant Engineer | Junior Engineer | ORD/000336/2021-2022 | 44/PD | 07/01/2022 | 21/02/2022 | TUMPA GORAIN | 18.54 | 10.89 | 58.77 | 100
23 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supplying and Layingand extention of distribution pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-II) | Assistant Engineer | Junior Engineer | ORD/000335/2021-2022 | 43/PD | 07/01/2022 | 08/03/2022 | SADHAN GORAIN | 92.36 | 20.8 | 22.52 | 100
24 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Providing FHTC at Kalafulia village under Ajodhya water supply scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000927/2023-2024 | 4856/PSD | 29/09/2023 | 09/10/2023 | MOUSUMI BANERJEE | 1 | 0.78 | 78.42 | 100
25 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Extention of distribution line for providing FHTC at Sitakunda to Bagandih&Kuchlirakha habitation under Ajodhya water supply scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001618/2023-2024 | 1829/PD | 12/12/2023 | 10/02/2024 | TUMPA GORAIN | 11.01 | 9.33 | 84.72 | 100
26 | PURULIA |  | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Laying of distribution pipeline from Gobria to Puniasashan & providing FHTC at Puniasashan & Churingsarang village & other allied works at Ajodhya water supply scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001492/2023-2024 | 1803/PD | 08/12/2023 | 06/02/2024 | ANUDIP SAHA | 12.87 | 10.95 | 85.07 | 100
27 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Construction of Big Dia R.B.T.W (200 mm × 165 mm) at Ajodhya Hill top of Bagmundi block in Purulia district under Purulia Mechanical Division PHE, Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000457/2023-2024 | 437/PMD | 11/03/2024 | 10/04/2024 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 14.57 | 13.45 | 92.34 | 90
28 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Construction of Rig Bore tubewell (200mm x 165 mm) by DTH method at Ajodhya for Ajodhya PWSS under Purulia Mechanical Division, P.H.Engineering Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000680/2024-2025 | 1692/PMD | 06/12/2024 | 05/01/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.94 | 1.73 | 58.83 | 90
29 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supply, delivery and installation of Voltage stabilizer with other allied work at low lift P/H no. 3 & 4 of Augmentation of Ajodhya water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000618/2024-2025 | 1540/PMD | 11/11/2024 | 06/05/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 5.42 | 0 | 0 | 80
30 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supply, delivery and installation of Submersible pumping machinery with other allied work at Newly sunk T/W of Augmentation of Ajodhya water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000579/2024-2025 | 1437/PMD | 01/10/2024 | 03/05/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 11.87 | 0 | 0 | 90
31 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Indoor & outdoor illumination arrangement with others electro-mechanical work at Ajodhya water supply scheme (Low lift) for Augmentation of Ajodhya PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000230/2024-2025 | 1224/PMD | 13/08/2024 | 04/05/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 6.95 | 0 | 0 | 30
32 | PURULIA |  | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | SM/09217 | Augmentation | Supply, delivery and installation of 75 KVA Voltage stabilizer with other allied work at High lift site of Augmentation of Ajodhya water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000047/2024-2025 | 966/PMD | 20/06/2024 | 28/02/2025 | BISHWANATH NANDI | 10.31 | 8.81 | 85.44 | 85
Total | [13 empty] | 460.35 | 225.41 | 48.97