## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Beldi Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000080/2021-2022 | 165/PMD | 07/03/2022 | 06/04/2022 | DEBJYOTI BASU | 20.5 | 0 | 0 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Tumba-Jhalda, Gouradag & Jhariadih) Part-B | Assistant Engineer | Junior Engineer-3 | ORD/000114/2020-2021 | 1241/PD | 01/12/2020 | 15/01/2021 | SUSANTA KR DUTTA | 42.97 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Repairing and Renovation of Beldi Pump house(OHR Site and Riversite) and repairing of bounday wall under Purulia Sadar Sub Division under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/000063/2022-2023 | 168/PSD | 18/04/2022 | 18/05/2022 | ASHOKE ADHIKARY | 4.83 | 0 | 0 | 100
4 | PURULIA |  | Purulia Division | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Construction of 5.0 x 3.0 mtr size Switch Room cum Chlorine Room approach road, plinth protection, surface drain etc. complete at Gouradag Riversite for Beldi W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000451/2021-2022 | 90/PSD | 14/03/2022 | 28/04/2022 | KANCHAN MAHATO | 4.53 | 0 | 0 | 85
5 | PURULIA |  | Purulia Mechanical | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, voltage stabilizer, Flowmeter with necessary substitutes and allied works at BELDI w/s scheme under PMD, PHE Dte. in the District of Purulia.. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000371/2022-2023 | 201/PMD | 28/02/2023 | 29/04/2023 | TAPAN KUMAR DEY | 34.55 | 0 | 0 | 60
6 | PURULIA |  | Purulia Mechanical | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Rectification of different feeders of Beldi W/S scheme(Low lift) for Augmentation of Beldi W/S Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000441/2023-2024 | 421/PMD | 11/03/2024 | 10/04/2024 | TAPAN KUMAR DEY | 5.21 | 0 | 0 | 30
7 | PURULIA |  | Purulia Division | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Construction of WBSEDCL Room and Repairing of old Rising Main Pipeline for Augmentation of Sirkabad W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. (Under Beldi Water Supply Scheme) | Assistant Engineer | Junior Engineer-3 | ORD/003512/2023-2024 | 314/PD | 01/03/2024 | 30/10/2024 | KABERI DUTTA | 2.53 | 0 | 0 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Bill payment for TDS Certificate 26Q for the Q.E June,2023 to September,2023. |  |  | BILL/00019/2024-2025 | BP-2024-25-18 | 22/04/2024 | 22/04/2024 | NIGAM CONSULTANCY SERVICE | 0.35 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Indian Railways Miscellaneous collection |  |  | BILL/01372/2023-2024 | BP-2023-24-758 | 11/01/2024 | 11/01/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 0.01 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Xerox bill paid for Raghunathpur Sub Division. |  |  | BILL/01613/2023-2024 | BP-2023-24-797 | 06/02/2024 | 06/02/2024 | DUTTA XEROX CENTRE | 0.06 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Beldi Water Supply Scheme | SM/09218 | Augmentation | Construction of 5.0 x 3.0 mtr size Guard Room, plinth protection,surface drain etc.complete at Sirkabad Riversite for Sirkabad W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte.(Under Beldi Water Supply Scheme) | Assistant Engineer | Junior Engineer-3 | ORD/003511/2023-2024 | 313/PD | 01/03/2024 | 29/09/2024 | MAHATO CONSTRUCTION | 5.5 | 0 | 0 | 100
Total | [13 empty] | 121.04 | 0 | 0