## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Sirkabad) | Assistant Engineer |  | ORD/000420/2021-2022 | 313/PD | 25/02/2022 | 11/04/2022 | DEBAKI RANJAN SARKAR | 190.82 | 46.35 | 24.29 | 95
2 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sirkabad Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000082/2021-2022 | 167/PMD | 07/03/2022 | 06/04/2022 | MAHADEV ENTERPRISE | 20.89 | 20.58 | 98.51 | 100
3 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte (Mouza-Lachmanpur) (Tender No.915/EE/PD of 2021-22) |  |  | VCH/001218/2021-2022 | BP-2021-22-352 | 28/03/2022 | 28/03/2022 | HIRAK KUMAR SAO | 17.27 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte (Mouza-Lachmanpur) (Tender No.915/EE/PD of 2021-22) |  |  | VCH/001061/2022-2023 | BP-2022-23-407 | 20/10/2022 | 20/10/2022 | HIRAK KUMAR SAO | 20.64 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Sirkabad) (Tender No- 24/SE/PMU of 2021-22) |  |  | VCH/001110/2021-2022 | BP-2021-22-379 | 29/03/2022 | 29/03/2022 | DEBAKI RANJAN SARKAR | 53.62 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Continuation work order for Preparation of DPR (consultancy work) in connection with Functional household Tap Connection of different existing PWSS (Sirkabad W/S Scheme & Puncha W/S Scheme Block- Puncha) to be Augmentation/ Rejuvenation (Tender No- 850/2021-22 of EE/PD) |  |  | VCH/001174/2021-2022 | BP-2021-22-323 | 22/03/2022 | 22/03/2022 | MRS. R DUTTA & COMPANY | 3.45 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Upar jambad) (Tender No.903/EE/PD of 2021-22) |  |  | VCH/000150/2022-2023 | BP-2022-23-17 | 07/04/2022 | 07/04/2022 | ALOK KUMAR CHAKRABORTY | 18.18 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and supplying & laying of HDPE Pipe for distribution system of Sirkabad Water Supply Scheme of Purulia Sadar Sub- Division, PHE Dte. (Mouza- Upar Jambad) (Tender No- 903/2021-22 of EE/PD) |  |  | VCH/000991/2022-2023 | BP-2022-23-157 | 26/07/2022 | 26/07/2022 | ALOK KUMAR CHAKRABORTY | 31.29 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Aharrah) (Tender No.917/EE/PD of 2021-22) |  |  | VCH/001126/2021-2022 | BP-2021-22-373 | 27/03/2022 | 27/03/2022 | KANTILAL SAO | 31.64 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Upar jambad) | Assistant Engineer |  | ORD/000349/2021-2022 | 99/PD | 18/01/2022 | 29/03/2022 | ALOK KUMAR CHAKRABORTY | 63.49 | 0 | 0 | 85
11 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | New sinking of 2 (Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Sirkabad river site of Sirkabad W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000492/2021-2022 | 525/PD | 30/03/2022 | 29/04/2022 | HIRAK KUMAR SAO | 12.95 | 7.9 | 61 | 0
12 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supplying & laying of HDPE pipe for Distribution System for augumentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Covered-(Sirkabad Mouza) | Assistant Engineer |  | ORD/000630/2022-2023 | 1398/PD | 01/09/2022 | 16/10/2022 | DEBAKI RANJAN SARKAR | 22.15 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Laying of Collecting line from Bandu Riverbed to Sirkabad Pump House of Sirkabad W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/001091/2022-2023 | 357/PD | 14/03/2023 | 13/04/2023 | HIRAK KUMAR SAO | 9 | 8.98 | 99.78 | 0
14 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte (Mouza-Lachmanpur) | Assistant Engineer |  | ORD/000350/2021-2022 | 100/PD | 18/01/2022 | 04/03/2022 | HIRAK KUMAR SAO | 39.45 | 0 | 0 | 98
15 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Bhelaidih) | Assistant Engineer |  | ORD/000351/2021-2022 | 101/PD | 18/01/2022 | 17/02/2022 | SK MANIR | 13.92 | 12.1 | 86.94 | 90
16 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Gandhabazar) | Assistant Engineer | Junior Engineer-3 | ORD/000352/2021-2022 | 102/PD | 18/01/2022 | 19/03/2022 | HIRAK KUMAR SAO | 45.46 | 45.44 | 99.97 | 60
17 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | New sinking of 1 (one) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Sirkabad river site of Sirkabad W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000409/2021-2022 | 330/PD | 28/02/2022 | 14/04/2022 | HIRAK KUMAR SAO | 6.82 | 4.88 | 71.54 | 60
18 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Installation of Street light , Laying of Cable trench, and other electrification works at Sirkabad OHR Site Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000182/2023-2024 | 4677/PSD | 27/07/2023 | 11/08/2023 | CHATTERJEE CONSTRUCTION | 0.96 | 0.96 | 100 | 100
19 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Laying of underground Cable trench from Sirkabad lab to OHR and Installation of Street light and other allied works at Sirkabad OHR Site Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000183/2023-2024 | 4678/PSD | 27/07/2023 | 11/08/2023 | CHATTERJEE CONSTRUCTION | 0.85 | 0.85 | 100 | 100
20 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 1506/PD | 13/12/2021 | 13/12/2021 | Resource Division | 65.38 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 397/PD | 11/03/2022 | 11/03/2022 | Resource Division | 0.76 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. |  |  | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 02/08/2023 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Continuation work order for the work of vendering service relating to E-return for Income Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f. 01/10/2022 to 30/09/2023) |  |  | VCH/001922/2022-2023 | BP-2023-24-116 | 22/05/2023 | 22/05/2023 | NIGAM CONSULTANCY SERVICE | 0.67 | 0 | 0 | 0
24 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supply, Delivery and installation of Submersible Pump of river bed tube well, Flowmeter & Water level transmiter with others allied works at Sirkabad w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000640/2024-2025 | 1572/PMD | 14/11/2024 | 12/02/2025 | M/S D. PALIT & CO. | 22.94 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Aharrah) | Assistant Engineer | Junior Engineer-3 | ORD/000353/2021-2022 | 103/PD | 18/01/2022 | 19/03/2022 | KANTILAL SAO | 71.76 | 38.3 | 53.37 | 100
26 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Covered-Bhelaidih,Gandhabazar,Aharrah)) | Assistant Engineer | Junior Engineer-3 | ORD/000631/2022-2023 | 1399/PD | 01/09/2022 | 31/10/2022 | HIRAK KUMAR SAO | 44.91 | 44.41 | 98.89 | 100
27 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Construction of Boundary wall at Sirkabad OHR Site under Sirkabad W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001035/2022-2023 | 243/PD | 20/02/2023 | 06/04/2023 | DILIP KUMAR MAHATO | 26.71 | 6.94 | 25.98 | 100
28 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supply delivery and installation of voltage stabilizer at Sirkabad W/S under PMD PHE dte in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000446/2022-2023 | 265/PMD | 06/03/2023 | 05/05/2023 | GOUTAM CHAKRABORTY | 12.75 | 9.4 | 73.69 | 75
29 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | New sinking of 07 (Seven) nos. 200 mm dia river bed tubewell (Horizontal) at Kansai river alongwith laying of 100 mm dia G.I. collecting line with all allied works at Sirkabad W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001093/2022-2023 | 360/PD | 14/03/2023 | 28/04/2023 | HIRAK KUMAR SAO | 80.83 | 23.64 | 29.25 | 100
30 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supply, delivery and installation of Submersible Pump motor and other related works at Sirkabad w/s scheme under Purulia Mechanical Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000043/2024-2025 | 956/PMD | 19/06/2024 | 17/09/2024 | RABINDRA NATH KHAN | 3.88 | 3.53 | 90.95 | 70
31 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Yard lighting arrangement with others allied work at Sirkabad water supply scheme (Pump house & OHR site) for Augmentation of Sirkabad PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000062/2024-2025 | 991/PMD | 21/06/2024 | 16/12/2024 | ASISH KR. SEN | 11.2 | 10.67 | 95.23 | 80
32 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | NEW CONNECTION FOR AUGMENTATION OF SIRKABAD |  |  | BILL/00477/2023-2024 | BP-23-24-249 | 04/01/2024 | 04/01/2024 | WBSEDCL PURULIA | 7.42 | 0 | 0 | 0
33 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Repairing and renovation of the damaged eleveted water reservoir at Sirkabad OHR Site under Sirkabad W/S Scheme Purulia Sadar Sub Division under Purulia Division , P.H.E. Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001095/2022-2023 | 362/PD | 14/03/2023 | 05/08/2024 | SEKH IRFAN | 10.84 | 0 | 0 | 80
34 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supply, Delivery and laying of Cable of river bed tube well with other allied works at Sirkabad w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000580/2024-2025 | 1438/PMD | 01/10/2024 | 31/10/2024 | M/S S.G.ENTERPRISE | 2.91 | 0 | 0 | 50
35 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Laying of parallel line & Branch line under command area of Sirkabad Water Supply Scheme of Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Aharrah Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/001054/2022-2023 | 286/PD | 27/02/2023 | 11/07/2024 | KANTILAL SAO | 8.44 | 6.21 | 73.65 | 100
36 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supply delivery and installation of Centrifugal pumping machineries with necessary substitutes and allied works at Augmentation of SIRKABAD W/S scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000444/2022-2023 | 263/PMD | 06/03/2023 | 05/05/2023 | RABINDRA NATH KHAN | 56.33 | 34.99 | 62.12 | 70
37 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supply and lowering of submersible pump motor sets at newly constructed River Bed Tubewell with supply of necessary substitute at Sirkabad water supply scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000025/2023-2024 | 410/PMD | 10/04/2023 | 01/01/2025 | M/S S.G.ENTERPRISE | 26.76 | 25.29 | 94.5 | 40
38 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supply delivery and installation of Flowmeter at Sirkabad water supply scheme under , PMD, PHE;Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000035/2023-2024 | 440/PMD | 19/04/2023 | 01/01/2025 | BISHWANATH NANDI | 4.67 | 2.09 | 44.83 | 80
39 | PURULIA |  | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Repairing of Pump house, Chlorine room, Toilet & Construction of Boundary wall and Other allied works at Sirkabad Riversite Site under Sirkabad W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000084/2023-2024 | 840/PD | 26/06/2023 | 23/09/2024 | SK ABBAS | 15.07 | 4.73 | 31.37 | 100
40 | PURULIA |  | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | SM/09578 | Augmentation | Supply, Delivery and installation of foot valve,erection of M.S Pipe, Cable laying, with other allied works at Sirkabad w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000634/2024-2025 | 1550/PMD | 11/11/2024 | 10/01/2025 | RABINDRA NATH KHAN | 4.71 | 0 | 0 | 80
Total | [13 empty] | 1082.46 | 358.23 | 33.09