## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Construction of switch room cum chlorine room at Zone-II OHR site of Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 857/21-22 of EE/PD) |  |  | VCH/000974/2022-2023 | BP-2022-23-144 | 20/07/2022 | 20/07/2022 | M/S SAYAK BHATTACHARYA | 4.19 | 0 | 0 | 0
2 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | NEW SERVICE CONNECTION FOR OHR SITE AT SUTABOI WATER SUPPLY SCHEME UNDER PMD PHE DTE. |  |  | VCH/000328/2022-2023 | BP-2022-23-32 | 08/09/2022 | 08/09/2022 | WBSEDCL PURULIA | 0.28 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Sinking of 08 (Eight) No. 200 mm dia river bed tube well horizontal at Darkeswar river (Sutaboi Ghat) along with laying of 100 mm dia GI collecting line with all allied works under Sutaboi Aug. Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 952/2021-22 of EE/PD) |  |  | VCH/000950/2022-2023 | BP-2022-23-99 | 16/07/2022 | 16/07/2022 | ASHOK KUMAR CHATTERJEE | 19.18 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Additional work of providing FHTC and other allied works of Sutaboi W/S Scheme at Kashipur under Raghunathpur Sub- Division, PHE Dte. (Tender No:- 54/EE/PD of 2022-23) |  |  | VCH/000965/2022-2023 | BP-2022-23-123 | 19/07/2022 | 19/07/2022 | SANTANU BANERJEE | 24.43 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Re sinking of 02 (Two) No. 200 mm dia river bed tube well horizontal at Darkeswar river (Sutaboi ghat) alongwith laying of 100 mm dia GI collecting line with all allied works under Sutaboi Water Supply Scheme under Raghunathpur Sub- Division, PHE dte. (TW No. 2& 6) (Tender No- 956/2021-22 of EE/PD) |  |  | VCH/000941/2022-2023 | BP-2022-23-104 | 16/07/2022 | 16/07/2022 | ASHOK KUMAR CHATTERJEE | 4.8 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Construction of switch room cum chlorine room at Zone-I OHR site of Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 966/2021-22 of EE/PD) |  |  | VCH/000964/2022-2023 | BP-2022-23-125 | 19/07/2022 | 19/07/2022 | ASHOK KUMAR CHATTERJEE | 4.22 | 0 | 0 | 0
7 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | NEW SERVICE CONNECTION AT OHR 2 SITE OF SUTABAI WATER SUPPLY SCHEME UNDER PMD PHE DTE. |  |  | VCH/000327/2022-2023 | BP-2022-23-33 | 08/09/2022 | 08/09/2022 | WBSEDCL PURULIA | 0.28 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Construction of switch room cum chlorine room at Head work site of Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 967/2021-22 of EE/PD) |  |  | VCH/000963/2022-2023 | BP-2022-23-126 | 19/07/2022 | 19/07/2022 | ASHOK KUMAR CHATTERJEE | 4.23 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir at Zone-I & II of Capcaity 350Cum & 150 Cum and other allied works under Sutaboi W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000367/2021-2022 | 153/PD | 25/01/2022 | 05/04/2022 | ASHOK KUMAR CHATTERJEE | 10.24 | 10.19 | 99.55 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Sutaboi river site under Sutaboi w/s Scheme under Raghunathpur Sub-Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000438/2021-2022 | 387/PD | 11/03/2022 | 19/06/2022 | ASHOK KUMAR CHATTERJEE | 13.89 | 11.26 | 81.11 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | Assistant Engineer |  | ORD/000403/2021-2022 | 260/PD | 11/02/2022 | 12/04/2022 | MUNNA AGROTECH ENTERPRISE | 88.48 | 0 | 0 | 100
12 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sutabai Water Supply scheme (OHR no 2 Site ) Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000007/2022-2023 | 310/PMD | 11/05/2022 | 10/06/2022 | COMBINE ENTERPRISE | 20.48 | 20.47 | 99.97 | 96
13 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Additional work by providing functional Household Tap Connection (FHTC) and other allied works of Sutaboi Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000173/2022-2023 | 790/PD | 05/05/2022 | 19/06/2022 | SANTANU BANERJEE | 24.47 | 0 | 0 | 0
14 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sutabai Water Supply scheme (OHR no 1 Site) Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000006/2022-2023 | 309/PMD | 11/05/2022 | 10/06/2022 | ANUP KR. SAHA | 20.47 | 20.46 | 99.97 | 96
15 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Sinking of 8 (Eight) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river ( Sutaboi Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Sutaboi Aug. W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000366/2021-2022 | 151/PD | 24/01/2022 | 23/02/2022 | ASHOK KUMAR CHATTERJEE | 41.88 | 22.46 | 53.63 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Construction of Pump House at Head work site of Sutaboi W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000382/2021-2022 | 204/PD | 01/02/2022 | 01/06/2022 | SUJIT CHAKRABORTY | 5.06 | 4.98 | 98.34 | 100
17 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Resinking of 2(Two) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river ( Sutaboi Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (TW NO-2 & 6) | Assistant Engineer | Junior Engineer | ORD/000359/2021-2022 | 144/PD | 24/01/2022 | 23/02/2022 | ASHOK KUMAR CHATTERJEE | 11.43 | 5.99 | 52.42 | 0
18 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Supply delivery and installation submersible pumping machineries at new deep tube well, MCC panel and laying of cable line, with others allied works for augmentation of Sutaboi water supply scheme under Purulia Mechanical Division, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000477/2022-2023 | 324/PMD | 22/03/2023 | 21/05/2023 | COMBINE ENTERPRISES | 71.28 | 64.48 | 90.46 | 100
19 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Yard lighting arrangement with others allied works at OHR-1 for Augmentation of sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000021/2023-2024 | 392/PMD | 06/04/2023 | 05/06/2023 | MOUSUMI BENERJEE | 5.88 | 5.45 | 92.68 | 100
20 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Riverbed illumination arrangement with others allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000022/2023-2024 | 393/PMD | 06/04/2023 | 05/06/2023 | MAHIPAL MAJHI | 5.95 | 5.48 | 92.18 | 100
21 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Internal lighting arrangement at Sutaboi pump house, Chlorination room at OHR site 1&2 with others allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE, Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000020/2023-2024 | 391/PMD | 06/04/2023 | 05/06/2023 | S. PATHAK & CO. | 2.74 | 2.39 | 87.32 | 100
22 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Yard lighting arrangement with others allied works at OHR-2 under sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000131/2023-2024 | 869/PMD | 21/07/2023 | 19/09/2023 | M/S UJJAL DIESEL SERVICE | 5.81 | 5.28 | 90.9 | 100
23 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 964/PD | 21/06/2022 | 21/06/2022 | Resource Division | 33.36 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Xerox bill office purpose. |  |  | BILL/00433/2023-2024 | BP-2023-24-301 | 14/07/2023 | 14/07/2023 | DUTTA XEROX CENTRE | 0.45 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Indian railway Miscellaneous collection. |  |  | BILL/00127/2022-2023 | BP-2022-23-555 | 18/01/2023 | 18/01/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.4 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. |  |  | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 02/08/2023 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
27 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Yard lighting arrangement with others allied work at Joypur water supply scheme (OHR site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER |  | ORD/000438/2023-2024 | 418/PMD | 11/03/2024 | 10/05/2024 | ASHOKE ADHIKARY | 8.07 | 0 | 0 | 0
28 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Supply, delivery and installation of Centrifugal Pump set with other allied work at River site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000582/2024-2025 | 1473/PMD | 21/10/2024 | 18/02/2025 | COMBINE ENTERPRISES | 5.61 | 0 | 0 | 0
29 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Supply, Delivery and installation of 150KVA oil cooled voltage stabilizer and supply cable and making cable trench with allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000487/2022-2023 | 353/PMD | 27/03/2023 | 26/05/2023 | SWAPAN ENTERPRISE | 18.17 | 17.56 | 96.66 | 100
30 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Supply delivery & installation of flow meter and with others allied works for Augmentation Sutaboi w/s scheme under Purulia Mechanical Division, PHE, Dte. in the Purulia District. (w.e.f 01.11.23 to 31.12.23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000019/2023-2024 | 390/PMD | 06/04/2023 | 05/06/2023 | S. PATHAK & CO. | 4.85 | 4.85 | 100 | 100
31 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Continuation work Order for the work of "Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/01/2023 to 31/12/2023)" | Assistant Engineer | Junior Engineer | ORD/001292/2022-2023 | 699/PD | 20/12/2022 | 20/12/2023 | NIRUPAMA DEY | 1.86 | 0.6 | 32.48 | 100
32 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Supply and installation of Booster pumping machinery for gaseous chlorination system at OHR-I site of Sutaboi W/S scheme under PMD P.H.E Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000494/2023-2024 | 218/PMD | 20/02/2024 | 06/03/2024 | S. PATHAK & CO. | 0.96 | 0.96 | 100 | 100
33 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Supply, delivery and installation of MCC panel at Sutaboi Water Supply Scheme under Purulia Mechanical Division P.H.E Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000486/2023-2024 | 193/PMD | 16/02/2024 | 02/03/2024 | SUJIT MUKHERJEE | 0.64 | 0.64 | 100 | 100
34 | PURULIA |  | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Sutaboi Water Supply Scheme under zone-I & zone-ii at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-2 | ORD/000635/2022-2023 | 1403/PD | 01/09/2022 | 01/07/2025 | ASHOK KUMAR CHATTERJEE | 85.35 | 46.29 | 54.24 | 70
35 | PURULIA |  | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09579 | Augmentation | Supply, delivery and installation of Centrifugal pumping machinery with other allied work at River site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000046/2024-2025 | 965/PMD | 20/06/2024 | 02/10/2025 | NUPUR CHANDRA HALDER | 20.18 | 0 | 0 | 20
Total | [13 empty] | 575.25 | 249.81 | 43.43