## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Arrah Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000069/2021-2022 | 114/PMD | 28/02/2022 | 30/03/2022 | TAPAN KUMAR DEY | 20.47 | 0 | 0 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line from Arra OHR to Lower Beniasole under Arra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Tender No.927/EE/PD of 2021-22) |  |  | VCH/001068/2022-2023 | BP-2022-23-416 | 07/11/2022 | 07/11/2022 | RABIN CHANDRA CHAIL | 3.94 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | SUPPLY DELIVERY AND INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF ARRAH WATER SUPPLY SCHEME UNDER KASHIPUR BLOCK (TR.NO 373 OF 2021-22) |  |  | VCH/000095/2022-2023 | C042228557261 | 13/04/2022 | 13/04/2022 | TAPAN KUMAR DEY | 8.76 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Argumentation of Arrah Water Supply Scheme (Zone-II & III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Manpura, Tupardi, Narayangarh alias Karka. (Tender No.932/EE/PD of 2021-22) |  |  | VCH/001123/2021-2022 | BP-2021-22-378 | 28/03/2022 | 28/03/2022 | SUBHAS CHANDRA MAHATO | 2.98 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supplying & Laying different dia HDPE pipe line from Arra OHR to lower Beniasole under Arra W/S Scheme (Tender No- 927/2021-22 of EE/PD) |  |  | VCH/001111/2021-2022 | BP-2021-22-371 | 29/03/2022 | 29/03/2022 | RABIN CHANDRA CHAIL | 37.14 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 700 cum at Arrah under Arrah W/S Scheme(Zone-I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000408/2021-2022 | 329/PD | 28/02/2022 | 29/04/2022 | RABIN CHANDRA CHAIL | 7.41 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Sinking of 1(one) No. 200 mm dia DTH rigbored tubewell and necessary 65 mm dia collecting line at Narayanpur river side under Arrah W/S Scheme under Raghunathpur Sub Division,P.H.E Dte. | Assistant Engineer |  | ORD/000978/2022-2023 | 83/PD | 17/01/2023 | 16/02/2023 | SUBHAS CHANDRA MAHATO | 2.21 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Raghunathpur -I Block under Purulia Division, PHE Dte.(Mouza-Arrah , Habitation-Arrah,Barabagan) | Assistant Engineer | Junior Engineer | ORD/000291/2020-2021 | 180/PD | 02/02/2021 | 19/03/2021 | SADHAN GORAIN | 131.09 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line for extension of distribution line in different lines of Uppar Beniasole, Mission Para and Panchudanga under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000198/2021-2022 | 579/RNP | 27/09/2021 | 11/11/2021 | MS GORAIN CONCERN | 4.84 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line from Arra OHR to Gosaidanga under Arra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000341/2021-2022 | 64/PD | 17/01/2022 | 03/03/2022 | RABIN CHANDRA CHAIL | 25.25 | 0 | 0 | 95
11 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 50m3 including ventury etc. complete at Arrah Zone-I OHR Campus,under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000342/2021-2022 | 65/PD | 17/01/2022 | 27/04/2022 | RABIN CHANDRA CHAIL | 6.81 | 0 | 0 | 95
12 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Argumentation of Arrah Water Supply Scheme (Zone-I) at Raghunathpur-I Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Arrah. | Assistant Engineer |  | ORD/000368/2021-2022 | 154/PD | 25/01/2022 | 11/03/2022 | MS GORAIN CONCERN | 14.02 | 0 | 0 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Argumentation of Arrah Water Supply Scheme (Zone-II & III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Manpura, Tupardi, Narayangarh alias Karka. | Assistant Engineer | Junior Engineer | ORD/000369/2021-2022 | 155/PD | 25/01/2022 | 11/03/2022 | SUBHAS CHANDRA MAHATO | 7.15 | 0 | 0 | 65
14 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Construction of Guard Room cum store at Pump House Campus under Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000407/2021-2022 | 328/PD | 28/02/2022 | 08/06/2022 | SUBHAS CHANDRA MAHATO | 6.23 | 0 | 0 | 100
15 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Laying of Distribution pipe line ( 90 mm dia HDPE pipe ) from Arrah Pump House to Narayangarh of Kashipur Development Block under Arrah W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | Assistant Engineer |  | ORD/000398/2022-2023 | 356/RNP | 01/06/2022 | 01/07/2022 | SUBHAS CHANDRA MAHATO | 1.33 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Construction of Switch Room Cum Chlorin Room at OHR Site (Zone-I) of Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000891/2022-2023 | 1878/PD | 14/12/2022 | 28/01/2023 | CHAIL CONSTRUCTION | 5.04 | 0 | 0 | 100
17 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Construction of Switch Room Cum Chlorin Room at OHR Site (Zone-II) of Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000892/2022-2023 | 1879/PD | 14/12/2022 | 14/03/2023 | SANDIP KUMAR DUBEY | 5.04 | 0 | 0 | 100
18 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 120 cum at Gagnabad under Arrah W/S Scheme(Zone-III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000894/2022-2023 | 1881/PD | 14/12/2022 | 13/01/2023 | TUMPA GORAIN | 4.19 | 0 | 0 | 100
19 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 100 cum at Manpura under Arrah W/S Scheme(Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000865/2022-2023 | 1818/PD | 06/12/2022 | 05/01/2023 | SANDIP KUMAR DUBEY | 4.46 | 0 | 0 | 100
20 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Laying of distribution pipe line ( 75 mm dia HDPE pipe ) towards Narayangarh Bauri Para under Arrah W/S Scheme of Raghunathpur Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000930/2022-2023 | 711/RNP | 23/12/2022 | 12/01/2023 | SUBHAS CHANDRA MAHATO | 0.97 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Construction of Switch Room Cum Chlorin Room at OHR Site (Zone-III) of Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000893/2022-2023 | 1880/PD | 14/12/2022 | 13/01/2023 | CHANCHAL MISHRA | 5.04 | 0 | 0 | 100
22 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply & installation of Centrifugal pumping machinery with MCC panel, Flow meter and other allied works for Augmentation at Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000370/2022-2023 | 200/PMD | 28/02/2023 | 29/04/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 71.89 | 0 | 0 | 100
23 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply & installation of Submersible pumping machineries for Direct pumping with other allied works for Augmentation at arrah w/s (zone-l) scheme under PMD, PHE, Dte. in the District of Puurlia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000298/2022-2023 | 89/PMD | 02/02/2023 | 03/04/2023 | SAMAN KUMAR MAHATO | 14.03 | 0 | 0 | 100
24 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Making interconnection between existing Rising main to CWR , CWR to distribution line towards Beniasole & Gosaindanga for direct pumping under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 993/PD | 26/07/2023 | 24/09/2023 | RABIN CHANDRA CHAIL | 2.74 | 0 | 0 | 100
25 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Raherdihi to Mohan Gora Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000176/2023-2024 | 992/PD | 26/07/2023 | 24/09/2023 | BISWAJIT MAJI | 10.19 | 0 | 0 | 100
26 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Sinking of 2 (Two) nos. 200 mm dia river bed tubewell (Horizontal) at Darakeswar river (Narayangarh Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Arrah W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 994/PD | 26/07/2023 | 09/09/2023 | CHAIL CONSTRUCTION | 12.17 | 0 | 0 | 100
27 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Emergency Hiring of Diesel Pump for pumping out water from sand pit of Intake Well (No.-1) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 90/CAMP/RNP | 26/04/2023 | 03/05/2023 | RABIN CHANDRA CHAIL | 0.93 | 0 | 0 | 100
28 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Emergency Hiring of Diesel Pump for pumping out water from sand pit of Intake Well (No.-2) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 91/CAMP/RNP | 26/04/2023 | 03/05/2023 | RABIN CHANDRA CHAIL | 0.93 | 0 | 0 | 100
29 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line from Arra OHR to Lower Beniasole under Arra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000337/2021-2022 | 53/PD | 13/01/2022 | 27/02/2022 | RABIN CHANDRA CHAIL | 63.62 | 0 | 0 | 100
30 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 961/PD | 20/06/2022 | 20/06/2022 | Resource Division | 37.97 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 800/PD | 16/06/2023 | 16/06/2023 | Resource Division | 17.7 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line from Arra OHR to Lower Beniasole under Arra W/S Scheme of Raghunathpur Sub- Division, PHE Dte. (Tender No- 927/2021-22 of EE/PD) |  |  | VCH/000897/2022-2023 | BP-2022-23-81 | 01/07/2022 | 01/07/2022 | RABIN CHANDRA CHAIL | 22.53 | 0 | 0 | 0
33 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | New connection for OHR 1 at Augmentation of Arrha Water Supply Scheme |  |  | BILL/00026/2022-2023 | BP-22-23-83 | 24/02/2023 | 24/02/2023 | WBSEDCL PURULIA | 1.16 | 0 | 0 | 0
34 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Arrah OHR-2 for Augmentation of Arrah Water Supply scheme Block Raghunathpur-I under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000384/2022-2023 | 215/PMD | 28/02/2023 | 30/03/2023 | TAPAN KUMAR DEY | 21.61 | 0 | 0 | 80
35 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Arrah OHR-1for Augmentation of Arrah Water Supply scheme Block Raghunathpur-I under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000383/2022-2023 | 214/PMD | 28/02/2023 | 30/03/2023 | COMBINE ENTERPRISES | 21.62 | 0 | 0 | 100
36 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Laying of HDPE pipe (PE-100, PN-10) for collecting line of riverbed Intake Well (for 1 & 2) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 995/PD | 26/07/2023 | 24/09/2023 | RABIN CHANDRA CHAIL | 6.21 | 0 | 0 | 100
37 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Laying of distribution pipe line ( 90 mm & 75 mm dia HDPE pipe ) towards Narayangarh Mahato Para & Majhee Para in connection with FHTC under Arrah W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2023-2024 | 996/PD | 26/07/2023 | 24/09/2023 | TUMPA GORAIN | 3.61 | 0 | 0 | 100
38 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supplying laying fitting fixing of HDPE pipe & FHTC Connection Near Amlatora more to Amlatora last matha & to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000679/2023-2024 | 1362/PD | 13/09/2023 | 28/10/2023 | IKBAL CONSTRUCTION | 8.95 | 0 | 0 | 50
39 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Continuation work Order for the work of "Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/01/2023 to 31/12/2023)" | Assistant Engineer | Junior Engineer | ORD/001292/2022-2023 | 699/PD | 20/12/2022 | 20/12/2023 | NIRUPAMA DEY | 1.86 | 0 | 0 | 100
40 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Providing Functional Household Tap Connection (FHTC) including other allied works of Arrah Water Supply Scheme (Zone - I) at Raghunathpur - I Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001490/2023-2024 | 1801/PD | 08/12/2023 | 06/02/2024 | CHAIL CONSTRUCTION | 7.03 | 0 | 0 | 100
41 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Providing House Hold Tap Connection (FHTC) at Narayangarh Majhipara and repairing and renovation of Pump House Campus under ARRAH W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001863/2023-2024 | 89/PD | 15/01/2024 | 15/03/2024 | SUBHAS CHANDRA MAHATO | 5.26 | 0 | 0 | 100
42 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Laying of distribution pipe line (90 mm dia HDPE pipe) From Milon Sporting Club to K. Mangal Rao House under Arrah W/S Scheme (Zone-I) of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001894/2023-2024 | 22/RNP | 15/01/2024 | 22/01/2024 | RABIN CHANDRA CHAIL | 0.96 | 0 | 0 | 100
43 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply, Delivery and installation of submersible pumping machineries into the intake well with allied cable line and other allied works for augmentation of Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000063/2024-2025 | 992/PMD | 21/06/2024 | 20/08/2024 | M/S R.K. ENTERPRISE | 4.6 | 0 | 0 | 100
44 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply delivery and installation of 50 KVA voltage stabilizer at Arrah OHR site(Z-I) for Augmentation of Arrah water supply scheme under PMD PHE Dte. in the district of purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000390/2023-2024 | 375/PMD | 04/03/2024 | 03/05/2024 | BISHWANATH NANDI | 7.09 | 0 | 0 | 100
45 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | New connection for OHR 2(Manpura) under Augmentation of Arrha Water Supply Scheme under PMD PHE Dte. |  |  | BILL/00027/2022-2023 | BP-23-24-271 | 22/01/2024 | 22/01/2024 | WBSEDCL PURULIA | 0.31 | 0 | 0 | 0
46 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Arrah w/s scheme(Zone-1and Zone-II) under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000123/2023-2024 | 819/PMD | 14/07/2023 | 01/04/2024 | M/S A.D. CONCERN | 5.9 | 0 | 0 | 100
47 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply, delivery and fitting fixing of ST pole and laying of cable line for lighting arrangement at(Z-I, Z-II and pump house) with other allied works under Arrah Water Supply Scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000216/2023-2024 | 1202/PMD | 03/11/2023 | 02/12/2024 | TAPAN KUMAR DEY | 6.6 | 0 | 0 | 70
48 | PURULIA |  | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Construction of 2 Nos. 3 mtr dia Intake well at Darakeshwar river alongwith laying of 100 mm dia G.I. collecting line with all allied works under Arrah W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000918/2022-2023 | 1927/PD | 22/12/2022 | 01/11/2023 | RABIN CHANDRA CHAIL | 19.19 | 0 | 0 | 100
49 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Supply & installation of submersible pumping machinery at newly constructed River Bed Tubewell for Augmentation of Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000369/2022-2023 | 199/PMD | 28/02/2023 | 09/10/2025 | JAL PRAVAHIKA PVT. LTD | 22.65 | 0 | 0 | 75
50 | PURULIA |  | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | SM/09580 | Augmentation | Augmentation of existing old LBSF unit by the new one VCB (one incoming two outgoing) at Arrah W/S scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000119/2023-2024 | 800/PMD | 12/07/2023 | 01/09/2025 | COMBINE ENTERPRISES | 29.23 | 0 | 0 | 81
Total | [13 empty] | 732.89 | 0 | 0