## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Functional household Tap connection (FHTC) in connection with other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur (Zone-II) (Tender No- 905/2021-22 of EE/PD) |  |  | VCH/001190/2021-2022 | BP-2021-22-318 | 22/03/2022 |  | RAHIBUDDIN MONDAL | 12.46 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Additional work for functional House Hold Tap Connection FHTC including other allied works of Kalaboni Water Supply Scheme of Hura Block Zone- I (Tender No- 982/2021-22 of EE/PD) |  |  | VCH/001152/2021-2022 | BP-2021-22-330 | 23/03/2022 |  | NANIGOPAL DEY | 7.35 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) (250 Nos.) (Tender No.978/EE/PD of 2021-22) |  |  | VCH/000138/2022-2023 | BP-2022-23-1 | 05/04/2022 |  | M/S ACHARJEE CONSTRUCTION | 10.69 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) (250 Nos.) (Tender No.987/EE/PD of 2021-22) |  |  | VCH/000185/2022-2023 | BP-2022-23-64 | 24/05/2022 |  | M/S ACHARJEE CONSTRUCTION | 1.67 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Construction of guard room along with sanitary & plumbing arrangement at OHR campus (Zone-III) at Deshra of kalaboni (Improvement) W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 886/2021-22 of EE/PD) |  |  | VCH/000962/2022-2023 | BP-2022-23-127 | 19/07/2022 |  | BASANTA KUMAR SINGHADEO | 5.04 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Construction of guard room along with sanitary & plumbing arrangement at OHR campus (Zone-III) at Deshra of kalaboni (Improvement) W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 886/2021-22 of EE/PD) |  |  | VCH/000962/2022-2023 | BP-2022-23-127 | 19/07/2022 |  | BASANTA KUMAR SINGHADEO | 5.04 | 0 | 0 | 0
7 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | NEW SERVICE CONNECTION FOR TILABANI OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. |  |  | VCH/000324/2022-2023 | BP-2022-23-37 | 08/09/2022 |  | WBSEDCL PURULIA | 0.48 | 0 | 0 | 0
8 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | NEW SERVICE CONNECTION FOR KALABANI WATER SUPPLY SCHEME |  |  | VCH/000321/2022-2023 | BP-22-23-34 | 08/09/2022 |  | WBSEDCL PURULIA | 0.48 | 0 | 0 | 0
9 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | NEW SERVICE CONNECTION AT PHE LADHURKA OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. |  |  | VCH/000322/2022-2023 | BP-2022-23-35 | 08/09/2022 |  | WBSEDCL PURULIA | 0.48 | 0 | 0 | 0
10 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | NEW SERVICE CONNECTION FOR DESHRA OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. |  |  | VCH/000323/2022-2023 | BP-2022-23-36 | 08/09/2022 |  | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Additional work by Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme of Hura Block of Raghunathpur Sub- Division under Purulia Division, PHE Dte. Zone-II (250) nos. (Tender No- 216/2022-23 of EE/PD) |  |  | VCH/000995/2022-2023 | BP-2022-23-159 | 27/07/2022 |  | RAHIBUDDIN MONDAL | 3.3 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Construction of Guard Room cum Chlorine Room at Kalabani Zone-I OHR Campus under Kalabani W/S Scheme (Zone-I) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Tender No.928/EE/PD of 2021-22) |  |  | VCH/000996/2022-2023 | BP-2022-23-253 | 15/09/2022 |  | RABIN CHANDRA CHAIL | 5.14 | 0 | 0 | 0
13 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000066/2021-2022 | 111/PMD | 28/02/2022 | 30/03/2022 | ORIENTAL ENGINEERING CO. | 20.43 | 13.93 | 68.21 | 70
14 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Repairing & renovation of RCC elevated Reservoir capacity 150 cum and boundary wall at Deshra OHR site under kalaboni W/S Scheme (zone-III of Raghunathpur Sub- Division under Purulia Division, PHE Dte. (Tender No-888/2021-22 of EE/PD) |  |  | VCH/000885/2022-2023 | BP-2022-23-79 | 01/07/2022 |  | BASANTA KUMAR SINGHADEO | 4.14 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Restoration, repairing & laying of HDPE Pipe line and other allied works under Kalaboni W/S Scheme(Zone-III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000583/2022-2023 | 496/RNP | 02/08/2022 | 22/08/2022 | SUBRATA SINGHADEO | 4.76 | 3.86 | 81.19 | 95
16 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supplying & laying of HDPE of pipeline for Tentuldih Village and Interconnection work of overflow line with distribution line at Kalaboni Zone-I OHR site under Kalaboni W/S Scheme under FHTC work (Jal Swapna Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000637/2022-2023 | 1405/PD | 01/09/2022 | 16/10/2022 | CHAIL CONSTRUCTION | 8.91 | 8.27 | 92.85 | 96
17 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Repairing and renovation of WTP campus under Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000274/2021-2022 | 761/RNP | 15/12/2021 | 29/01/2022 | SADHAN GORAIN | 4.46 | 3.67 | 82.24 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum and Boundary Wall at Tilabani zone- IV under Kalabani W/S Scheme (Zone-IV) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000253/2021-2022 | 1526/PD | 13/12/2021 | 11/02/2022 | SADHAN GORAIN | 5 | 4.81 | 96.25 | 0
19 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 2 site) Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000041/2022-2023 | 322/PMD | 17/05/2022 | 16/06/2022 | AHALYA ENGINEERING WORKS | 20.57 | 20.56 | 99.95 | 98
20 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum and Boundary Wall at Kalabani OHR Site under Kalabani W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000249/2021-2022 | 1523/PD | 13/12/2021 | 11/02/2022 | RABIN CHANDRA CHAIL | 4.97 | 1.52 | 30.62 | 95
21 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Construction of Guard Room cum Chlorine Room at Kalabani Zone-I OHR Campus under Kalabani W/S Scheme (Zone-I) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000247/2021-2022 | 1521/PD | 13/12/2021 | 23/03/2022 | RABIN CHANDRA CHAIL | 5.92 | 0 | 0 | 96
22 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 150 cum and Boundary Wall at Ladhurka OHR Site under Kalabani W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000250/2021-2022 | 1524/PD | 13/12/2021 | 11/02/2022 | NANIGOPAL DEY | 4.8 | 4.44 | 92.4 | 95
23 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Construction of Guard Room cum Chlorine Room at Tilabani Zone-IV OHR Campus under Kalabani W/S Scheme (Zone-IV) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000248/2021-2022 | 1522/PD | 13/12/2021 | 23/03/2022 | SADHAN GORAIN | 5.95 | 4.99 | 83.97 | 0
24 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 3 site) Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000042/2022-2023 | 323/PMD | 17/05/2022 | 16/06/2022 | S.P. ENTERPRISE | 20.48 | 20.45 | 99.86 | 100
25 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply delivery and installation of submersible pump-motor set instead of existing submersible pump-motor set at Kalabani w/s scheme under Purulia Mechanical Division , PHE, Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000080/2023-2024 | 592/PMD | 24/05/2023 | 23/06/2023 | SUBRATA DUTTA | 9.05 | 9.05 | 100 | 100
26 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply, delivery and installation of lighting arrangement at Tialabani OHR site (Zone-IV) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000112/2023-2024 | 640/PMD | 08/06/2023 | 08/07/2023 | MOON LIGHT HOUSE | 2.5 | 1.17 | 46.89 | 15
27 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-I) | Assistant Engineer |  | ORD/000241/2021-2022 | 1515/PD | 13/12/2021 | 12/01/2022 | NANIGOPAL DEY | 7.36 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-II) | Assistant Engineer |  | ORD/000242/2021-2022 | 1516/PD | 13/12/2021 | 12/01/2022 | BASANTA KUMAR SINGHADEO | 7.91 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) | Assistant Engineer |  | ORD/000243/2021-2022 | 1517/PD | 13/12/2021 | 12/01/2022 | PRIYATOSH MUKHERJEE | 8.38 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-II) (250 Nos.) | Assistant Engineer | Junior Engineer | ORD/000244/2021-2022 | 1518/PD | 13/12/2021 | 12/01/2022 | RAHIBUDDIN MONDAL | 12.36 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 150 cum and Boundary Wall at Deshra OHR Site under Kalabani W/S Scheme (Zone-III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000252/2021-2022 | 1525/PD | 13/12/2021 | 11/02/2022 | BASANTA KUMAR SINGHADEO | 4.87 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone- I) (120 Nos.) | Assistant Engineer | Junior Engineer | ORD/000255/2021-2022 | 1528/PD | 13/12/2021 | 12/01/2022 | CHAIL CONSTRUCTION | 7.56 | 0 | 0 | 0
33 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) (250 Nos.) | Assistant Engineer | Junior Engineer | ORD/000245/2021-2022 | 1519/PD | 13/12/2021 | 12/01/2022 | M/S ACHARJEE CONSTRUCTION | 12.43 | 0 | 0 | 0
34 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Construction of Guard Room cum Chlorine Room at Deshra Zone-III OHR Campus under Kalabani W/S Scheme (Zone-III) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000246/2021-2022 | 1520/PD | 13/12/2021 | 23/03/2022 | BASANTA KUMAR SINGHADEO | 5.89 | 0 | 0 | 0
35 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Sinking of 1(one) No. 200 mm dia DTH rigbored tubewell and dismantling and renovation of boundary wall at (Zone-I ) under Kolaboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000663/2023-2024 | 1356/PD | 13/09/2023 | 13/10/2023 | CHAIL CONSTRUCTION | 3.19 | 3.19 | 99.97 | 100
36 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Sinking of 1(one) No. 200 mm dia DTH rigbored tubewell and dismantling and renovation of boundary wall at (Zone-IV ) under Kolaboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000662/2023-2024 | 1355/PD | 13/09/2023 | 13/10/2023 | SADHAN GORAIN | 4.34 | 4.34 | 99.97 | 100
37 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 4 site) Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000043/2022-2023 | 324/PMD | 17/05/2022 | 16/06/2022 | CREATIVE WATER AND PROCESS TECHNOLOGY PVT LTD. | 20.51 | 19.76 | 96.37 | 100
38 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -I OHR site to Hirgram & Hir Rangadihi Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni W/S Scheme of Raghunathpur Sub- Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000883/2023-2024 | 1533/PD | 16/10/2023 | 30/11/2023 | CHAIL CONSTRUCTION | 18.17 | 9.05 | 49.78 | 100
39 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Sinking of 200mmX165mm tubewell and other allied works for Kalabani water supply scheme Purulia,under PMD, PHE Dte. in the District of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000215/2023-2024 | 1201/PMD | 03/11/2023 | 18/11/2023 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 7.12 | 3.61 | 50.68 | 100
40 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Gravel Paking around Intake, Construction of Guard Wall , Chain link fencing , Digging of earth at Kolaboni Intake site under Kaloboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001859/2023-2024 | 87/PD | 15/01/2024 | 15/03/2024 | SADHAN GORAIN | 11.17 | 5.5 | 49.22 | 100
41 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -II main distribution pipe line to Kusmagora Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2023-2024 | 991/PD | 26/07/2023 | 24/09/2023 | ALOK KUMAR CHAKRABORTY | 14.14 | 7.07 | 49.99 | 100
42 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -I main distribution pipe line to Jabjobi Gora Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000672/2023-2024 | 1359/PD | 13/09/2023 | 28/10/2023 | M/S SAYAK BHATTACHARYA | 18.72 | 18.68 | 99.75 | 100
43 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply, delivery fitting & fixing of 5 Nos. Scheme Description Sign boards (6' X 3') under Kalaboni W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Location:- Zone-I (Kalaboni), Zone-II (Ladhurka), Zone-III(Deshra), Zone-IV(Tilaboni) & WTP Campus. | Assistant Engineer | Junior Engineer | ORD/001940/2023-2024 | 24/RNP | 15/01/2024 | 22/01/2024 | M/S SAYAK BHATTACHARYA | 0.86 | 0 | 0 | 0
44 | PURULIA |  | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Restoration work by construction of RCC Retaining wall for Protection work at Kalabani Intake site of Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000254/2021-2022 | 1527/PD | 13/12/2021 | 11/02/2022 | SADHAN GORAIN | 5.68 | 0 | 0 | 0
45 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply, delivery and installation of lighting arrangement at Kalabani OHR site (Zone-I) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000113/2023-2024 | 641/PMD | 08/06/2023 | 08/07/2023 | MD. ASLAM | 2.56 | 2.39 | 93.52 | 100
46 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply, delivery and installation of lighting arrangement at Deshra OHR site (Zone-III) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000114/2023-2024 | 642/PMD | 08/06/2023 | 08/07/2023 | MD. ASLAM | 2.45 | 2.07 | 84.75 | 100
47 | PURULIA |  | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | SM/09581 | Augmentation | Supply, delivery and installation of lighting arrangement at Ladhurka OHR site (Zone-II) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000115/2023-2024 | 643/PMD | 08/06/2023 | 08/07/2023 | KOUSHIK CHATTERJEE | 2.46 | 2.35 | 95.67 | 100
Total | [13 empty] | 352.48 | 174.74 | 49.58