## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Supplying & laying different dia HDPE pipe line from Barrah Shiv Mandir to Borkha Village under Rangamati Village. (Tender No.1005/EE/PD of 2021-22) |  |  | VCH/001129/2021-2022 | BP-2021-22-375 | 29/03/2022 | 29/03/2022 | MANATOSH SINGH | 14.39 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. (Tender No.906/EE/PD of 2021-22) |  |  | VCH/001143/2021-2022 | BP-2021-22-297 | 09/03/2022 | 09/03/2022 | SANTANU BANERJEE | 2.49 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. (Tender No.906/EE/PD of 2021-22) (Ad-interim) |  |  | VCH/001140/2021-2022 | BP-2021-22-275 | 03/03/2022 | 03/03/2022 | SANTANU BANERJEE | 16 | 0 | 0 | 0
4 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Rangamati w/s scheme under PMD, PHE Dte. in the District of Purulia. |  | JUNIOR ENGINEER | ORD/000443/2022-2023 | 262/PMD | 06/03/2023 | 05/05/2023 | NUPUR CHANDRA HALDER | 8.54 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Laying of distribution pipe line ( 110 mm & 90 mm dia HDPE pipe ) from Bankati Siv Mandir to Dejuri - Shyambathan More in connection with FHTC under Rangamati W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 548/PD | 12/04/2023 | 12/05/2023 | M/S. DESTINY CONSTRUCTION | 7.19 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Construction of Guard Room cum store at OHR Campus under Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000356/2021-2022 | 106/PD | 18/01/2022 | 28/04/2022 | CHANCHAL MISHRA | 5.86 | 0 | 0 | 98
7 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 250 cum at Barrah under Rangamati W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000357/2021-2022 | 107/PD | 18/01/2022 | 19/03/2022 | MANATOSH SINGH | 5.27 | 0 | 0 | 90
8 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | New sinking of 4 (Four) nos. 200 mm dia river bed tubewell (Horizontal) at Darakeshwar river alongwith laying of 100 mm dia G.I. collecting line with all allied works under Rangamati W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000433/2021-2022 | 380/PD | 11/03/2022 | 10/05/2022 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 29.49 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Construction of Guard Room cum store at Pump House Campus under Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000435/2021-2022 | 381/PD | 11/03/2022 | 19/06/2022 | CHANCHAL MISHRA | 5.94 | 0 | 0 | 0
10 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Rangamatia Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000054/2022-2023 | 395/PMD | 16/06/2022 | 16/07/2022 | MS EMMESS | 20.5 | 0 | 0 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 965/PD | 21/06/2022 | 21/06/2022 | Resource Division | 18.28 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Construction of Guard Room cum store at OHR Campus under Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Tender No.889/EE/PD of 2021-22) |  |  | VCH/001027/2022-2023 | BP-2022-23-342 | 29/09/2022 | 29/09/2022 | CHANCHAL MISHRA | 5.48 | 0 | 0 | 0
13 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | NEW CONNECTION FOR AUGMENTATION OF RANGAMATI WATER SUPPLY SCHEME |  |  | BILL/00041/2022-2023 |  | 28/02/2023 | 28/02/2023 | WBSEDCL PURULIA | 4.21 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | New sinking of 04 (Four) No. 200 mm dia river bed tube well horizontal at Darakeswar river along with laying of 100 mm dia GI collecting with all allied works under Rangamati Water Supply Scheme under Raghunathpur Sub- division, PHE Dte. (Tender No- 11/2022-23 of EE/PD) |  |  | VCH/000920/2022-2023 | BP-2022-23-102 | 16/07/2022 | 16/07/2022 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 8.56 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Supplying & laying different dia HDPE pipe line from Barrah Siv Mandir to Bankati village under Rangamati W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000355/2021-2022 | 105/PD | 18/01/2022 | 04/03/2022 | MANATOSH SINGH | 22.36 | 0 | 0 | 100
16 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Supply delivery and installation of 100KVA voltage stabilizer for Augmentation of Rangamati water supply scheme under Purulia Mechanical Division PHE, Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000480/2022-2023 | 339/PMD | 24/03/2023 | 23/05/2023 | SANTU MITRA | 10.39 | 0 | 0 | 100
17 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Internal external illumination with other allied works for Augmentation of Rangamati Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000205/2023-2024 | 1195/PMD | 03/11/2023 | 02/01/2024 | SANTU MITRA | 6.37 | 0 | 0 | 100
18 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Additional work for supply delivery and laying of submersible cable with jointing kit for newly constructed river bed tube well for augmentation of Rangamati water supply scheme under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000239/2023-2024 | 335/PMSD(W/S) | 11/09/2023 | 26/09/2023 | NUPUR CHANDRA HALDER | 0.89 | 0 | 0 | 100
19 | PURULIA |  | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Providing Functional Household Tap Connection (FHTC) including other allied works of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001623/2023-2024 | 1833/PD | 12/12/2023 | 10/02/2024 | BOSE CONSTRUCTION | 4.23 | 0 | 0 | 100
20 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Supply, delivery and laying of cable line at Rangamati water supply scheme under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000553/2023-2024 | 106/PMSD(W/S) | 05/03/2024 | 12/03/2024 | SANTU MITRA | 0.74 | 0 | 0 | 100
21 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | New Connection for Augmentation of Rangamati water supply Scheme |  |  | BILL/00248/2023-2024 | BP-23-24-203 | 17/10/2023 | 17/10/2023 | WBSEDCL PURULIA | 4.21 | 0 | 0 | 0
22 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Supply, Delivery and installation of submersible pumping machineries into the existing CWR and in River bed Tube Well with allied cable line and other allied works for augmentation of Rangamati w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000468/2024-2025 | 1294/PMD | 30/08/2024 | 01/10/2025 | M/S A.D. CONCERN | 10 | 0 | 0 | 50
23 | PURULIA |  | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | SM/09582 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmwter and other allied works for augmentation of Rangamati water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000442/2022-2023 | 261/PMD | 06/03/2023 | 05/05/2023 | NUPUR CHANDRA HALDER | 46.44 | 0 | 0 | 72
Total | [13 empty] | 257.82 | 0 | 0