## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 85 KVA AT 0.4 KV TO 119/119/119/119/119 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 932416100) TO THEIR PREMISES AT PARBELIYA WATER SUPPLY SARBARI NETURIA DIST PURULIA UNDER REGIONAL OFFICE PURULIA |  |  | VCH/000423/2022-2023 | BP-22-23-86 | 28/02/2023 |  | WBSEDCL PURULIA | 1.98 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Repairing and renovation of Pump House at River Side under Parbeylia W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000931/2022-2023 | 712/RNP | 23/12/2022 | 07/01/2023 | AMIT PATHAK | 1 | 0.64 | 64.39 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Installation of 3 (Three) nos. 1.00 H.P. capacity Solar Photovoltaic Submersible Pump set in pre-existing / new bore Tube well along with 1200 Watt peak capacity Solar photovoltaic array panels on steel structure including Supply & Delivery of approved quality materials & Geophysical investigation by electrologging with all allied works at different places within Neturia Block in Purulia District of Raghunathpur Sub-Division under Purulia Division, PHE Dte.[Phase-iii][Group-E] | Assistant Engineer |  | ORD/001098/2022-2023 | 365/PD | 14/03/2023 | 28/04/2023 | ASHOK KUMAR CHATTERJEE | 30.01 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Construction of Guard Room cum store at Pump House Campus under Parbeliya W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000343/2021-2022 | 66/PD | 17/01/2022 | 27/04/2022 | M/S SHYAMASHREE ENTERPRISE | 5.2 | 5.18 | 99.62 | 100
5 | PURULIA |  | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Construction of Switch Room Cum Chlorin Room at CWR Site of Parbeliya W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000966/2022-2023 | 45/PD | 09/01/2023 | 19/04/2023 | M/S KARUNAMOYEE CONSTRUCTION | 4.86 | 4.82 | 99.12 | 100
6 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Supply delivery & installation of Electromagnetic flow meter and with others allied works for Augmentation of Parbeliya w/s scheme (Low lift & High lift) under Purulia Mechanical Division, PHE, Dte. in the Purulia District. |  | JUNIOR ENGINEER | ORD/000435/2022-2023 | 254/PMD | 06/03/2023 | 05/05/2023 | BISHWANATH NANDI | 6.91 | 5.72 | 82.82 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | New Sinking of 1 (One) Nos 200 mm dia river bed vertical tubewell (T/W No.- 1) alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Parbeliya W/S Scheme under Raghunathpur Sub Division, PHE Dte. |  |  | ORD/000399/2022-2023 | 357/RNP | 01/06/2022 | 21/06/2022 | ASHOK KUMAR CHATTERJEE | 1.76 | 0.87 | 49.42 | 100
8 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Supply, Delivery and installation of 50KVA oil cooled voltage stabilizer and allied works for Augmentation of Parbeliya w/s scheme (Low lift) under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000079/2023-2024 | 588/PMD | 23/05/2023 | 22/07/2023 | M/S A.D. CONCERN | 5.88 | 2.92 | 49.71 | 100
9 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | New power connection at Parbeliya PWSS OHR Campus(Reference M.B.NO MB/0000210/2023-2024) |  |  | BILL/00870/2023-2024 | BP-23-24-300 | 05/03/2024 |  | WBSEDCL PURULIA | 0.11 | 0 | 0 | 0
10 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | New power connection at Parbeliya PWSS OHR Campus(Reference M.B.NO MB/0000210/2023-2024) |  |  | BILL/00870/2023-2024 | BP-23-24-300 | 05/03/2024 |  | WBSEDCL PURULIA | 0.11 | 0 | 0 | 0
11 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Sub: Enhancement of the contract demand from 85 KVA at 0.4 KV to 119/119/119/119/119 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o-THE EXE. ENGG, PMD, P.H.E DTE., PURULIA, SITE- PHE PERBELIA W/S under Purulia Regional Office. (1) Application No.- L000005249. (2) Consumer Id.- 932416100 |  |  | BILL/00892/2023-2024 | BP-23-24-339 | 27/03/2024 |  | WBSEDCL PURULIA | 6.85 | 0 | 0 | null
12 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Sub: Enhancement of the contract demand from 85 KVA at 0.4 KV to 119/119/119/119/119 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o-THE EXE. ENGG, PMD, P.H.E DTE., PURULIA, SITE- PHE PERBELIA W/S under Purulia Regional Office. (1) Application No.- L000005249. (2) Consumer Id.- 932416100 |  |  | BILL/00892/2023-2024 | BP-23-24-339 | 27/03/2024 |  | WBSEDCL PURULIA | 6.85 | 0 | 0 | null
13 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Supply, delivery & installation of MCC Panel at Parbelia w/s scheme under PMD, PHE Dte. |  |  | ORD/000532/2023-2024 | 354/PMD | 29/02/2024 | 15/03/2024 | SUBAL SARKAR | 0.64 | 0 | 0 | 0
14 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Supply, delivery of Submersible pumping machineries for Parbeliya W/S scheme under PMD P.H.E Dte. in the District Purulia. | AE | JUNIOR ENGINEER | ORD/000501/2023-2024 | 196/PMD | 16/02/2024 | 02/03/2024 | M/S A.D. CONCERN | 0.59 | 0.3 | 50 | 100
15 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Parbeliya Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER,ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000040/2022-2023 | 321/PMD | 17/05/2022 | 16/06/2022 | MS SAJAHAN CHOWDHURY | 20.49 | 17.23 | 84.09 | 100
16 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | External and internal illumination of OHR site,High lift and low lift site of Parbeliya water supply scheme and Flood light at Low lift site for Augmentation work under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000044/2024-2025 | 962/PMD | 20/06/2024 | 18/09/2024 | MOON LIGHT HOUSE | 8.27 | 0 | 0 | 0
17 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Supply delivery and installation of 500 ltr UPVC tank and pipe line for eye shower for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division, P.H.E Dte. in the District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000556/2023-2024 | 195/PMD | 16/02/2024 | 26/02/2024 | MS SAJAHAN CHOWDHURY | 0.37 | 0.17 | 45.28 | 100
18 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Supply, delivery & installation of Dewatering submersible pump set at Parbelia w/s scheme under PMD, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000510/2023-2024 | 344/PMD | 28/02/2024 | 14/03/2024 | M/S R.K. ENTERPRISE | 0.55 | 0.28 | 50 | 100
19 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Internal illumination of pump house room with others allied works for Augmentation of Parbeliya w/s scheme (Low lift & High lift) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000132/2023-2024 | 647/PMD | 08/06/2023 | 07/08/2023 | GOLAP KR. GHOSH | 1.46 | 0.62 | 42.29 | 100
20 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Supply delivery and installation of 40 KVA voltage stabilizer for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | ASSISTANT ENGINEER,ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000467/2024-2025 | 1293/PMD | 30/08/2024 | 28/12/2024 | AVISHEK ENTERPRISE | 5.97 | 0 | 0 | 0
21 | PURULIA |  | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | SM/09583 | Augmentation | Supply, Delivery and installation of submersible pumps motor sets with other allied works for Parbeliya w/s scheme (Low lift) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000032/2023-2024 | 437/PMD | 19/04/2023 | 18/06/2023 | KOUSHIK CHATTERJEE | 12.04 | 7.14 | 59.28 | 30
Total | [13 empty] | 121.9 | 45.88 | 37.64