## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A( Mouza-Amlatara,Chatumadar,Kajali,Karamadi under Chatumadar G.P). (987 Nos.) (Tender No.409/EE/PD of 2020-2021) |  |  | VCH/000989/2021-2022 | BP-2021-22-240 | 16/02/2022 |  | ALOK KUMAR CHAKRABORTY | 2.61 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Additional Functional Household Tap Connection (FHTC) in connection with other allied works of Manguria-Lalpur W/s Scheme. (Tender No.901/EE/PD of 2021-22) |  |  | VCH/001009/2021-2022 | BP-2021-22-258 | 25/02/2022 |  | ALOK KUMAR CHAKRABORTY | 5.92 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-C (Mouza-Maguria-Lalpur under Maguria-Lalpurr G.P). 1218 Nos.) (Tender No.307/EE/PD of 2020-21) |  |  | VCH/001116/2021-2022 | BP-2021-22-326 | 22/03/2022 |  | SWAPAN MANDAL | 8.16 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Distribution Main by supplying & laying of different dia HDPE pipe line and Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.959/EE/PD of 2021-22) |  |  | VCH/001137/2021-2022 | BP-2021-22-292 | 09/03/2022 |  | PREMNATH MITRA | 53.06 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B)(Daldali G.P.)(220 Nos.) (Tender No.946/EE/PD of 2021-22) |  |  | VCH/000144/2022-2023 | BP-2022-23-31 | 08/04/2022 |  | M/S CHAKRABORTY CONSTRUCTION | 8.65 | 0 | 0 | 0
6 | PURULIA |  | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | SUPPLY DELIVERY & INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM OF AUGMENTATION OF MANGURIA LALPUR W/S SCHEME, HURA BLOCK UNDER PMD PHE DTE.(TR.NO 371 OF 2021-22) |  |  | VCH/000081/2022-2023 | C042211603113 | 08/04/2022 |  | JAL PRAVAHIKA PVT. LTD | 8.78 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B)(Daldali G.P.)(220 Nos.) (Tender No.22/EE/PD of 2022-23) |  |  | VCH/000174/2022-2023 | BP-2022-23-51 | 17/05/2022 |  | M/S CHAKRABORTY CONSTRUCTION | 4.54 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Additional work for FHTC including other allied works of Manguria-lalpur W/S Scheme at Hura Block (Part- C) [Tender No- 939/2021-22 of EE/PD] |  |  | VCH/000184/2022-2023 | BP-2022-23-63 | 24/05/2022 |  | SWAPAN MANDAL | 18.23 | 0 | 0 | 0
9 | PURULIA |  | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 110 KVA AT 0.4 KV TO 160/160/160/160/160 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , THE EX ENGG PMD PHE DTE(CONSUMER ID : 950009505) TO THEIR PREMISES AT MANGURIA LALPUR WATER SUPPLY DIST PURULIA UNDER REGIONAL OFFICE PURULIA |  |  | VCH/000427/2022-2023 | null | 03/11/2022 |  | WBSEDCL PURULIA | 9.17 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A) (Chatumadar G.P.)(300 Nos) (Tender No..902/EE/PD OF 2021-22) |  |  | VCH/000999/2022-2023 | BP-2022-23-238 | 05/09/2022 |  | ALOK KUMAR CHAKRABORTY | 6.2 | 0 | 0 | 0
11 | PURULIA |  | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Manguria lalpur Water Supply scheme Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000081/2021-2022 | 166/PMD | 07/03/2022 | 06/04/2022 | JAL PRAVAHIKA PVT. LTD | 20.5 | 11.71 | 57.13 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum at Amlatora OHR under Manguria-Lalpur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000076/2022-2023 | 653/PD | 22/04/2022 | 22/05/2022 | KANAILAL PAL | 4.69 | 3.97 | 84.68 | 90
13 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | New sinking of 05 (Five) Nos. 200 mm dia river bed tube well (Horizontal) at Kansabati river (Amrakocha Ghat) along with laying of 100 mm dia GI collecting line with all allied works under Manguria-lalpur W/S Scheme under Raghunathpur Sub- Division, PHE Dte. (Tender No- 53/2022-23 of EE/PD) |  |  | VCH/000895/2022-2023 | BP-2022-23-72 | 01/07/2022 |  | NANIGOPAL DEY | 10.12 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Supplying and laying of HDPE pipe line from existing CWR to Karandih through Amrakotcha village under Manguria-Lalpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000862/2022-2023 | 1815/PD | 06/12/2022 | 20/01/2023 | ALOK KUMAR CHAKRABORTY | 14.41 | 14.21 | 98.64 | 100
15 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Allied works for repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum at Amlatora OHR under Manguria-Lalpur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001015/2022-2023 | 183/PD | 07/02/2023 | 09/03/2023 | KANAILAL PAL | 2.64 | 2.64 | 99.99 | 100
16 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Distribution Main by supplying & laying of different dia HDPE pipe line and Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000279/2021-2022 | 1554/PD | 15/12/2021 | 13/02/2022 | PREMNATH MITRA | 78.3 | 9.15 | 11.68 | 85
17 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B)(Daldali G.P.)(220 Nos.) | Assistant Engineer |  | ORD/000376/2021-2022 | 162/PD | 25/01/2022 | 11/03/2022 | M/S CHAKRABORTY CONSTRUCTION | 9.95 | 0 | 0 | 35
18 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 300 cum at Manguria OHR under Manguria-Lalpur W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000372/2021-2022 | 158/PD | 25/01/2022 | 26/03/2022 | KANAILAL PAL | 7.43 | 6.75 | 90.88 | 95
19 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at Amrakocha Pump House Site under Manguria-Lalpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000417/2021-2022 | 85/RNP | 28/02/2022 | 29/05/2022 | M/S SAYAK BHATTACHARYA | 4.39 | 3.75 | 85.34 | 90
20 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Car bill for hair charges for office purpose against vehicle reg. no.WB55A/7171 for the period form March,23 to April,23. |  |  | BILL/00264/2023-2024 | BP-2023-24-231 | 14/06/2023 |  | NIRUPAMA DEY | 0.71 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A)(Chatumadar G.P.)(300 Nos) | Assistant Engineer |  | ORD/000375/2021-2022 | 161/PD | 25/01/2022 | 11/03/2022 | ALOK KUMAR CHAKRABORTY | 13.88 | 5.3 | 38.18 | 65
22 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | New sinking of 5(Five) nos. 200 mm dia river bed tubewell (Horizontal) at Kansabati river ( Amrakocha Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Manguria-Lalpur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. |  |  | ORD/000073/2022-2023 | 650/PD | 22/04/2022 | 06/06/2022 | NANIGOPAL DEY | 18.95 | 5.56 | 29.33 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Making Two nos Bypass arrangement with allied works in between of over flow line to distribution main at Maguria Lalpur Zone-I & II OHR site under Maguria Lalpur water supply scheme of Raghunathpur Sub Division uneder Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 880/PD | 03/07/2023 | 02/08/2023 | ALOK KUMAR CHAKRABORTY | 4.2 | 4.2 | 99.94 | 100
24 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Additional work of Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) (Daldali G.P.) (220 Nos.) | Assistant Engineer | Junior Engineer | ORD/000498/2021-2022 | 144/RNP | 31/03/2022 | 14/04/2022 | M/S CHAKRABORTY CONSTRUCTION | 4.55 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Supplying laying fitting fixing of HDPE pipe Near Doldoli Bridge to Doldoli Bastri to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Manguria-Lalpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000174/2023-2024 | 990/PD | 26/07/2023 | 24/09/2023 | CHANCHAL MISHRA | 5.79 | 5.78 | 99.75 | 100
26 | PURULIA |  | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Manguria Lalpur water supply scheme under PMD PHE Dte. In the district of Purulia |  | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000290/2022-2023 | 82/PMD | 01/02/2023 | 02/04/2023 | SWAPAN ENTERPRISE | 13.25 | 13.25 | 100 | 100
27 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 960/PD | 20/06/2022 |  | Resource Division | 39.43 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -II main distribution pipe line to Chatumather Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Manguria-Lalpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000686/2023-2024 | 1357/PD | 13/09/2023 | 28/10/2023 | PRAMIT CHATTERJEE | 18.04 | 0.11 | 0.61 | 100
29 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Additional work for functional Household Tap Connection (FHTC) and other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A) (Chatumadar G.P.) | Assistant Engineer | Junior Engineer | ORD/000660/2023-2024 | 1353/PD | 13/09/2023 | 28/10/2023 | ALOK KUMAR CHAKRABORTY | 2.02 | 0 | 0 | 100
30 | PURULIA |  | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, Flowmeter, MCC Panel and other allied works for augmentation of Manguria Lalpur water supply scheme under PMD, PHE Dte. In the district of Purulia. |  | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000294/2022-2023 | 81/PMD | 01/02/2023 | 02/04/2023 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 49.6 | 42.3 | 85.29 | 100
31 | PURULIA |  | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well and existing one no tube well with allied cable line and other allied works for augmentation of Manguria Lalpur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000289/2022-2023 | 80/PMD | 01/02/2023 | 02/04/2023 | RAJIB COMPANY | 24.65 | 22.9 | 92.87 | 100
32 | PURULIA |  | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | SM/09943 | Augmentation | Clearing of chokage and making HDPE loop line for Kalali , Amlatora, Chatumadar, & Hijuli under under Manguria-Lalpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000861/2022-2023 | 1814/PD | 01/12/2022 | 30/05/2023 | ALOK KUMAR CHAKRABORTY | 8.16 | 0 | 0 | 100
Total | [13 empty] | 481.01 | 151.58 | 31.51