## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Ramchandrapur Water Supply scheme Block Santuri under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000076/2021-2022 | 161/PMD | 07/03/2022 | 06/04/2022 | MERCURY ENGINEERING COMPANY | 20.5 | 20.5 | 100 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supplying laying different dia HDPE and DI pipe including Functional Household Connection (FHTC) for Distribution system (Zone-I) of Augmentation of Ramchandrapur W/s Scheme. (Tender No.23/SE/PMU of 2021-22) |  |  | VCH/001125/2021-2022 | BP-2021-22-385 | 29/03/2022 | 29/03/2022 | ANUP KUMAR SAHA | 42.77 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Construction of Guard room near intake pathway under Ramchandrapur W/ S Scheme under Raghunathpur Sub- Division, PHE Dte.(Tender No- 569/2021-22 of EE/PD) |  |  | VCH/000943/2022-2023 | BP-2022-23-101 | 16/07/2022 | 16/07/2022 | MADHU SUDAN RAKSHIT | 4.21 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Ramchandrapur W/S Scheme Block - Santuri) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.538/EE/PD of 2021-22) |  |  | VCH/000965/2021-2022 | BP-2021-22-274 | 03/03/2022 | 03/03/2022 | RADIANT | 4.26 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Functional Household Tap Connection (FHTC including other allied works of Ramchandrapur Water Supply Scheme (Zone - III) at Santuri Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. at Mouza - Murulia (Jl No. 15) | Assistant Engineer |  | ORD/000361/2021-2022 | 147/PD | 24/01/2022 | 10/03/2022 | BASANTA KUMAR SINGHADEO | 68.57 | 68.57 | 100 | 95
6 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Internal and External illumination work for Augmentation Ramchandrapur Water supply scheme at Existing WTP and Intake pump house , Block: santuri , Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000099/2022-2023 | 525/PMD | 05/08/2022 | 04/09/2022 | MOON LIGHT HOUSE | 9.48 | 9.13 | 96.34 | 55
7 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supply, delivery and installation of automatically controlled Chlorinator having flow rate of 100 LPH and maximum pressure of 10 kg/cm2. at Augmentation of Ramchandrapur water supply scheme OHR/pump house block Santuri, under Purulia Mechanical Division PHE, Dte. district-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000306/2022-2023 | 94/PMD | 03/02/2023 | 05/03/2023 | GOLAP KR. GHOSH | 1.92 | 1.27 | 66.14 | 0
8 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supply delivery and installation of Centrifugal pump motor sets MCC, Flowmeter to supply Zone I & II OHR with allied works at New pump house of Augmentation of Ramchandrapur water supply scheme Block: Santuri, Under Purulia Mechanical Division PHE, Dte. in the District of Purulia. |  | JUNIOR ENGINEER | ORD/000305/2022-2023 | 93/PMD | 03/02/2023 | 04/04/2023 | MAHADEV ENTERPRISE | 36.04 | 21.11 | 58.57 | 20
9 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supply, delivery and installation of voltage stabilizer at WTP site and allied works for Augmentation of Ramchandrapur water supply scheme District- Purulia, under Purulia Mechanical Division PHE, Dte. Dist- Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000307/2022-2023 | 95/PMD | 03/02/2023 | 04/04/2023 | MOON LIGHT HOUSE | 6.31 | 4.38 | 69.42 | 40
10 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 150 Cum including other allied works at OHR site of Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000229/2021-2022 | 733/RNP | 06/12/2021 | 04/02/2022 | MADHU SUDAN RAKSHIT | 4.59 | 4.18 | 91.05 | 25
11 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2021-2022 | 148/PD | 24/01/2022 | 24/04/2022 | MADHU SUDAN RAKSHIT | 10.63 | 10.62 | 99.88 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Ramchandrapur W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer |  | ORD/000401/2022-2023 | 340/RNP | 01/06/2022 | 01/07/2022 | VOYAGER | 1.4 | 1.06 | 75.47 | 80
13 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Repairing and renovation of existing Boundary Wall at Ramchandrapur WTP under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000919/2022-2023 | 1924/PD | 22/12/2022 | 21/01/2023 | MOONLIGHT HOUSE | 4.15 | 3.98 | 95.83 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Construction of pump house for accommodating centrifugal pump for pumping of water including panel room & chlorination room of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000491/2021-2022 | 524/PD | 30/03/2022 | 08/07/2022 | MADHU SUDAN RAKSHIT | 16.75 | 13.85 | 82.71 | 100
15 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 394 | 11/03/2022 | 11/03/2022 | Resource Division | 29.79 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 976/PD | 22/06/2022 | 22/06/2022 | Resource Division | 144.33 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Demand notice for renewal of 150mm dia M.S carrier pipe with 600mm dia MS casing pipe under Rly Track at Km. N305/25-27 in between Muradih-Madhukunda station by PHED/Purulia for Ramchandrapur W/s Scheme. (Letter No.Engg./TE/1/C dt.24/08/2022) |  |  | BILL/00072/2022-2023 | BP-2022-23-509 | 22/12/2022 | 22/12/2022 | F.A &C A.O/S.E RAILWAY GURDEN | 3.34 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Indian Railway miscellaneous collection. |  |  | BILL/00409/2023-2024 | BP-2023-24-302 | 14/07/2023 | 14/07/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supplying laying different dia HDPE and DI pipe including Functional Household Tap Connection (FHTC) for distribution system (Zone-I) augmentation of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. Sl no- 1 (Tender No- 23/2021-22 of SE/PMU/WBPWSP(P) ) |  |  | VCH/000908/2022-2023 | BP-2022-23-93 | 07/07/2022 | 07/07/2022 | ANUP KUMAR SAHA | 87.04 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Indian Railway miscellaneous collection. |  |  | BILL/00410/2023-2024 | BP-2023-24-303 | 14/07/2023 | 14/07/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum, Pump house for accommodating centrifugal pump and making inter-connection by CIDF & M.S Pipe for pumping of water including Panel room & Chlorination room, Boundary wall and Sinking of 3 (Three) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Santuri OHR campus of Santuri W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000890/2023-2024 | 1541/PD | 16/10/2023 | 01/02/2025 | CHATTERJEE CONSTRUCTION | 67.71 | 5.47 | 8.09 | 45
22 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Internal Illumination and Yard lighting arrangement at newly Constructed Pump House under under Augmentation of Ramchandrapur Water Supply Scheme, Block: Santuri, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER |  | ORD/000386/2023-2024 | 372/PMD | 04/03/2024 | 03/05/2024 | SEN BROTHERS | 11.66 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supplying, laying different dia HDPE pipe including Functional House Hold Tap Connection (FHTC) for Distribution System (Zone-III) of augmentation of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000096/2022-2023 | 621/PD | 20/04/2022 | 04/06/2022 | ASHOK KUMAR CHATTERJEE | 195.98 | 170.16 | 86.83 | 100
24 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supply delivery and installation of Centrifugal pump motor sets, MCC, with allied works at WTP site for Augmentation of Ramchandrapur water supply scheme Block: Santuri, Under Purulia Mechanical Division PHE Dte. Dist-Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000348/2022-2023 | 133/PMD | 20/02/2023 | 21/04/2023 | DEBJYOTI BASU | 34.04 | 33.54 | 98.54 | 100
25 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supplying, laying different dia HDPE pipe including Functional House Hold Tap Connection (FHTC) for Distribution System including Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 400 cum and staging height 20 mtr. (Zone-II) of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000600/2022-2023 | 1198/PD | 12/08/2022 | 09/05/2023 | NIBHAS SINHA | 316.96 | 250.64 | 79.07 | 100
26 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Rangadanga High School , OHR Campus under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 175 mtr.) | Assistant Engineer | Junior Engineer | ORD/001622/2023-2024 | 1832/PD | 12/12/2023 | 11/01/2024 | NIBHAS SINHA | 17.72 | 15.47 | 87.28 | 100
27 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Providing And Installation of H.O.T. Crane at newly constructed Pump House and old pump house under Augmentation of Ramchandrapur Water Supply Scheme, Block: Santuri, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000385/2023-2024 | 371/PMD | 04/03/2024 | 03/05/2024 | EASTERN INDIA SALES AND SERVICE | 16.98 | 0 | 0 | 100
28 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Quotation for new connection at Rangadanga OHR site under Ramchandrapur water supply scheme. |  |  | BILL/00089/2024-2025 | BP-24-25-11 | 10/05/2024 | 10/05/2024 | SANTURI CCC | 2.88 | 0 | 0 | 0
29 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Quotation money payment for new connection near baranti Dam |  |  | BILL/00168/2024-2025 | BP-2024-25-32 | 21/06/2024 | 21/06/2024 | SANTURI CCC | 6.19 | 0 | 0 | 0
30 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Quotation for New Connection at New Pump House at Ramchandrapur |  |  | BILL/00112/2024-2025 | BP-24-25-14 | 24/05/2024 | 24/05/2024 | SANTURI CCC | 1.29 | 0 | 0 | 0
31 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Bill for Load Enhancement for Aug of Ramchandrapur W/S Scheme. |  |  | BILL/00433/2023-2024 | BP-23-24-226 | 05/12/2023 | 05/12/2023 | WBSEDCL PURULIA | 1.41 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Laying of 200 mm dia DI pipe for Rising Main including allied works of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000174/2022-2023 | 791/PD | 05/05/2022 | 01/06/2025 | ASHOK KUMAR CHATTERJEE | 12.83 | 5.92 | 46.15 | 50
33 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supply delivery and installation of VT pump motor , MCC Panel and other electromechanical equipment's for Raw water intake pump house at Augmentation of Ramchandrapur PWSS, Block: Santuri, Under Purulia Mechanical Division PHE Dte Dist- Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000255/2022-2023 | 46/PMD | 19/01/2023 | 01/04/2025 | EASTERN INDIA SALES AND SERVICE | 65.49 | 35.92 | 54.85 | 100
34 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Supply, delivery and installation of Vertical multistage centrifugal pump motor sets , Panel , Flow meter and all electro mechanical equipments at Augmentation of Ramchandrapur water supply scheme for direct pumping Block- Santuri, under Purulia Mechanical Division PHE Dte. Dist- Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000308/2022-2023 | 96/PMD | 03/02/2023 | 01/04/2025 | EASTERN INDIA SALES AND SERVICE | 51.14 | 36.49 | 71.35 | 100
35 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Ramchandrapur CWR,Pump House Campus (Zone -II ) under Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, P.H.E. Dte. (Total length of Boundary Wall 217.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000915/2022-2023 | 1923/PD | 22/12/2022 | 29/05/2025 | MADHU SUDAN RAKSHIT | 21.27 | 16.7 | 78.52 | 80
36 | PURULIA |  | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Providing And Installation of 2 M.T. capacity manually operated curved monorail for Low Lift Pump House and High Lift Pump House under Augmentation of Sonathali Water Supply Scheme, Block: Kashipur, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000546/2023-2024 | 379/PMD | 04/03/2024 | 15/02/2025 | S. PATHAK & CO. | 10.22 | 0 | 0 | 100
37 | PURULIA |  | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | SM/10045 | Augmentation | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
Total | [13 empty] | 1332.43 | 728.98 | 54.71