## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : SAPUA MOUZA] (Tender No- 90/2022-23 of EE/PD) |  |  | VCH/001039/2022-2023 | BP-2022-23-373 | 19/10/2022 | 19/10/2022 | SOUMITRA CHAKRABORTY | 17.32 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-J : BANSHGARH (Part) MOUZA] (Tender No- 29/2021-22 of SE/PMU/WBPWSP(P) ) |  |  | VCH/001064/2022-2023 | BP-2022-23-410 | 28/10/2022 | 28/10/2022 | SADHAN GORAIN | 11.91 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-K : BANSHGARH(Part) MOUZA] (Tender No.983/EE/PD of 2021-22) |  |  | VCH/000175/2022-2023 | BP-2022-23-44 | 02/05/2022 | 02/05/2022 | BOSE CONSTRUCTION | 23.66 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : BERMA(Part) MOUZA] (Tender No- 168/2022-23 of EE/PD) |  |  | VCH/001065/2022-2023 | BP-2022-23-409 | 28/10/2022 | 28/10/2022 | MS GORAIN CONCERN | 35.37 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line for augmentation of Balarampur (Zone-II) Water Supply Scheme of Purulia Sadar Sub- Division under Purulia Division, PHE Dte. [Part- G Rangadih (Part) Mouza] (Tender No- 979/2021-22 of EE/PD) |  |  | VCH/001080/2022-2023 | BP-2022-23-437 | 30/11/2022 | 30/11/2022 | SIKHA ENTERPRISES | 10.34 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-I : BALARAMPUR(Part) MOUZA] | Assistant Engineer |  | ORD/000391/2021-2022 | 230/PD | 09/02/2022 | 26/03/2022 | TUMPA GORAIN | 18.71 | 18.11 | 96.81 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-K : BANSHGARH(Part) MOUZA] | Assistant Engineer |  | ORD/000390/2021-2022 | 229/PD | 09/02/2022 | 26/03/2022 | BOSE CONSTRUCTION | 53.83 | 0 | 0 | 65
8 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-M : TENTLOW(Part) MOUZA] | Assistant Engineer |  | ORD/000389/2021-2022 | 228/PD | 09/02/2022 | 11/03/2022 | ANUDIP SAHA | 9.57 | 9.5 | 99.26 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : SAPUA MOUZA] | Assistant Engineer |  | ORD/000074/2022-2023 | 651/PD | 22/04/2022 | 06/06/2022 | SOUMITRA CHAKRABORTY | 95.27 | 48.87 | 51.29 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under augmentation of Balarampur W/S Scheme (Zone-I) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : Water Supply through Direct pumping at Chhota Urma (Part), Namsol (Part) & Amruhansa Mouza] (2nd Call) | Assistant Engineer | Junior Engineer-3 | ORD/000349/2022-2023 | 877/PD | 23/05/2022 | 07/07/2022 | ANUP KUMAR SAHA | 156.85 | 100.58 | 64.13 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Laying of parallel distribution pipeline for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Balarampur (Zone-II) Water Supply Scheme of Balarampur Block under Purulia Sadar Sub-Division,PHE Dte ( Mouza- SAPUA) | Assistant Engineer |  | ORD/000873/2022-2023 | 1841/PD | 12/12/2022 | 26/01/2023 | SOUMITRA CHAKRABORTY | 39.68 | 4.23 | 10.67 | 25
12 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Laying of DI & MS distribution pipeline including installation of sluice valve due to widening & strengthening of Balarampur NH-32 of Balarampur W/S Scheme [Zone-II] of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/001096/2022-2023 | 363/PD | 14/03/2023 | 13/04/2023 | KOUSHIK CHATTERJEE | 7.39 | 0 | 0 | 0
13 | PURULIA |  | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Balarampur OHR side zone-2 for Augmentation of Balarampur Water Supply scheme Block Balarampur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000037/2023-2024 | 443/PMD | 20/04/2023 | 20/05/2023 | ASHUTOSH DAS AND CO. | 21.56 | 0 | 0 | 0
14 | PURULIA |  | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Internal and external illumination with other allied works for augmentation of Balarampur OHR site(Z-1 & Z-2) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000211/2023-2024 | 1197/PMD | 03/11/2023 | 02/01/2024 | MOON LIGHT HOUSE | 8.85 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-C : BERMA(Part) MOUZA] | Assistant Engineer |  | ORD/000394/2021-2022 | 233/PD | 09/02/2022 | 26/03/2022 | SOUMITRA CHAKRABORTY | 21.93 | 20.46 | 93.29 | 100
16 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-G : RANGADIH(Part) MOUZA] | Assistant Engineer | Junior Engineer-3 | ORD/000392/2021-2022 | 231/PD | 09/02/2022 | 26/03/2022 | SIKHA ENTERPRISES | 11.76 | 0.73 | 6.22 | 100
17 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Construction of Boundary wall with other allied works at Balarampur Zone-I OHR site under Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub_ Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000859/2022-2023 | 1812/PD | 06/12/2022 | 20/01/2023 | SHYAMAL KUMAR DEY | 15.1 | 13.55 | 89.74 | 91
18 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 396/PD | 11/03/2022 | 11/03/2022 | Resource Division | 24.46 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 989/PD | 23/06/2022 | 23/06/2022 | Resource Division | 127.38 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Continuation work for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Chitmu W/S Scheme & Balarampur W/S Scheme (Zone-I), block-Jhalda-II & Balarampur) to be augmentation/ Rejuvenation under Purulia Division, PHE Dte. (Tender No- 844/2021-22 of EE/PD) |  |  | VCH/000921/2022-2023 | BP-2022-23-106 | 16/07/2022 | 16/07/2022 | ROY CHOWDHURY ASSOCIATES | 2.37 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Indian Railways Miscellaneous collection. |  |  | BILL/00091/2022-2023 | BP-2022-23-5178 | 02/01/2023 | 02/01/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 6.34 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Balarampur W/S Scheme (Zone-II) Block- Balarampur ) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 541/2021-22 of EE/PD) |  |  | VCH/000912/2022-2023 | BP-2022-23-89 | 07/07/2022 | 07/07/2022 | HORIZEN | 8.39 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on i) Balarampur-Bagmundi Road and ii) Jhalda-Bagmundi Road in respect of Augumentation of Balarampur water supply scheme in the District of Purulia. |  |  | BILL/00062/2022-2023 | BP-2022-23-510 | 22/12/2022 | 22/12/2022 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 45.73 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Chitmu W/S Scheme & Balarampur W/S Scheme Zone-I block-Jhalda II & Balarampur) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 358/2021-22 of EE/PD) |  |  | VCH/000937/2022-2023 | BP-2022-23-108 | 16/07/2022 | 16/07/2022 | ROY CHOWDHURY ASSOCIATES | 2.79 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under augmentation of Balarampur W/S Scheme (Zone-I) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-A : Water Supply through OHR at Baraurma, Berada, Chhota Urma (Part), & Namsol (Part) Mouza] | Assistant Engineer | Junior Engineer-3 | ORD/000419/2021-2022 | 314/PD | 25/02/2022 | 11/04/2022 | SANTANU BANERJEE | 261.89 | 176.84 | 67.52 | 92
26 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-D : BERMA(Part) MOUZA] | Assistant Engineer | Junior Engineer-3 | ORD/000393/2021-2022 | 232/PD | 09/02/2022 | 26/03/2022 | MANATOSH SINGH | 32.6 | 13.04 | 39.99 | 70
27 | PURULIA |  | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, Flowmeter, MCC Panel and other allied works for augmentation of Balarampur WTP under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000455/2022-2023 | 197/PMD | 24/02/2023 | 25/04/2023 | ORIENTAL ENGINEERING CO. | 147.95 | 83.65 | 56.54 | 55
28 | PURULIA |  | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, floor mounted MCC panel, Voltage stabilizer, Flowmeter and other allied works for augmentation of Balarampur OHR site(Zone-1) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000212/2023-2024 | 1198/PMD | 03/11/2023 | 02/03/2024 | COMBINE ENTERPRISES | 33.66 | 10.22 | 30.38 | 55
29 | PURULIA |  | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, floor mounted MCC panel, Voltage stabilizer, Flowmeter and other allied works for augmentation of Balarampur OHR site(Zone-2) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000213/2023-2024 | 1199/PMD | 03/11/2023 | 02/03/2024 | COMBINE ENTERPRISES | 34.58 | 10.25 | 29.64 | 60
30 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Construction of Guard Room with sanitary and plumbing arrangment with approach road, plinth protection, surface drain etc. complete at Balarampur Zone-I for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/003454/2023-2024 | 323/PD | 01/03/2024 | 30/05/2024 | PURNA CHANDRA TEWARI | 5.29 | 3.37 | 63.73 | 60
31 | PURULIA |  | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Supply delivery and installation of MS pipe, specials including supply and laying of different size cables including allied works at WTP site under Augmentation of Balarampur Water supply scheme under Purulia Mechanical Division, PHE Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000626/2024-2025 | 1548/PMD | 11/11/2024 | 10/01/2025 | ORIENTAL ENGINEERING CO. | 15.53 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Laying of Parallel distribution Pipeline at Barabazar Road and Balarampur Town at Balarampur Zone-2 to Providing FHTC under Balarampur Water Supply Scheme in Connection with Jal-Jeevan Mission Works at Purulia Division ,PHEDte. | Assistant Engineer | Junior Engineer-3 | ORD/003453/2023-2024 | 315/PD | 01/03/2024 | 30/04/2024 | SADHAN GORAIN | 95.14 | 28.47 | 29.93 | 20
33 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection(FHTC) in Connection with jal jeevan mission(JJM and Jal Jeevan) and Laying of parallel line under command area of Balarampur Water Supply Scheme of Balarampur Block under Purulia Division, PHE Dte (Kadamdih Mouza) |  |  | ORD/003967/2023-2024 | 511/PD | 16/03/2024 | 15/05/2024 | DEBASISH CHAKRABORTY | 11.92 | 0 | 0 | 0
34 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Construction of 6.0 x 3.50 mtr size Panel room with other allied works for Augmentation of Balarampur W/S Scheme at Balarampur WTP site of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000860/2022-2023 | 1813/PD | 06/12/2022 | 20/01/2023 | SABYASACHI MISHRA | 4.09 | 4 | 97.79 | 100
35 | PURULIA |  | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, flowmeter, MCC panel and other allied works at intake side pump house for augmentation of Balarampur water supply scheme under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000256/2022-2023 | 47/PMD | 19/01/2023 | 20/03/2023 | COMBINE ENTERPRISES | 74.71 | 74.31 | 99.47 | 100
36 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | PCC Road restoration work due to dismantling the road for providing functional househole tap connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at Balarampur (Part) mouza for Agumentation of Balarampur (Zone -II) W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001059/2022-2023 | 291/PD | 27/02/2023 | 14/03/2023 | TUMPA GORAIN | 1.88 | 1.36 | 72.41 | 100
37 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Repairing and Renovation of Boundary wall & centry room including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001036/2022-2023 | 324/PD | 09/03/2023 | 08/04/2023 | ANADI MAHATO | 3.27 | 3.02 | 92.25 | 100
38 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 m3 at River site including repairing of boundary wall at OHR site & shifting of 150mm dia DI distribution pipeline for Ramnagar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 397/PD | 16/03/2023 | 24/06/2023 | SWASTIK ENTERPRISE | 24.75 | 5.38 | 21.73 | 100
39 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Balarampur_Zone-I OHR site for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000012/2023-2024 | 540/PD | 12/04/2023 | 21/07/2023 | SHYAMAL KUMAR DEY | 14.21 | 14.19 | 99.84 | 81
40 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Balarampur_Zone-II (Berma) OHR site for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000013/2023-2024 | 541/PD | 12/04/2023 | 21/07/2023 | SADHAN GORAIN | 14.25 | 14.23 | 99.84 | 65
41 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 800 Cum (Intze Type) including bypass arrangement & other allied works in connection with Jal Jeevan Mission (JJM) for Augmentation of Zone-II of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000089/2023-2024 | 819/PD | 26/06/2023 | 24/09/2023 | SADHAN GORAIN | 18.27 | 17.83 | 97.6 | 100
42 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Repairing and Renovation of High lift pump house & Sub station building including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000169/2023-2024 | 940/PD | 19/07/2023 | 18/08/2023 | SAIBAL SARKAR | 5.95 | 5.77 | 96.99 | 70
43 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 180 Cum (Intze Type) including bypass arrangement & other allied works in connection with Jal Jeevan Mission (JJM) for Augmentation of Zone-I of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000054/2023-2024 | 661/PD | 17/05/2023 | 16/07/2023 | SHYAMAL KUMAR DEY | 9.17 | 6.81 | 74.27 | 100
44 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Construction of Guard Room with sanitary and plumbing arrangment with approach road, plinth protection, surface drain etc. complete at Balarampur Zone-II OHR Site for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/003452/2023-2024 | 328/PD | 02/03/2024 | 31/05/2024 | MOHOR CONSTRUCTION | 5.29 | 5.21 | 98.54 | 100
45 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line of Balarampur (Zone-II) W/S Scheme of Purulia SadarSub_Division under Purulia Division PHE Dte. [Tentlow Mouza] | Assistant Engineer | Junior Engineer-3 | ORD/000118/2024-2025 | 891/PD | 07/05/2024 | 21/06/2024 | SIKHA ENTERPRISES | 12.4 | 10.72 | 86.45 | 100
46 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Office Computer purpose bill payment. |  |  | BILL/00058/2024-2025 | BP-2024-25-58 | 14/05/2024 | 14/05/2024 | SRI KRISHNA COMPUTER | 0.5 | 0 | 0 | 0
47 | PURULIA |  | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | New Connection for Augmentation of Balarampur. |  |  | BILL/00485/2023-2024 | BP-23-24-246 | 28/12/2023 | 28/12/2023 | WBSEDCL PURULIA | 6.55 | 0 | 0 | 0
48 | PURULIA |  | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | New Connection for Augmentation of Balarampur. |  |  | BILL/00486/2023-2024 | BP-23-24-245 | 28/12/2023 | 28/12/2023 | WBSEDCL PURULIA | 4.7 | 0 | 0 | 0
49 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : BERMA(Part) MOUZA] | Assistant Engineer | Junior Engineer-3 | ORD/000395/2021-2022 | 234/PD | 09/02/2022 | 05/10/2023 | MS GORAIN CONCERN | 70.99 | 0 | 0 | 65
50 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-F : RANGADIH(Part) MOUZA] | Assistant Engineer | Junior Engineer-3 | ORD/000426/2021-2022 | 357/PD | 04/03/2022 | 15/02/2026 | SADHAN GORAIN | 136.58 | 22.56 | 16.52 | 70
51 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-J : BANSHGARH (Part) MOUZA] | Assistant Engineer | Junior Engineer-3 | ORD/000427/2021-2022 | 367/PD | 04/03/2022 | 05/03/2026 | SADHAN GORAIN | 129.15 | 29.24 | 22.64 | 70
52 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-H : BALARAMPUR(Part) MOUZA] | Assistant Engineer | Junior Engineer-3 | ORD/000439/2021-2022 | 366/PD | 04/03/2022 | 07/02/2026 | SADHAN GORAIN | 107.69 | 35.49 | 32.95 | 70
53 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-A : DIRECT PUMPING AT BELA, SUNIDIH & RANGADIH MOUZA] | Assistant Engineer | Junior Engineer-3 | ORD/000440/2021-2022 | 365/PD | 04/03/2022 | 03/09/2025 | SADHAN GORAIN | 281.46 | 161.01 | 57.21 | 82
54 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Construction of Chlorine cum Switch Room & Guard Room with sanitary and plumbing arrangment with other allied works at Zone-II OHR Site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000040/2023-2024 | 657/PD | 17/05/2023 | 31/08/2024 | SADHAN GORAIN | 7.96 | 0 | 0 | 100
55 | PURULIA |  | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | SM/10046 | Augmentation | Repairing and Renovation of Boundary wall including withdrawing and relaying pipeline and other allied works at Zone-II OHR site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000113/2023-2024 | 881/PD | 03/07/2023 | 02/09/2024 | MS GORAIN CONCERN | 8.19 | 0 | 0 | 100
Total | [13 empty] | 2357.13 | 953.02 | 40.43