## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) (Tender No.963/EE/PD of 2021-22) |  |  | VCH/000133/2022-2023 | BP-2022-23-7 | 05/04/2022 | 05/04/2022 | MUNNA AGROTECH ENTERPRISE | 62.99 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Sinking of 4 nos 200 mm dia river bed tube well (Horizon) of Darekeswar river (Baikara Ghat) along with laying of 100mm dia GI collecting line with all allied works under Kashipur W/S Scheme (Tender No- 1008/EE/PD of 2021-22) |  |  | VCH/000191/2022-2023 | BP-2022-23-56 | 20/05/2022 | 20/05/2022 | RABIN CHANDRA CHAIL | 9.27 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kashipur W/S Scheme, Block - Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.727/EE/PD of 2021-22) |  |  | VCH/001019/2021-2022 | BP-2021-22-266 | 28/02/2022 | 28/02/2022 | STEELCONC AND ASSOCIATES | 4.78 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-A) (Tender No.37/SE/PMU of 2022-23) |  |  | VCH/000679/2022-2023 | BP-2022-23-360 | 30/09/2022 | 30/09/2022 | SANTANU BANERJEE | 207.93 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kashipur W/S Scheme, Block - Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.727/EE/PD of 2021-22) |  |  | VCH/000964/2021-2022 |  | 23/02/2022 | 23/02/2022 | STEELCONC AND ASSOCIATES | 4.78 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kashipur W/S Scheme, Block Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.836/EE/PD of 2021-22) |  |  | VCH/001113/2021-2022 | BP-2021-22-333 | 23/03/2022 | 23/03/2022 | STEELCONC AND ASSOCIATES | 1.97 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | Assistant Engineer |  | ORD/000403/2021-2022 | 260/PD | 11/02/2022 | 12/04/2022 | MUNNA AGROTECH ENTERPRISE | 88.48 | 18.48 | 20.88 | 100
8 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied for Augmentation at KASHIPUR w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000251/2022-2023 | 40/PMD | 19/01/2023 | 20/03/2023 | PINTU DEY | 7.98 | 7.97 | 99.79 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Sinking of 4 (Four) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river (Baikara Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Kashipur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000398/2021-2022 | 237/PD | 09/02/2022 | 11/03/2022 | RABIN CHANDRA CHAIL | 26.74 | 16.39 | 61.31 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Construction of Pump House at Head work site under Kashipur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000404/2021-2022 | 261/PD | 11/02/2022 | 22/05/2022 | RABIN CHANDRA CHAIL | 15.35 | 11.51 | 75 | 85
11 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Supply, Delivery and installation of 4 nos. submersible pumps motor sets with other allied works for augmentation of Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000093/2022-2023 | 519/PMD | 05/08/2022 | 04/09/2022 | DEY ENTERPRISE, HOWRAH | 10.24 | 10.23 | 99.91 | 80
12 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Kashipur W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer |  | ORD/000405/2022-2023 | 344/RNP | 01/06/2022 | 01/07/2022 | GLORY ENGINEERS SYNDICATE | 1.4 | 1.4 | 100 | 100
13 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Supply delivery and installation of 125 KVA voltage stabilizer for Augmentation of KASHIPUR water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000284/2022-2023 | 75/PMD | 01/02/2023 | 02/04/2023 | PINTU DEY | 11.26 | 11.26 | 100 | 100
14 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Supply delivery and fitting of 3 Ton capacity triple spur gear type chain pulley Block Mono rail with others allied works for Augmentation at KASHIPUR w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000252/2022-2023 | 41/PMD | 19/01/2023 | 20/03/2023 | RABINDRA NATH KHAN | 9.64 | 9.64 | 100 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Route Survey & Drawing Preparation for uncovered areas under Kashipur Block under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 526/PD | 10/04/2023 | 25/04/2023 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.95 | 4.94 | 99.94 | 100
16 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2021-2022 | 399/PD | 11/03/2022 | 11/03/2022 | Resource Division | 17.15 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 962/PD | 21/06/2022 | 21/06/2022 | Resource Division | 18.67 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 975/PD | 22/06/2022 | 22/06/2022 | Resource Division | 3.52 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Argumentation of Kashipur W/S Scheme on Hura Kaaluput Adra Raghunathpur Road (From Ch.16.00 Km to Ch.16.346 Km) under Purulia Division PWD in the District of Purulia during the year 2023-2024. |  |  | BILL/00455/2023-2024 | BP-2023-24-312 | 26/07/2023 | 26/07/2023 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 11.08 | 0 | 0 | 0
20 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 60 KVA AT 0.4 KV TO 105/105/105/105/105 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 950023805) TO THEIR PREMISES AT KASHIPUR WATER SUPPLY KASHIPUR DIST PURULIA UNDER REGIONAL OFFICE PURULIA |  |  | VCH/000424/2022-2023 | BP-22-23-87 | 28/02/2023 | 28/02/2023 | WBSEDCL PURULIA | 3.71 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Construction of RCC elevated reservoir of capacity 250 cum Other allied works under Kashipur W/S Scheme under Raghunathpur Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2022-2023 | 652/PD | 22/04/2022 | 17/01/2023 | NANIGOPAL DEY | 62.33 | 54.15 | 86.87 | 100
22 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Repairing and Renovation of R.C.C. Old and New Elevated Reservoir including Pump House and other allied works under Kashipur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000920/2022-2023 | 1928/PD | 22/12/2022 | 22/03/2023 | SUDHANSHU OJHA | 11.58 | 11.49 | 99.19 | 75
23 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Supply delivery & installation of flow meter and with others allied works for Augmentation at KASHIPUR w/s scheme under Purulia Mechanical Division, PHE, Dte. in the Purulia District. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000341/2022-2023 | 123/PMD | 15/02/2023 | 16/04/2023 | SANTU MITRA | 3.92 | 3.74 | 95.29 | 30
24 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Supply delivery and installation of Centrifugal pumping machineries, MCC Panel with others allied works for Augmentation of KASHIPUR Water supply Scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000267/2022-2023 | 39/PMD | 19/01/2023 | 20/03/2023 | WEST BENGAL ENGINEERING CO | 67.56 | 66.8 | 98.87 | 43
25 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Laying of distribution pipe line & Restoration work by cleaning and chowkage clearance of distribution Main & including providing House Hold Tap Connection (FHTC) two no (Adivasi Hostel) and other allied works at Daldali village under Kashipur Piped water supply scheme of Raghunathpur Sub Division uneder Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000151/2024-2025 | 907/PD | 07/05/2024 | 06/07/2024 | CHANCHAL MISHRA | 2.61 | 2.61 | 99.89 | 100
26 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Construction of Meter Room at Pump House Site (Kaduri) of Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Under Kashipur Water Supply Scheme) | Assistant Engineer | Junior Engineer-1 | ORD/003510/2023-2024 | 347/PD | 04/03/2024 | 02/06/2024 | SUBHAS CHANDRA MAHATO | 2.03 | 1.91 | 93.85 | 100
27 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Supply, delivery & installation of submersible pumping machinery at River Bed Tubewell and changing cable line, clamping and other allied works at Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000242/2024-2025 | 1230/PMD | 13/08/2024 | 02/09/2024 | PINTU DEY | 1.62 | 1.61 | 99.76 | 100
28 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Cable laying from river bed site to pump house at kashipur water supply scheme of augumentation and other allied works under PMD, PHE Dte in the district of purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000045/2024-2025 | 963/PMD | 20/06/2024 | 20/07/2024 | PINTU DEY | 1.71 | 1.71 | 100 | 100
29 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Enhancement of the contract demand from 60 KVA at 0.4 KV to 105/105//105/105/105 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Kashipur Water Supply, (Consumer ID -950023805) |  |  | BILL/00893/2023-2024 | BP-23-24-311 | 21/03/2024 | 21/03/2024 | WBSEDCL KASHIPUR CCC | 4.47 | 0 | 0 | 0
30 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Supply, Delivery and installation of 4 nos. submersible pumps motor sets with other allied works for Augmentation work of Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000624/2024-2025 | 1546/PMD | 11/11/2024 | 14/02/2026 | PINTU DEY | 12.16 | 0 | 0 | 45
31 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Allied works for Laying pipe line , mending good of tap connection due to damage of road during construction of drainage system in connection with Jal jiban mission within Augmentation of Kashipur w/s Scheme under Raghunathpur Sub Division PHE Dte . | Assistant Engineer | Junior Engineer-1 | ORD/000023/2025-2026 | 580/PD | 07/04/2025 | 22/05/2025 | MAHARSHI BANERJEE | 28.69 | 0 | 0 | 80
32 | PURULIA |  | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-A) | Assistant Engineer | Junior Engineer-1 | ORD/000346/2022-2023 | 881/PD | 23/05/2022 | 26/01/2025 | SANTANU BANERJEE | 356.15 | 110.42 | 31 | 90
33 | PURULIA |  | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme | SM/10047 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kashipur Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000087/2022-2023 | 430/PMD | 23/06/2022 | 23/07/2022 | PREMNATH MITRA | 20.49 | 19.3 | 94.19 | 100
Total | [13 empty] | 1097.18 | 365.55 | 33.32