## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of 250mm dia DI (K9) pipe rising main from riverside pump house site to OHR site under Puncha W/s Scheme (T/N-940/21-22) |  |  | VCH/000242/2022-2023 |  | 05/07/2022 | 05/07/2022 | SWAPAN MANDAL | 11.08 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part -A) (Tender No- 33/2022-23 of SE/PMU) |  |  | VCH/001046/2022-2023 | BP-2022-23-387 | 19/10/2022 | 19/10/2022 | SWAPAN MANDAL | 16.59 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | New sinking of 4 nos 200 mm dia riverbed tube wells horizontal of kansai along with laying of 100mm dia GI connecting line with all allied works of Puncha W/S Scheme. (Tender No- 01/2022-23 of EE/PD) |  |  | VCH/000177/2022-2023 | BP-2022-23-49 | 19/05/2022 | 19/05/2022 | KOUSHIK CHATTERJEE | 9.58 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through OHR under command area of augmentation of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No-20/SE/PMU of 21-22) |  |  | VCH/000181/2022-2023 | BP-2022-23-52 | 17/05/2022 | 17/05/2022 | JAYANTA KUMAR MONDAL | 105.31 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Dhadki, Amalakanali) (Tender No- 985/2021-22 of EE/PD) |  |  | VCH/001033/2022-2023 | BP-2022-23-382 | 19/10/2022 | 19/10/2022 | SWAPAN MANDAL | 30.29 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Regarding laying of water supply pipe line aling road side and road croosing on Hura-Puncha Road from 19.00 Kmp to 21.00 Kmp in respect of Augmentation of Purulia water supply scheme (Dhadki more towards Puncha Girls High School) |  |  | VCH/000891/2022-2023 | BP-2022-23-430 | 24/11/2022 | 24/11/2022 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 32.27 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-B) (Tender No- 141/2022-23 of EE/PD) |  |  | VCH/001047/2022-2023 | BP-2022-23-388 | 19/10/2022 | 19/10/2022 | SWAPAN MANDAL | 56.04 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capacity 250 cum (Intze Type With Solid Raft), Staging height 20 metre for Distribution System under Puncha W/S Scheme under Purulia Division, PHE Dte. (Tender No- 27/2022-23 of EE/PD) |  |  | VCH/001058/2022-2023 | BP-2022-23-406 | 20/10/2022 | 20/10/2022 | JAYANTA KUMAR MONDAL | 29.19 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Pandui) | Assistant Engineer |  | ORD/000396/2021-2022 | 235/PD | 09/02/2022 | 10/04/2022 | SUNRISE ENGINEERING CORPORATION | 52.23 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | New sinking of 4 (Four) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Puncha river site of Puncha W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000365/2021-2022 | 150/PD | 24/01/2022 | 10/03/2022 | KOUSHIK CHATTERJEE | 25.5 | 0 | 0 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of balance distribution pipeline including other allied works for Puncha W/S scheme under Purulia Sadar Sub Division under Purulia Division ,PHE. Dte. | Assistant Engineer |  | ORD/000607/2022-2023 | 505/PSD | 12/08/2022 | 11/09/2022 | JAYANTA KUMAR MONDAL | 4.31 | 4.25 | 98.66 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of 180mm HDPE pipe with other allied works at Puncha Mouza to provide FHTC for Puncha W/S scheme under Purulia Sadar sub Division under Purulia Division ,PHE. Dte | Assistant Engineer |  | ORD/000605/2022-2023 | 503/PSD | 12/08/2022 | 11/09/2022 | JAYANTA KUMAR MONDAL | 4.48 | 4.25 | 94.91 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Construction of Boundary wall at Bahadurpur OHR Site under Puncha W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000830/2022-2023 | 1722/PD | 22/11/2022 | 21/01/2023 | RAHIBUDDIN MONDAL | 22.83 | 22.79 | 99.8 | 25
14 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 398/PD | 11/03/2022 | 11/03/2022 | Resource Division | 30.45 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 164/PD | 27/01/2022 | 27/01/2022 | Resource Division | 316.76 | 0 | 0 | 0
16 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 615/PMD | 01/06/2023 | 01/06/2023 | Resource Division | 1.55 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through OHR under command area of augmentation of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Tender No- 20/2021-22 of SE/PMU/WBPWSP(P) |  |  | VCH/001220/2021-2022 | BP-2021-22-335 | 23/03/2022 | 23/03/2022 | JAYANTA KUMAR MONDAL | 116.68 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum at Puncha OHR site of Puncha W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 23/2022-23 of EE/PD) |  |  | VCH/000918/2022-2023 | BP-2022-23-116 | 16/07/2022 | 16/07/2022 | SOUVIK MANDAL | 7.03 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of distribution pipe line from Bahadurpur CWR to Laulara mouza under command area of Puncha W/S Scheme (Tender No- 33/2022-23 of SE/PMU/WBPWSP(P) ) |  |  | VCH/000957/2022-2023 | BP-2022-23-132 | 19/07/2022 | 19/07/2022 | SWAPAN MANDAL | 85.91 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum at Puncha river site pump house of Puncha W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 29/2022-23 of EE/PD) |  |  | VCH/000919/2022-2023 | BP-2022-23-121 | 16/07/2022 | 16/07/2022 | KM ENTERPRISES | 7.01 | 0 | 0 | 0
21 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | New Connection for Augmentation of Puncha W/S Scheme |  |  | BILL/00251/2023-2024 | BP-2023-24-155 | 14/09/2023 | 14/09/2023 | WBSEDCL PURULIA | 2.8 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of 250 mm dia Di K9 pipe as rising main from riverside pump house site to OHR site under Puncha W/s Scheme of Purulia Sadar Sub- Division, under Purulia Division PHE Dte. (Tender No- 940/2021-22 of EE/PD) |  |  | VCH/000890/2022-2023 | BP-2022-23-75 | 01/07/2022 | 01/07/2022 | SWAPAN MANDAL | 11.08 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Office purpose computer bill payment. |  |  | BILL/00431/2023-2024 | BP-2023-24-300 | 14/07/2023 | 14/07/2023 | SRI KRISHNA COMPUTER | 0.95 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Dhadki, Amalakanali) | Assistant Engineer | Junior Engineer-3 | ORD/000397/2021-2022 | 236/PS | 09/02/2022 | 10/04/2022 | SWAPAN MANDAL | 65.64 | 0 | 0 | 90
25 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation & Supplying & laying of HDPE pipe through CWR for Distribution System of Puncha W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Tatari) | Assistant Engineer | Junior Engineer-3 | ORD/000784/2022-2023 | 1631/PD | 03/11/2022 | 18/12/2022 | SOUVIK MANDAL | 53.02 | 42.02 | 79.25 | 80
26 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of parallel line under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Laulara Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/001013/2022-2023 | 180/PD | 07/02/2023 | 24/03/2023 | MS D.PALIT AND CO. | 25.24 | 0 | 0 | 100
27 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Puncha OHR Site (Bahadurpur) for Augmentation of Puncha W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000055/2023-2024 | 662/PD | 17/05/2023 | 25/08/2023 | ASHOKE ADHIKARY | 14.24 | 0 | 0 | 60
28 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Providing and installation of HOT Crane, Electro magnetic Flow meter and other allied woks for Augmentation of Puncha Water Supply Scheme (River Site) under purilia Mechanical Division, P.H.E. Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000206/2023-2024 | 1196/PMD | 03/11/2023 | 01/05/2024 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 10.26 | 10.15 | 98.96 | 80
29 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capacity 250 cum (Intze Type With Solid Raft), Staging height 20 metre for Distribution System under Puncha W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000003/2022-2023 | 537/PD | 01/04/2022 | 27/12/2022 | JAYANTA KUMAR MONDAL | 66.71 | 17.38 | 26.06 | 100
30 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of parallel distribution pipeline for providing FHTC at Tatari Mouza of Puncha Water Supply Scheme ounder Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-3 | ORD/001088/2022-2023 | 356/PD | 14/03/2023 | 13/04/2023 | SOUVIK MANDAL | 3.67 | 3.64 | 99.28 | 100
31 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Augmentation of Puncha w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000130/2023-2024 | 868/PMD | 21/07/2023 | 19/09/2023 | SOUVIK MANDAL | 2.83 | 2.73 | 96.34 | 100
32 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of gap portion of Distribution pipeline at bridge portion Between Bahadurpur to puncha Mouzas for puncha W/S Scheme under purulia sadar Sub-Division under purulia division. PHE.Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000172/2023-2024 | 890/PD | 04/07/2023 | 03/08/2023 | J.S. CONSTRUCTION | 10.39 | 7.2 | 69.33 | 100
33 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Work of Vendoring service service relating to E-return for Income-Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f 01.10.2023 to 30.09.2024) |  |  | BILL/00706/2024-2025 | BP-2024-25-356 | 11/09/2024 | 11/09/2024 | NIGAM CONSULTANCY SERVICES | 0.77 | 0 | 0 | 0
34 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | New Connection for Augmentation of Puncha. |  |  | BILL/00487/2023-2024 | BP-23-24-247 | 28/12/2023 | 28/12/2023 | WBSEDCL PURULIA | 11.46 | 0 | 0 | 0
35 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-B) | Assistant Engineer | Junior Engineer-3 | ORD/000097/2022-2023 | 643/PD | 22/04/2022 | 04/03/2025 | SWAPAN MANDAL | 79.55 | 18.32 | 23.03 | 100
36 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Laulara) | Assistant Engineer | Junior Engineer-3 | ORD/000406/2022-2023 | 935/PD | 16/06/2022 | 31/07/2022 | MS D.PALIT AND CO. | 112.05 | 51.99 | 46.4 | 85
37 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Supply & installation of submersible pumping machinery at with MCC panel newly constructed River Bed Tubewell for Augmentation of Puncha w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000440/2022-2023 | 259/PMD | 06/03/2023 | 31/01/2026 | ANUP KR. SAHA | 36.41 | 24.26 | 66.64 | 66
38 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Puncha w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000047/2023-2024 | 516/PMD | 05/05/2023 | 10/01/2026 | EASTERN INDIA SALES AND SERVICE | 65.68 | 35.56 | 54.15 | 36
39 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Supply, delivery and installation of Open well Submersible pumping machinery with others electro-mechanical work at Puncha River site for Augmentation of Puncha PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000756/2024-2025 | 40/PMD | 10/01/2025 | 01/12/2025 | S. PATHAK & CO. | 9.44 | 0 | 0 | 100
40 | PURULIA |  | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Daily Operation & mtc. of rising main & distribution system, sluice valve, street stand post etc. under Puncha W/S Scheme under Purulia Sadar Sub-Division, P.H.E. Dte. [For the period of 01.09.2022 to 31.08.2023] | Assistant Engineer | Junior Engineer-3 | ORD/000662/2022-2023 | 1273/PD | 30/08/2022 | 30/08/2023 | M/S ACHARJEE CONSTRUCTION | 7.84 | 0 | 0 | 100
41 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Puncha w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000438/2022-2023 | 257/PMD | 06/03/2023 | 16/08/2025 | SWAPAN MANDAL | 3.01 | 0 | 0 | 90
42 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Supply, Delivery and installation 125kva voltage stabilizer for Augmentation of Puncha(River Site) w/s scheme for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000441/2022-2023 | 260/PMD | 06/03/2023 | 29/08/2025 | SEN BROTHERS | 13.61 | 13.08 | 96.1 | 100
43 | PURULIA |  | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | SM/10048 | Augmentation | Supply, Delivery and installation 60kva voltage stabilizer for Augmentation of Puncha w/s scheme(OHR Site) for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000439/2022-2023 | 258/PMD | 06/03/2023 | 16/08/2025 | SWAPAN MANDAL | 7.71 | 4.29 | 55.67 | 60
Total | [13 empty] | 1579.45 | 261.92 | 16.58