## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Repairing of Pipeline at Sirishgora road due to damage of Pipeline near New Culvert and Bandwan Bazar under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 434/2022-23 of EE/PD) |  |  | VCH/001051/2022-2023 | BP-2022-23-395 | 28/10/2022 | 28/10/2022 | BOSE CONSTRUCTION | 0.92 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Sirisgora Mouza) (Tender No- 998/2021-22 of EE/PD) |  |  | VCH/000993/2022-2023 | BP-2022-23-155 | 26/07/2022 | 26/07/2022 | ANUP KUMAR SAHA | 55.85 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Water supply arrangement of schools model-2 (201-500 students) at Bandwan Pry. School under Bandwan Block under RWS Purulia Sub- Division, PHE Dte. (Tender No- 1021/2021-22 of EE/PD) |  |  | VCH/000985/2022-2023 | BP-2022-23-148 | 25/07/2022 | 25/07/2022 | KABERI DUTTA | 0.98 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Pargela Mouza) (Tender No- 1002/2021-22 of EE/PD) |  |  | VCH/000992/2022-2023 | BP-2022-23-156 | 26/07/2022 | 26/07/2022 | BOSE CONSTRUCTION | 19.67 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Laying of G.I Pipeline and other allied works at Galudih Road near Culvert under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 410/2022-23 of EE/PD) |  |  | VCH/001052/2022-2023 | BP-2022-23-396 | 20/10/2022 | 20/10/2022 | ROY CONSTRUCTION | 1.07 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Various ICDS Centre and Schools and Supply of drinking water through water tanker to various places from nearby headwork sites of different W/S Scheme to mitigate draught like situation under Bandwan Block block of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000059/2022-2023 | 169/PSD | 18/04/2022 | 13/05/2022 | BOSE CONSTRUCTION | 1.68 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Laying of distribution pipe line at Sirishgora Mouza under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | Assistant Engineer | Junior Engineer-3 | ORD/000867/2022-2023 | 18111/PD | 06/12/2022 | 20/01/2023 | ANUP KUMAR SAHA | 13.22 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Supplying delivery fitting& fixing 20 nos of Sign board (ACP Sheet)at different solar tubewell site within Bandwan Block in Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001229/2022-2023 | 251/PSD | 31/03/2023 | 05/04/2023 | R.K ENTERPRISE | 0.48 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Installation of 3000 mm dia x 1800 mm Pressure shell for WTP at Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(2 Nos) | Assistant Engineer | Junior Engineer-3 | ORD/000340/2021-2022 | 58/PD | 13/01/2022 | 14/03/2022 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 23.8 | 23.79 | 99.94 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Installation of 3000 mm dia x 1800 mm (3 & 4 nos) Pressure filter shell for WTP under Augumentation of Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(2 Nos) | Assistant Engineer | Junior Engineer-3 | ORD/000489/2021-2022 | 523/PD | 30/03/2022 | 29/05/2022 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 23.63 | 23.62 | 99.94 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Repairing of Pipeline at Sirishgora road due to damage of Pipeline near New Culvert and Bandwan Bazar under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000505/2022-2023 | 441/PSD | 24/06/2022 | 04/07/2022 | BOSE CONSTRUCTION | 1.26 | 0 | 0 | 80
12 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Laying of G.I Pipeline and other allied works at Galudih Road near Culvert under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000507/2022-2023 | 443/PSD | 24/06/2022 | 09/07/2022 | ROY CONSTRUCTION | 1.07 | 0 | 0 | 100
13 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Replacement of H.L. Centrifugal pump with allied motor as needed at 950 KLD water treatment plant, Bundwan under PMD,PHE, Dte, in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000061/2022-2023 | 403/PMD | 17/06/2022 | 17/07/2022 | RABINDRA NATH KHAN | 9.19 | 9.19 | 100 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Augmentation of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Rithugora Mouza)Bardih Village,Jordih Village & Kodogora Village | Assistant Engineer | Junior Engineer-3 | ORD/000855/2022-2023 | 1806/PD | 06/12/2022 | 20/01/2023 | BOSE CONSTRUCTION | 11.49 | 9.61 | 83.64 | 25
15 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Laying of distribution pipe line at Sirishgora Mouza under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | Assistant Engineer | Junior Engineer | ORD/000866/2022-2023 | 1811/PD | 06/12/2022 | 20/01/2023 | ANUP KUMAR SAHA | 13.22 | 12.72 | 96.22 | 100
16 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Repairing and renovation of the damaged eleveted water reservoir at Bandwan OHR Site under Bandwan W/S Scheme Purulia Sadar Sub Division under Purulia Division , P.H.E. Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000834/2022-2023 | 1736/PD | 22/11/2022 | 06/01/2023 | SUJIT CHAKRABORTY | 6.15 | 4.37 | 71.1 | 100
17 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Supply and Delivery of different gaseous chlorine spare parts for Bandwan and other water supply schemes under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000343/2022-2023 | 125/PMD | 16/02/2023 | 18/03/2023 | RABINDRA NATH KHAN | 10.82 | 10.82 | 100 | 100
18 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Supplying delivery fitting& fixing 30 nos of Sign board (ACP Sheet)at different solar tubewell site within Bandwan Block in Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001228/2022-2023 | 250/PSD | 31/03/2023 | 05/04/2023 | R.K ENTERPRISE | 0.72 | 0.72 | 100 | 100
19 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 250 Cum with other allied works at WTP campus of Bandwan W/S scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000081/2022-2023 | 632/PD | 22/04/2022 | 31/07/2022 | WRISHI ENTERPRISE | 28.1 | 27.26 | 97 | 0
20 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 390/PD | 11/03/2022 | 11/03/2022 | Resource Division | 37.05 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 1015/PD | 05/07/2022 | 05/07/2022 | Resource Division | 225.01 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 239/PD | 20/02/2023 | 20/02/2023 | Resource Division | 228.79 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Jitan Mouza) Jitan village (Tender No- 1035/2021-22 of EE/PD) |  |  | VCH/000880/2022-2023 | BP-2022-23-70 | 01/07/2022 | 01/07/2022 | ROY CONSTRUCTION | 7.17 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Bandwan W/S Scheme & Bandwan Spot W/S Scheme block-Bandwan) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 536/2021-22 of EE/PD) |  |  | VCH/000911/2022-2023 | BP-2022-23-90 | 07/07/2022 | 07/07/2022 | RADIANT | 1.26 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on i) Manbazar-Bandwan-Kuilapal Road ii) Barabazar-Bandwan Road iii) Bandwan-Ashanpani Road in respect of Augmentation of bandwan water supply scheme in the District of Purulia. |  |  | BILL/00173/2022-2023 | BP-2022-23-662 | 23/02/2023 | 23/02/2023 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 139.71 | 0 | 0 | 0
26 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 85 KVA AT 0.4 KV TO 245/245/245/245/245 KVA RESPECTIVELY AT 11 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 942408200) TO THEIR PREMISES AT BUNDWAN WATER SUPPLY DIST PURULIA UNDER REGIONAL OFFICE PURULIA |  |  | VCH/000422/2022-2023 | BP-22-23-84 | 28/02/2023 | 28/02/2023 | WBSEDCL PURULIA | 9.31 | 0 | 0 | 0
27 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | FOR NEW SERVICE CONNECTION OF AUGMENTATION OF BUNDWAN WATER SUPPLY SCHEME |  |  | BILL/00043/2022-2023 |  | 28/02/2023 | 28/02/2023 | WBSEDCL PURULIA | 0.71 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Jitan Mouza) Bamandiha village (from node J-851 to J-864) Part- B (Tender No- 55/2022-23 of EE/PD) |  |  | VCH/000913/2022-2023 | BP-2022-23-88 | 07/07/2022 | 07/07/2022 | CHATTERJEE CONSTRUCTION | 2.47 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Jitan Mouza) Bamandiha village [from node J-846 to J-851 Part A] (Tender No- 32/2022-23 of EE/PD) |  |  | VCH/000898/2022-2023 | BP-2022-23-82 | 01/07/2022 | 01/07/2022 | CHATTERJEE CONSTRUCTION | 2.43 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Refreshment bill paid for office meeting. |  |  | BILL/00604/2023-2024 | BP-2023-24-368 | 10/08/2023 | 10/08/2023 | MATHUR DUTTA | 0.12 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Office stationary bill payment. |  |  | BILL/00244/2023-2024 | BP-2023-24-150 | 30/05/2023 | 30/05/2023 | KETIKA CONSUMERS CO-OP STORES LTD | 1.47 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. |  |  | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 02/08/2023 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
33 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Sirishgora Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/000414/2021-2022 | 335/PD | 28/02/2022 | 29/05/2022 | ANUP KUMAR SAHA | 95.06 | 17.8 | 18.73 | 85
34 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Rithugora Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/000412/2021-2022 | 333/PD | 28/02/2022 | 29/04/2022 | BOSE CONSTRUCTION | 51.38 | 28.05 | 54.58 | 80
35 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Bamandiha Village(From node J-851 to J-864)(Part-B) | Assistant Engineer | Junior Engineer-3 | ORD/000004/2022-2023 | 150/PSD | 04/04/2022 | 29/04/2022 | CHATTERJEE CONSTRUCTION | 4.59 | 1.24 | 27.01 | 100
36 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Jitan Village | Assistant Engineer | Junior Engineer-3 | ORD/000413/2021-2022 | 334/PD | 28/02/2022 | 30/03/2022 | ROY CONSTRUCTION | 18.56 | 5.22 | 28.15 | 100
37 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Bamandiha Village(From node J-846 to J-851)(Part-A) | Assistant Engineer | Junior Engineer-3 | ORD/000449/2021-2022 | 98/PSD | 14/03/2022 | 08/04/2022 | CHATTERJEE CONSTRUCTION | 4.56 | 0.89 | 19.5 | 100
38 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing internal and external illumination arrangement at existing at Intake pump house, clear water, chemical house building, substation building, OHR site Chorination room for Augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000119/2022-2023 | 547/PMD | 18/08/2022 | 17/09/2022 | ASHOKE ADHIKARY | 8.91 | 7.83 | 87.83 | 90
39 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Construction of Over Head reservoir (OHR) of capacity 350 Cum with other allied works of Bandwan W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000928/2022-2023 | 1890/PD | 15/12/2022 | 11/09/2023 | PRAVAT SARKAR | 118.62 | 34.64 | 29.2 | 100
40 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chilla Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/000082/2022-2023 | 633/PD | 22/04/2022 | 21/06/2022 | BOSE CONSTRUCTION | 96.26 | 81.71 | 84.89 | 100
41 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Sinking of 200mmX165mm tubewell and other allied works at Bandwan spot water supply scheme Purulia,under PMD, PHE Dte. in the District of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000189/2023-2024 | 1179/PMD | 03/11/2023 | 18/11/2023 | SAIBAL SARKAR | 7.13 | 6.76 | 94.89 | 100
42 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Augmentation of existing old VCB by the new one(one incoming two outgoing) and installation of one new transformer for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000118/2022-2023 | 537/pmd | 17/08/2022 | 16/10/2022 | M/S M S ENTERPRISE | 66.56 | 66.56 | 100 | 100
43 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | SHIFTING OF ENERGY METER FROM EXISTING METER ROOM TO ANOTHER METER ROOM AT AUG OF BUNDWAN WATER SUPPLY SCHEME UNDER PMD PHE DTE. |  |  | BILL/00099/2023-2024 | C072325293658 | 14/07/2023 | 14/07/2023 | WBSEDCL PURULIA | 0.26 | 0 | 0 | 0
44 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Additional Quotation for PHE Connection at Chilla. |  |  | BILL/00501/2023-2024 | BP-23-24-270 | 22/01/2024 | 22/01/2024 | WBSEDCL PURULIA | 4.02 | 0 | 0 | 0
45 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | LOAD ENHANCEMENT FOR AUG OF BUNDWAN WS SCHEME |  |  | BILL/00604/2023-2024 | BP-2023-24-201 | 17/10/2023 | 17/10/2023 | WBSEDCL PURULIA | 0.71 | 0 | 0 | 0
46 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Supudih Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/000410/2022-2023 | 937/PD | 16/06/2022 | 31/12/2025 | SANTANU BANERJEE | 120.63 | 81.87 | 67.87 | 65
47 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Laying of Main line and Parallel line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Bandwan Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/001062/2022-2023 | 295/PD | 27/02/2023 | 01/04/2026 | DEBAKI RANJAN SARKAR | 67.69 | 23.48 | 34.69 | 30
48 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Supply delivery and installation of Flowmeter for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000091/2022-2023 | 526/PMD | 05/08/2022 | 01/02/2025 | SUBRATA DUTTA | 8.02 | 4.67 | 58.3 | 100
49 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Supply delivery and installation of centrifugal pumping machineries with necessary allied works at intake for augmentation of Bandwan w/s project under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000096/2022-2023 | 522/PMD | 05/08/2022 | 01/12/2025 | TAPAN KUMAR DEY | 27.3 | 17.41 | 63.78 | 65
50 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Supply delivery and installation of centrifugal pumping machineries with necessary substitutes with allied works for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000097/2022-2023 | 523/PMD | 05/08/2022 | 04/10/2022 | RABINDRA NATH KHAN | 88.94 | 53.46 | 60.11 | 65
51 | PURULIA |  | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bandwan Water Supply scheme (OHR site) Block Bandwan under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2022-2023 | 394/PMD | 16/06/2022 | 01/04/2025 | S P CONSTRUCTION | 20.5 | 0 | 0 | 100
52 | PURULIA |  | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10198 | Augmentation | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
Total | [13 empty] | 1693.19 | 553.7 | 32.7