## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10222 | School | FHTC Connetion for School Purulia-I W/s Scheme. |  |  | VCH/000293/2022-2023 |  | 18/07/2022 | 18/07/2022 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 61 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10222 | School | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Purulia-1 Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000464/2021-2022 | 435/PD | 21/03/2022 | 05/05/2022 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 190.01 | 145.69 | 76.67 | 100
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10222 | School | Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage =-IV or as similar model for Surveying the work of AWC in 10 Nos. Blocks within Purulia District under RWS Purulia Sub Division under Purulia Division PHE Dte | Assistant Engineer |  | ORD/001691/2023-2024 | 258/A/PR | 03/05/2023 | 23/05/2023 | ANUP KUMAR SAHA | 0.29 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10222 | School | Water supply Tap Connection Arrangement for 54 nos School upto 200 Students, within Purulia-I Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2022-2023 | 565/PD | 08/04/2022 | 23/05/2022 | MS D.PALIT AND CO. | 227.74 | 162.24 | 71.24 | 100
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10222 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, 3 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Balarampur Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000380/2022-2023 | 925/PD | 07/06/2022 | 22/07/2022 | ANUP KUMAR SAHA | 188.97 | 176.87 | 93.6 | 100
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10222 | School | Water supply Tap Connection Arrangement for 6 nos AWC within Purulia-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000146/2022-2023 | 758/PD | 02/05/2022 | 16/06/2022 | SOUHARDYA BUSINESS LINE | 27.15 | 0 | 0 | 100
Total | [13 empty] | 695.16 | 484.8 | 69.74