## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Water supply tap connection arrangement for 38 nos. school upto 200 students within Purulia-II block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No- 33/2021-22 of SE/PMU/WBPWSP(P) ) |  |  | VCH/000947/2022-2023 | BP-2022-23-113 | 16/07/2022 | 16/07/2022 | ANUP KUMAR SAHA | 65.04 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Water supply tap connection arrangement for 38 nos. school upto 200 students within Manbazar-II block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No- 15/2022-23 of SE/PMU/WBPWSP(P) ) |  |  | VCH/000946/2022-2023 | BP-2022-23-114 | 16/07/2022 | 16/07/2022 | KOUSHIK CHATTERJEE | 66.37 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage =-IV or as similar model for Surveying the work of AWC in 10 Nos. Blocks within Purulia District under RWS Purulia Sub Division under Purulia Division PHE Dte | Assistant Engineer |  | ORD/001695/2023-2024 | 258-B/PR | 03/05/2023 | 23/05/2023 | ANUP KUMAR SAHA | 0.29 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Manbazar-II Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2022-2023 | 578/PD | 12/04/2022 | 27/05/2022 | PREMNATH MITRA | 228 | 151.47 | 66.44 | 100
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Water supply Tap Connection Arrangement for 9 nos AWC within Bagmundi Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000486/2021-2022 | 497/PD | 29/03/2022 | 13/05/2022 | SUNRISE ENGINEERING CORPORATION | 71.04 | 0 | 0 | 100
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students, within Manbazar-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000091/2022-2023 | 673/PD | 25/04/2022 | 09/06/2022 | KOUSHIK CHATTERJEE | 159.88 | 47.46 | 29.69 | 100
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Water supply Tap Connection Arrangement for 46 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Purulia-II Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2021-2022 | 402/PD | 11/03/2022 | 25/04/2022 | EQUIPMENTS AND SPARES AGENCIES | 223.56 | 173.89 | 77.78 | 100
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewells sinked at various Schools & AWCs of . Bundwan & Manbazar-II Blocks under Purulia Division ,PHE,Dte. | Assistant Engineer | Junior Engineer | ORD/001380/2023-2024 | 1736/PD | 04/12/2023 | 03/01/2024 | PRAKASH DESHMUKH | 9.8 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Xerox bill paid for Division office |  |  | BILL/00027/2024-2025 | BP-2024-25-29 | 26/04/2024 | 26/04/2024 | DUTTA XEROX CENTRE | 1.07 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Car bill for office purpose against vehicle reg. no.WB55-B6555 period form July,22 to Jan,23. |  |  | BILL/00025/2024-2025 | BP-2024-25-30 | 26/04/2024 | 26/04/2024 | ANUP KUMAR SAHA | 2.77 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10223 | School | Car bill for office purpose against vehicle reg. no.WB55-B6555 period form July,22 to Jan,23. |  |  | BILL/00026/2024-2025 | BP-2024-25-28 | 26/04/2024 | 26/04/2024 | BOSE CONSTRUCTION | 1.73 | 0 | 0 | 0
Total | [13 empty] | 829.57 | 372.82 | 44.94