## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | FHTC Connetion for School Hura W/s Scheme. |  |  | VCH/000289/2022-2023 | null | 18/07/2022 |  | MS D.PALIT AND CO. | 225.03 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | Water supply Tap Connection Arrangement for 35 nos School upto 200 Students within Hura Block (Part-C) and 15 nos School upto 200 Students within Raghunathpur-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No. 23/2022-23 of SE/PMU/WBPWSP(P) ) |  |  | VCH/000997/2022-2023 | BP-2022-23-235 | 05/09/2022 |  | BALAJI UDDYOG | 77.99 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | Providing Functional Household Tap Connection (FHTC) at different AWC, School and other allied works of Raghunathpur Water Supply Scheme (Zone-VIII) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000013/2022-2023 | 170/RNP | 07/04/2022 | 07/05/2022 | KHITISH CHANDRA PATHAK | 1.88 | 1.81 | 96.33 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | ESTIMATE FOR WATER SUPPLY ARRANGEMENT OF CHITORMA JUNIOR HIGH SCHOOL, PABRA PRY SCHOOL & DAMANPUR PRY SCHOOL IN RAGHUNATHPUR-II BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 , UPTO 200 STUDENTS). SL NO.03 | Assistant Engineer |  | ORD/000169/2021-2022 | 27/PR | 31/01/2022 | 30/07/2022 | PRATIK SAHA | 3.16 | 2 | 63.34 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | Water supply Tap Connection Arrangement for 49 nos School upto 200 Students within Hura Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000090/2022-2023 | 678/PD | 25/04/2022 | 09/06/2022 | EQUIPMENTS AND SPARES AGENCIES | 206.57 | 197.33 | 95.53 | 100
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | Water supply Tap Connection Arrangement for 45 nos School upto 200 Students, 7 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Hura Block (Part-A) of Purulia District under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000018/2022-2023 | 567/PD | 08/04/2022 | 23/05/2022 | MS D.PALIT AND CO. | 227.54 | 227.45 | 99.96 | 100
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | Water supply Tap Connection Arrangement for 35 nos School upto 200 Students within Hura Block (Part-C) and 15 nos School upto 200 Students within Raghunathpur-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000095/2022-2023 | 699/PD | 28/04/2022 | 12/06/2022 | BALAJI UDDYOG | 210.78 | 90.15 | 42.77 | 100
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | FHTC Connetion for School Hura W/s Scheme. |  |  | VCH/001927/2022-2023 | null | 18/07/2022 |  | MS D.PALIT AND CO. | 225.03 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students, within Purulia-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000457/2021-2022 | 414/PD | 16/03/2022 | 30/04/2022 | ANUP KUMAR SAHA | 159.38 | 85.09 | 53.39 | 100
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10224 | School | Water supply Tap Connection Arrangement for 45 nos School upto 200 Students, 3 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Raghunathpur-II Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000094/2022-2023 | 700/PD | 28/04/2022 | 12/06/2022 | BALAJI UDDYOG | 211.01 | 173.36 | 82.15 | 100
Total | [13 empty] | 1548.37 | 777.19 | 50.19