## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 6 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within PARA BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000461/2021-2022 | 434/PD | 21/03/2022 | 05/05/2022 | PRINCE INDUSTRIES ( INDIA) | 232.18 | 232.17 | 100 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | School | Water supply Tap Connection Arrangement for 30 nos School upto 200 Students, within RAGHUNATHPUR-I Block (Part-B) and 10 nos School upto 200 Students, within PARA BLOCK (Part-C) of Purulia District under Purulia Division, PHE Dte. (Tender No.39/SE/PMU of 2021-22) |  |  | VCH/001031/2022-2023 | BP-2022-23-357 | 30/09/2022 | 30/09/2022 | ABHIJIT MUKHERJEE | 37.53 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | School | Water supply Tap Connection Arrangement for 30 nos School upto 200 Students, within RAGHUNATHPUR-I Block (Part-B) and 10 nos School upto 200 Students, within PARA BLOCK (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000479/2021-2022 | 454/PD | 23/03/2022 | 07/05/2022 | ABHIJIT MUKHERJEE | 168.37 | 89.82 | 53.34 | 100
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | School | Making Xerox copy of original DPR, Drawing, Mouza Map etc. |  |  | BILL/00248/2023-2024 | 27/2023-149 | 30/05/2023 | 30/05/2023 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Raghunathpur-I & Raghunathpur-II Blocks under Purulia Division ,PHE,Dte. | Assistant Engineer |  | ORD/001387/2023-2024 | 1740/PD | 04/12/2023 | 03/01/2024 | TUSHAR KANTI GORAI | 7.5 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | School | Water supply Tap Connection Arrangement for 45 nos School upto 200 Students, within PARA BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000478/2021-2022 | 453/PD | 23/03/2022 | 07/05/2022 | GOENKA ENTERPRISE | 189.42 | 138.21 | 72.97 | 100
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | School | Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Airconditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001715/2023-2024 | 430-A/PR | 01/08/2023 | 12/02/2024 | ANUP KUMAR SAHA | 0.96 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | School | Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Airconditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001713/2023-2024 | 430/PR | 01/08/2023 | 12/02/2024 | BOSE CONSTRUCTION | 0.96 | 0 | 0 | 95
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | SM/10225 | School | Continuation work order for Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Air conditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/004963/2023-2024 | 56/A/PR | 09/02/2024 | 22/08/2024 | ANUP KUMAR SAHA | 0.96 | 0 | 0 | 0
Total | [13 empty] | 638.24 | 460.2 | 72.1