## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. | SM/10226 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 4 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Arsha Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000088/2022-2023 | 672/PD | 25/04/2022 | 09/06/2022 | ANUP KUMAR SAHA | 218.38 | 217.39 | 99.55 | 0
2 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. | SM/10226 | School | Water supply Tap Connection Arrangement for 43 nos School upto 200 Students, within Bandwan Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000216/2022-2023 | 771/PD | 02/05/2022 | 01/08/2025 | PREMNATH MITRA | 181.33 | 153.1 | 84.43 | 100
3 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. | SM/10226 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Bandwan Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000463/2021-2022 | 436/PD | 21/03/2022 | 07/02/2025 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 227.94 | 161.78 | 70.98 | 100
4 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. | SM/10226 | School | Water supply Tap Connection Arrangement for 20 nos. AWC within Jhalda-I, Arsha & Bandwan Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001329/2022-2023 | 1050_PD | 08/07/2022 | 22/08/2022 | PRASENJIT BASAK | 157.97 | 70.38 | 44.55 | 100
5 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. | SM/10226 | School | FHTC Connetion for School Bundwan W/s Scheme. |  |  | VCH/000290/2022-2023 |  | 18/07/2022 | 18/07/2022 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 60 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. | SM/10226 | School | Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Airconditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-C) | Assistant Engineer |  | ORD/001720/2023-2024 | 430-B/PR | 01/08/2023 | 12/02/2024 | SUMIT KUMAR CHAKRABORTY | 0.96 | 0 | 0 | 0
Total | [13 empty] | 846.57 | 602.65 | 71.19