## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos School upto 200 Students within Kashipur Block (Part -B) and 5 nos School for 200 Students within Saturi Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000213/2022-2023 | 795/PD | 05/05/2022 | 19/06/2022 | SINGHA ENTERPRISE | 231.61 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Water supply Tap Connection Arrangement for Sourceless 4 nos School upto 200 Students , 1 nos School for 501-800 Students within PURULIA-I Block ,9 nos School upto 200 Students , 1 nos School for 201-500 Students, 3 nos School for 501-800 Students, , 1 nos School for above 800 Students within PURULIA-II Block, 3 nos School upto 200 Students within NETURIA Block,11 nos School upto 200 Students within KASHIPUR Block, 1 nos School upto 200 Students within RAGHUNTHPUR-I Block, 3 nos School upto 200 Students within RAGHUNTHPUR-II, 2 nos School for 501-800 Students within SANTURI of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000021/2022-2023 | 555/PD | 06/04/2022 | 21/05/2022 | JYOTY SOLAR POWER | 164.92 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos School upto 200 Students, 3 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Saturi Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000214/2022-2023 | 796/PD | 05/05/2022 | 19/06/2022 | PRINCE INDUSTRIES ( INDIA) | 232.09 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | WATER SUPPLY ARRANGEMENT OF KHARAI, PRY. SCHOOL, GHORCHOR PRY. SCHOOL & KOLLOLI PRY. SCHOOL IN KASHIPUR BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 UPTO 200 STUDENTS). (Tender No- 1025/21-22 of EE/PD) |  |  | VCH/001002/2022-2023 | BP-2022-23-243 | 05/09/2022 | 05/09/2022 | SUDHANSHU OJHA | 2.9 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Water supply tap connection arrangement for 4 nos school upto 200 students, 1 nos school for 501-800 students within Purulia-I block, 9 nos School upto 200 Students 1 nos school school for 201-500 students, 3nos school for 501-800 students, 1 nos school for above 800 students within PURULIA-II Block, 3 nos School upto 200 Students within NETURIA Block,11 nos School upto 200 Students within KASHIPUR Block, 1 nos School upto 200 Students within RAGHUNTHPUR-I Block, 3 nos School upto 200 Students within RAGHUNTHPUR-II, 2 nos School for 501-800 Students within SANTURI of Purulia District under Purulia Division, PHE Dte. (Tender No.01/SE/PMU of 2022-23) |  |  | VCH/001038/2022-2023 | BP-2022-23-374 | 19/10/2022 | 19/10/2022 | JYOTY SOLAR POWER | 16.72 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | ESTIMATE FOR WATER SUPPLY ARRANGEMENT OF KHARAI, PRY. SCHOOL, GHORCHOR PRY. SCHOOL & KOLLOLI PRY. SCHOOL IN KASHIPUR BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 UPTO 200 STUDENTS). SL NO.04 | Assistant Engineer |  | ORD/000092/2021-2022 | 28/PR | 31/01/2022 | 30/07/2022 | SUDHANSHU OJHA | 3.49 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | ESTIMATE FOR WATER SUPPLY ARRANGEMENT OF RAMJANGAL PR. SCHOOL,MASHILA PR. SCHOOL & MANPURA PR. SCHOOL IN KASHIPUR BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 UPTO 200 STUDENTS). SL NO.11 | Assistant Engineer |  | ORD/000097/2021-2022 | 35/PR | 31/01/2022 | 30/07/2022 | M/S KARUNAMOYEE CONSTRUCTION | 3.22 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Daily Operation & Mtc. of Rising Main & all Distribution System, sluice valve, street stand post etc. under Sutabai W/S Scheme under Raghnathpur Sub-Division, P.H.E. Dte. (w.e.f.01.09.2021 to 31.08.2022) | Assistant Engineer |  | ORD/000178/2021-2022 | 1082/PD | 31/08/2021 | 31/08/2022 | ASHOK KUMAR CHATTERJEE | 7.33 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos School upto 200 Students, 3 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Snturi BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. (Tender No.30/SE/PMU of 2022-23) |  |  | VCH/001009/2022-2023 | BP-2022-23-267 | 20/09/2022 | 20/09/2022 | PRINCE INDUSTRIES ( INDIA) | 232.09 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Water supply Tap Connection Arrangement for Sourceless 4 nos School upto 200 Students , 1 nos School for 501-800 Students within PURULIA-I Block ,9 nos School upto 200 Students , 1 nos School for 201-500 Students, 3 nos School for 501-800 Students, , 1 nos School for above 800 Students within PURULIA-II Block, 3 nos School upto 200 Students within NETURIA Block,11 nos School upto 200 Students within KASHIPUR Block, 1 nos School upto 200 Students within RAGHUNTHPUR-I Block, 3 nos School upto 200 Students within RAGHUNTHPUR-II, 2 nos School for 501-800 Students within SANTURI of Purulia District under Purulia Division, PHE Dte. (Tender No 01/2022-23 of SE/PMU) |  |  | VCH/001082/2022-2023 | BP-2022-23-223 | 29/08/2022 | 29/08/2022 | JYOTY SOLAR POWER | 146.67 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos School upto 200 Students within Kashipur Block (Part -B) and 5 nos School for 200 Students within Saturi Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No.) (Tender No.27/22-23 of SE/PMU) |  |  | VCH/001084/2022-2023 | BP-2022-23-228 | 29/08/2022 | 29/08/2022 | SINGHA ENTERPRISE | 231.61 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Water supply Tap Connection Arrangement for 36nos school for 201-500 students, 2 no. school for 501-800 students and 2no school avove 800 students within Kashipur Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000595/2022-2023 | 1219/PD | 17/08/2022 | 01/10/2022 | PRAVAT SARKAR | 202.09 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos school upto 200 students within Kashipur Block (Part - C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 1251/PD | 30/08/2022 | 14/10/2022 | PARTHA PRATIM CHHATAIT | 211.38 | 0 | 0 | 100
Total | [13 empty] | 1686.12 | 0 | 0