## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. | SM/10228 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students within Puncha Block (Part -C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000020/2022-2023 | 577/PD | 12/04/2022 | 27/05/2022 | B.K. ENTERPRI SE | 168.51 | 150.4 | 89.25 | 0
2 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. | SM/10228 | School | FHTC Connetion for School Puncha W/s Scheme. |  |  | VCH/000292/2022-2023 |  | 18/07/2022 | 18/07/2022 | B.K. ENTERPRI SE | 115 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. | SM/10228 | School | Water supply Tap Connection Arrangement for 23 nos School upto 200 Students within Joypur Block (Part -B) and 25 nos School upto 200 Students within Puncha Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000019/2022-2023 | 580/PD | 12/04/2022 | 27/05/2022 | B.K. ENTERPRI SE | 202.23 | 184.56 | 91.26 | 0
4 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. | SM/10228 | School | Water supply Tap Connection Arrangement for Sourceless 3 nos School upto 200 Students , 1 nos School for 201-500 Students within BALARAMPUR Block ,4 nos School upto 200 Students within BANDWAN Block, 8 nos School upto 200 Students,2 no School above 800 within BARABAZAR Block,16 nos School upto 200 Students within MANBAZAR-I Block, 2 nos School upto 200 Students within MANBAZAR-II Block, 1 nos School upto 200 Students, 2 nos School for 501-800 Students within PUNCHA Block , of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000087/2022-2023 | 671/PD | 25/04/2022 | 09/06/2022 | ANUP KUMAR SAHA | 163.9 | 163.9 | 100 | 0
5 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. | SM/10228 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 6 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Puncha Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000022/2022-2023 | 581/PD | 12/04/2022 | 27/05/2022 | M DHARA & BROTHERS | 231.81 | 226.68 | 97.79 | 100
6 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. | SM/10228 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 4 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Joypur Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000093/2022-2023 | 675/PD | 25/04/2022 | 09/06/2022 | EQUIPMENTS AND SPARES AGENCIES | 223.53 | 137.71 | 61.6 | 100
7 | PURULIA |  | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. | SM/10228 | School | Water supply Tap Connection Arrangement for 2 nos AWC within Joypur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000141/2022-2023 | 725/PD | 02/05/2022 | 16/06/2022 | HUSSAIN CONSTRUCTION | 15.68 | 7.37 | 47 | 100
Total | [13 empty] | 1120.67 | 870.61 | 77.69