## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10229 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, within Manbazar-I Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No.17/SE/PMU of 2022-23) |  |  | VCH/001029/2022-2023 | BP-2022-23-328 | 29/09/2022 | 29/09/2022 | EQUIPMENTS AND SPARES AGENCIES | 75.73 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10229 | School | Water supply Tap Connection Arrangement for 49 nos School upto 200 Students, 4 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Neturia Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000015/2022-2023 | 566/PD | 08/04/2022 | 23/05/2022 | MS D.PALIT AND CO. | 232.21 | 0 | 0 | 100
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10229 | School | Water supply Tap Connection Arrangement for 46 nos School upto 200 Students, 7 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Manbazar-I Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000551/2022-2023 | 676/PD | 25/04/2022 | 09/06/2022 | EQUIPMENTS AND SPARES AGENCIES | 232.07 | 0 | 0 | 100
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10229 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, within Manbazar-I Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000089/2022-2023 | 674/PD | 25/04/2022 | 09/06/2022 | EQUIPMENTS AND SPARES AGENCIES | 168.51 | 0 | 0 | 100
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10229 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Puncha&Manbazar-I Blocks under Purulia Division ,PHE,Dte. | Assistant Engineer | Junior Engineer | ORD/001383/2023-2024 | 1738/PD | 04/12/2023 | 03/01/2024 | ESSAR CONSTRUCTION | 12.6 | 0 | 0 | 70
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10229 | School | Water supply Tap Connection Arrangement for 30 nos School upto 200 Students, within Manbazar-I Block (Part-C) and 16 nos School upto 200 Students, within Neturia Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2022-2023 | 677/PD | 25/04/2022 | 09/06/2022 | BINGAS ELECTRICAL ELECTRONICS AND SOLAR SYSTEM | 193.98 | 0 | 0 | 100
Total | [13 empty] | 915.1 | 0 | 0