## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | Water supply Tap Connection Arrangement for 25 nos AWC within Barabazar Block (Part-Q) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000974/2022-2023 | 57/PD | 10/01/2023 | 24/02/2023 | ANUP KUMAR SAHA | 206.73 | 0 | 0 | 90
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | Water supply Tap Connection Arrangement for 20 nos School upto 200 Students, within JHALDA-II (Part-B) and 35 nos School upto 200 Students, within BARABAZAR BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000086/2022-2023 | 619/PD | 20/04/2022 | 04/06/2022 | S N POLYMERS PVT LTD | 231.75 | 0 | 0 | 100
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | supply Tap Connection Arrangement for 49 nos School upto 200 Students, 4 nos School for 201-500 Students and 1 no School for 501-800 Students within JHALDA-II BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000084/2022-2023 | 617/PD | 20/04/2022 | 04/06/2022 | S N POLYMERS PVT LTD | 227.71 | 0 | 0 | 100
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | Water supply Tap Connection Arrangement for 42 nos School upto 200 Students, 7 nos School for 201-500 Students and 1 no School for 501-800 Students within BARABAZAR BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000085/2022-2023 | 618/PD | 20/04/2022 | 04/06/2022 | S N POLYMERS PVT LTD | 210.94 | 0 | 0 | 100
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | Water supply arrangement of schools at bamusadhu ashram high school under barabazar block within purulia district. | Assistant Engineer | Junior Engineer | ORD/001207/2022-2023 | 492/PD | 31/03/2023 | 15/05/2023 | MRINAL KANTI GORAI | 1.5 | 0 | 0 | 70
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | Water supply Tap Connection Arrangement for 3 nos School upto 200 Students within Jhalda-II Block of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000088/2023-2024 | 837/PD | 26/06/2023 | 10/08/2023 | PRINCE INDUSTRIES ( INDIA) | 16.93 | 0 | 0 | 100
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | Water supply Tap Connection Arrangement for 42 nos School upto 200 Students, 7 nos School for 201-500 Students and 1 no School for 501-800 Students within BARABAZAR BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. (Tender No.12/SE/PMU of 2022-23) |  |  | VCH/001095/2022-2023 | BP-2022-23-198 | 16/08/2022 | 16/08/2022 | S N POLYMERS PVT LTD | 145.54 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, within BARABAZAR BLOCK (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000223/2022-2023 | 798/PD | 05/05/2022 | 19/06/2022 | SANTANU BANERJEE | 168.21 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewells sinked at various Schools & AWCs of . Barabazar & Purulia-I Blocks under Purulia Division ,PHE,Dte. | Assistant Engineer | Junior Engineer | ORD/001377/2023-2024 | 1734/PD | 04/12/2023 | 03/01/2024 | BANERJEE CONSTRUCTION | 14.87 | 0 | 0 | 100
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10230 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewells sinked at various Schools & AWCs of . Jhalda-I & Jhalda-II Blocks under Purulia Division ,PHE,Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer,Junior Engineer-3 | ORD/001373/2023-2024 | 1733/PD | 04/12/2023 | 03/01/2024 | AMIT CHOURASIA | 8.57 | 0 | 0 | 100
Total | [13 empty] | 1232.73 | 0 | 0