## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Chharrah G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000171/2022-2023 | 1129/BMD | 12/09/2022 | 27/09/2022 | ABHIJIT MUKHERJEE | 42.52 | 23.27 | 54.72 | 0
2 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Ghongha G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000172/2022-2023 | 1130/BMD | 12/09/2022 | 07/10/2022 | SUMIT KUMAR CHAKRABORTY | 70.88 | 44.22 | 62.39 | 0
3 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Hutmura & Raghabpur G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000173/2022-2023 | 1131/BMD | 12/09/2022 | 27/09/2022 | CHAKRABORTY MAINING & ENGINEERING. | 35.89 | 29.31 | 81.69 | 0
4 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Belma & Bhangra G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000170/2022-2023 | 1128/BMD | 12/09/2022 | 27/09/2022 | ABHIJIT MUKHERJEE | 42.52 | 29.49 | 69.35 | 0
5 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Aga yesa Narrah G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000176/2022-2023 | 1197/BMD | 22/09/2022 | 07/10/2022 | PREMNATH MITRA | 35.83 | 28.26 | 78.88 | 0
6 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method sourceless AWC at Purulia-II Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE Dte. in the District of Purulia |  |  | ORD/000060/2023-2024 | 529/PMD | 05/05/2023 | 04/06/2023 | NUPUR CHANDRA HALDER | 31.54 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Purulia-II Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000127/2022-2023 | 739/PD | 02/05/2022 | 16/06/2022 | INDRAJIT SARKAR | 13.6 | 13.59 | 99.95 | 100
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Purulia-II Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000140/2022-2023 | 740/PD | 02/05/2022 | 16/06/2022 | BHUTNATH MISHRA | 13.53 | 8.14 | 60.19 | 100
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Installation of Big-Dia D.T.H. Tube Well (200mm x 165mm) by Robotic DTH Rigs for drilling upto 1200 ft or small form factor trolly mounted rig with trolly mounted compressor suitable for narrow 68 inch wide roads considering 200mt Depth in diferent AWC of different Blocks (PHASE-1) of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000969/2022-2023 | 48/PD | 09/01/2023 | 23/02/2023 | S N POLYMERS PVT LTD | 96.17 | 96.17 | 100 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Purulia-II Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000959/2022-2023 | 37/PD | 09/01/2023 | 23/02/2023 | TAPAN CHANDRA | 6.4 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Purulia-II Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000152/2022-2023 | 766/PD | 02/05/2022 | 16/06/2022 | SOUHARDYA BUSINESS LINE | 40.73 | 37.34 | 91.68 | 100
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within PURULIA-II Block (Part-J,L,M,N,N,O) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000878/2022-2023 | 1869/PD | 13/12/2022 | 27/01/2023 | IKBAL CONSTRUCTION | 28.24 | 27.51 | 97.42 | 100
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Purulia-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000810/2022-2023 | 1702/PD | 22/11/2022 | 06/01/2023 | KOUSHIK CHATTERJEE | 91.59 | 65.78 | 71.82 | 100
14 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Golamara G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000177/2022-2023 | 1198/BMD | 22/09/2022 | 07/10/2022 | AMITAVA CHAKRABORTY | 35.4 | 34.52 | 97.51 | 100
15 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Pindra G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000178/2022-2023 | 1199/BMD | 22/09/2022 | 07/10/2022 | AMITAVA CHAKRABORTY | 32.22 | 28.79 | 89.36 | 90
16 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | SM/10249 | Anganwadi | Supply and Delivery of fuel(Diesel) and lubricants to Departmental Rig KLR and supporting vehicle WB 67 6943 in connection of Purulia JJM Program at BMSD(D) under PHE Dte. |  |  | BILL/00362/2024-2025 |  | 30/05/2024 | 30/05/2024 | LALJI RAJA & SONS AGENCIES | 1.69 | 0 | 0 | 0
Total | [13 empty] | 618.74 | 466.39 | 75.38