## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Nutundih GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000141/2022-2023 | 681/PMD | 28/09/2022 | 13/10/2022 | KHITISH CH. PATHAK | 25.33 | 0 | 0 | 0
2 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Borrah GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000138/2022-2023 | 679/PMD | 28/09/2022 | 13/10/2022 | NUPUR CHANDRA HALDER | 15.87 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Mangalda Moutore GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000140/2022-2023 | 680/PMD | 28/09/2022 | 13/10/2022 | KHITISH CH. PATHAK | 38 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Raghunathpur-II Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 19/2022-23 of EE/PD) |  |  | VCH/001072/2022-2023 | BP-2022-23-431 | 25/11/2022 | 25/11/2022 | JYOTY SOLAR POWER | 65.07 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | ESTIMATE FOR WATER SUPPLY ARRANGEMENT OF NARENDRAPUR PRY SCHOOL, CHANGURI PRY.NARIRA PRY IN RAGHUNATHPUR-II BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 , UPTO 200 STUDENTS). SL NO.09 | Assistant Engineer |  | ORD/000095/2021-2022 | 33/PR | 31/01/2022 | 30/07/2022 | ANUDIP SAHA | 3.18 | 2.02 | 63.34 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 19 nos AWC within Raghunathpur-II Block of Purulia District under Purulia Division, PHE Dte.(Phase-II) [Part-B(4 Nos.), Part-D & F] | Assistant Engineer | Junior Engineer | ORD/000270/2022-2023 | 822/PD | 17/05/2022 | 01/07/2022 | WRISHI ENTERPRISE | 86.06 | 28.31 | 32.89 | 35
7 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Joradih GP and Chelyama GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000159/2022-2023 | 709/PMD | 17/10/2022 | 16/11/2022 | ANUP KR. SAHA | 69.67 | 23.86 | 34.25 | 0
8 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Execution of the yield test at Serendi, Tunturi- Suisa GP in Bagmundi Block within the district of Purulia under code SM10250 under PMD, PHE, Dte. |  |  | ORD/000329/2022-2023 | 21/PMSD(Drilling) | 31/01/2023 | 15/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0.98 | 100 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Raghunathpur-II Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000488/2021-2022 | 499/PD | 29/03/2022 | 13/05/2022 | JYOTY SOLAR POWER | 71.04 | 0 | 0 | 0
10 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Nildih GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000144/2022-2023 | 682/PMD | 28/09/2022 | 13/10/2022 | RABINDRA NATH KHAN | 28.52 | 8.42 | 29.52 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 3 nos AWC within Raghunathpur-II Block (Part-E) of Purulia District under Purulia Division, PHE Dte." | Assistant Engineer |  | ORD/000807/2022-2023 | 1734/PD | 22/11/2022 | 06/01/2023 | MADHU SUDAN RAKSHIT | 14.08 | 13.59 | 96.51 | 0
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Mangalda Moutore GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.220/EE/PMD of 2022-23) |  |  | VCH/001671/2022-2023 | BP-2022-23-508 | 22/12/2022 | 22/12/2022 | KHITISH CHANDRA PATHAK | 6.56 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Neturia GP, Raghunathpur II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.226/EE/PMD of 2022-23) |  |  | VCH/001713/2022-2023 | BP-2022-23-472 | 16/12/2022 | 16/12/2022 | KHITISH CHANDRA PATHAK | 18.29 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Paradih GP and Chelyama GP, Raghunathpur II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.218/EE/PMD of 2022-23) |  |  | VCH/001718/2022-2023 | BP-2022-23-463 | 08/12/2022 | 08/12/2022 | ANUP KUMAR SAHA | 42.76 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Borrah GP, Raghunathpur-II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.222/EE/PMD of 2022-23) |  |  | VCH/001657/2022-2023 | BP-2022-23-528 | 09/01/2023 | 09/01/2023 | NUPUR CHANDRA HALDER | 11.59 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Nildih GP, Raghunathpur-II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.219/EE/PMD of 2022-23) |  |  | VCH/001729/2022-2023 | BP-2022-23-452 | 02/12/2022 | 02/12/2022 | RABINDRANATH KHAN | 17.88 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Mangalda Moutora GP, Raghunathpur II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.220/EE/PMD of 2022-23) |  |  | VCH/001715/2022-2023 | BP-2022-23-471 | 16/12/2022 | 16/12/2022 | KHITISH CHANDRA PATHAK | 28.45 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Raghunathpur-II Block of Purulia District under Purulia Division, PHE Dte.(Phase-I) [Part-A(12 Nos.) & Part-B(8 Nos.)] | Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 823/PD | 17/05/2022 | 01/07/2022 | NATIONAL CONSTRUCTION | 90.59 | 45.67 | 50.42 | 60
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within RAGHUNATHPUR-II Block (Part-C),12 nos Awc Within RAGHUNATHPUR block (Part-G) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000889/2022-2023 | 1871/PD | 13/12/2022 | 27/01/2023 | RABINDRANATH KHAN | 66.19 | 26.64 | 40.25 | 50
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 4 nos AWC within RAGHUNATHPUR-II Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000888/2022-2023 | 1870/PD | 13/12/2022 | 27/01/2023 | M/S ACHARJEE CONSTRUCTION | 32.75 | 15.29 | 46.68 | 50
21 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10250 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Raghunathpur-ll Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000276/2022-2023 | 70/PMD | 31/01/2023 | 20/02/2023 | GOENKA ENTERPRISE | 41.02 | 6.53 | 15.91 | 15
Total | [13 empty] | 773.89 | 171.31 | 22.14