## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Tarabari & R.C pur G.P of Santuri Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000165/2022-2023 | 1101/BMD | 05/09/2022 | 30/09/2022 | CHAKRABORTY MAINING & ENGINEERING. | 77.7 | 61.72 | 79.43 | 0
2 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Muradi & Balitora G.P of Santuri Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000164/2022-2023 | 1100/BMD | 05/09/2022 | 30/09/2022 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 77.89 | 74.26 | 95.34 | 0
3 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of Tyre for Different Rig Vehicle at B.M.S.D(D) in connection to JJM Programme. | Assistant Engineer |  | ORD/000185/2022-2023 | 442/BMSD(D) | 13/06/2022 | 03/07/2022 | RAJIB COMPANY | 2.32 | 2.32 | 100 | 0
4 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of 4 1/2 "(114 mm approx) x 10 ' long Drill Tube for Different Drilling Rig Machine of BMSD(D), Under BMD,PHE Dte. in connection to JJM programme. | Assistant Engineer |  | ORD/000186/2022-2023 | 274/BMSD(D) | 29/04/2022 | 14/05/2022 | CHAKRABORTY MAINING & ENGINEERING. | 4.86 | 4.86 | 100 | 0
5 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Providing man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit 7D at B.M.S.D(D) under B.M.D, P.H.E Dte . | Assistant Engineer |  | ORD/000192/2022-2023 | 436/BMSD(D) | 13/06/2022 | 29/09/2022 | PRADIP KUMAR DHABAL | 3.39 | 2.86 | 84.26 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Construction of Rig bored tube-well (200mmx165mm) by DTH method at Bara Urma GP at Balarampur Block under Purulia Mechanical Division PHE Dte. (Tender No.137/EE/PMD of 2022-23) |  |  | VCH/000454/2022-2023 | BP-2022-23-261 | 15/09/2022 | 15/09/2022 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 7.21 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students within Balarampur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No.26/SE/PMU of 2022-23) |  |  | VCH/001045/2022-2023 | BP-2022-23-389 | 19/10/2022 | 19/10/2022 | CARBON SERVICES INDIA | 2.51 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students within Balarampur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No.26/SE/PMU of 2022-23 [Ad - Interim Payment] ) |  |  | VCH/001025/2022-2023 | BP-2022-23-322 | 29/09/2022 | 29/09/2022 | CARBON SERVICES INDIA | 47.79 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Submission of bill in connection with work of sinking Tube well in AWC Santuri Block. |  |  | BILL/00074/2022-2023 |  | 16/12/2022 | 16/12/2022 | M/S SHANKAR AUTO SERVICE | 4.44 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students within Balarampur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000226/2022-2023 | 800/PD | 05/05/2022 | 19/06/2022 | CARBON SERVICES INDIA | 159.88 | 84.54 | 52.88 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Santuri Block (Part-D) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | Assistant Engineer |  | ORD/000564/2022-2023 | 1119/PD | 25/07/2022 | 08/09/2022 | MS CHANDI CHARAN ROY | 53.71 | 43.79 | 81.54 | 0
12 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method at Bara Urma GP, Balarampur Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000080/2022-2023 | 452/PMD | 04/07/2022 | 19/07/2022 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 38.16 | 0 | 0 | 0
13 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery and installation of Double vane hydraulic pump for repairing Rig vehicle 7D in connection to JJM Programme at B.M.S.D(D) under Bankura Mechanical Division PHE Dte | Driller-in-Charge |  | ORD/000217/2022-2023 | 935/BMSD(D) | 30/11/2022 | 10/12/2022 | CHAKRABORTY MINING & ENGINEERING. | 1.31 | 1.31 | 100 | 0
14 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling site in Darda GP of Balarampur Block and Saturi GP of Saturi Block of Purulia District in Connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | Driller-in-Charge |  | ORD/000215/2022-2023 | 933/BMSD(D) | 30/11/2022 | 10/12/2022 | UNITED TRADERS | 1.93 | 1.93 | 100 | 0
15 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling site in Balarampur and Saturi Block of Purulia District in Connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | Driller-in-Charge |  | ORD/000216/2022-2023 | 934/BMSD(D) | 30/11/2022 | 15/12/2022 | M/S SWAPAN BANERJEE | 2.89 | 2.89 | 100 | 0
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 55 nos AWC within Saturi Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000954/2022-2023 | 32/PD | 09/01/2023 | 23/02/2023 | SUMIT KUMAR CHAKRABORTY | 30.55 | 0 | 0 | 0
17 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Balarampur Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000279/2022-2023 | 72/PMD | 31/01/2023 | 02/03/2023 | KOUSHIK CHATTERJEE | 88.32 | 8.78 | 9.94 | 0
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 55 nos AWC within Balarampur & Addl. Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000951/2022-2023 | 28/PD | 09/01/2023 | 23/02/2023 | NATIONAL CONSTRUCTION | 30.54 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Fuel Bill in connection with work of sinking Tube Well in Purulia District related to JJM work |  |  | VCH/001685/2022-2023 | BP-2022-23-490 | 22/12/2022 | 22/12/2022 | M/S SHANKAR AUTO SERVICE | 4.44 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Boro Urma GP is Balarampur block under Purulia Mechanical Division PHE Dte. (T/N 137/EE/PMD of 2022-23) |  |  | VCH/000418/2022-2023 | BP-2022-23-218 | 24/08/2022 | 24/08/2022 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 30.91 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Balarampur Block (Part-B) & 8 nos AWC within Balarampur Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000568/2022-2023 | 1123/PD | 25/07/2022 | 08/09/2022 | NATIONAL CONSTRUCTION | 90.59 | 0 | 0 | 70
22 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within SANTURI Block (Part-C) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000890/2022-2023 | 1872/PD | 13/12/2022 | 27/01/2023 | THE BUSINESS ENGINEERS INDIA | 56.73 | 51.64 | 91.03 | 100
23 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Santuri Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Without Tubewell) (SL - 1) | Assistant Engineer | Junior Engineer | ORD/001038/2022-2023 | 144/PD | 03/02/2023 | 20/03/2023 | BILTU DAS | 117.72 | 68.44 | 58.14 | 100
24 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Providing hired driver and skilled operator for construction of R.B.T.W in connection to JJM by Rig unit KLR at B.M.S.D(D) under Bankura Mechanical Division PHE Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000340/2022-2023 | 966/BMSD(D) | 09/12/2022 | 28/12/2022 | CHAKRABORTY MINING & ENGINEERING. | 0.91 | 0 | 0 | 100
25 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Santuri & Neturia Blocks under Purulia Division ,PHE,Dte. | Assistant Engineer |  | ORD/001365/2023-2024 | 1739/PD | 04/12/2023 | 03/01/2024 | SUMIT KUMAR MITRA | 9.38 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Balarampur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000480/2021-2022 | 491/PD | 29/03/2022 | 13/05/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 70.7 | 47.01 | 66.5 | 75
27 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Santuri Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000565/2022-2023 | 1120/PD | 25/07/2022 | 20/04/2025 | MOLLA ENTERPRISE | 54.41 | 44.58 | 81.93 | 100
28 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Santuri Block (Part-A) & 2 Nos. AWC within Santuri Block (Part-F) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000603/2022-2023 | 1227/PD | 22/08/2022 | 02/11/2023 | MD AAMIR KHAN | 63.5 | 0 | 0 | 70
Total | [13 empty] | 1134.68 | 500.93 | 44.15