## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000024/2022-2023 | 595/PD | 19/04/2022 | 03/06/2022 | MEGA SOLAR ENERGY | 47.31 | 27.71 | 58.56 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Acceptance cum Work Order for, ¿Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-I Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-I)" | Assistant Engineer | JUNIOR ENGINEER | ORD/000827/2022-2023 | 1716/PD | 22/11/2022 | 06/01/2023 | DIGITEK | 91.23 | 75.78 | 83.07 | 91
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 9 nos AWC within Manbazar-I Block (Part-N) of Purulia District under Purulia Division, PHE Dte.(Phase-IV)" | Assistant Engineer | JUNIOR ENGINEER | ORD/000819/2022-2023 | 1719/PD | 22/11/2022 | 06/01/2023 | NANIGOPAL DEY | 75.02 | 41.62 | 55.48 | 95
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-I Block (Part-O) & 1 no AWC within Manbazar-I Block (Part-P) of Purulia District under Purulia Division, PHE Dte.(Phase-V)" | Assistant Engineer | JUNIOR ENGINEER | ORD/000820/2022-2023 | 1720/PD | 22/11/2022 | 06/01/2023 | MANATOSH SINGH | 58.28 | 21.24 | 36.45 | 40
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Acceptance cum Work Order for, ¿Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-I Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II)" | Assistant Engineer |  | ORD/000828/2022-2023 | 1717/PD | 22/11/2022 | 06/01/2023 | BILTU DAS | 91.09 | 64.68 | 71.01 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Manbazar-I Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000534/2022-2023 | 1047/PD | 08/07/2022 | 22/08/2022 | AMITAVA CHAKRABORTY | 157.91 | 96.25 | 60.95 | 61
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Manbazar-I Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000638/2022-2023 | 1249/PD | 30/08/2022 | 14/10/2022 | M DHARA & BROTHERS | 197.78 | 151.58 | 76.64 | 90
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Manbazar-I Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000028/2022-2023 | 599/PD | 19/04/2022 | 03/06/2022 | GOUTAM CHAKRABORTY | 15.78 | 14.1 | 89.36 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-I Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III)" | Assistant Engineer | JUNIOR ENGINEER | ORD/000818/2022-2023 | 1718/PD | 22/11/2022 | 06/01/2023 | SINGHA ENTERPRISE | 91.63 | 78.18 | 85.32 | 100
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within MANBAZAR-1 Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000883/2022-2023 | 1861/PD | 13/12/2022 | 27/01/2023 | NANIGOPAL DEY | 99.13 | 83.22 | 83.95 | 86
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Manbazar-I Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000026/2022-2023 | 597/PD | 19/04/2022 | 03/06/2022 | RAJAT KARMAKAR | 23.66 | 17.22 | 72.78 | 0
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Manbazar-I Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000025/2022-2023 | 596/PD | 19/04/2022 | 03/06/2022 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 23.64 | 17.96 | 75.98 | 60
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Manbazar-I Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000029/2022-2023 | 600/PD | 19/04/2022 | 03/06/2022 | DEBSHANKAR LAYEK | 7.82 | 6.03 | 77.12 | 0
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000023/2022-2023 | 594/PD | 19/04/2022 | 03/06/2022 | THE BUSINESS ENGINEERS INDIA | 47.2 | 4.24 | 8.99 | 0
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. (Tender No- 706/2022-23 of EE/PD) |  |  | VCH/001073/2022-2023 | BP-2022-23-434 | 25/11/2022 | 25/11/2022 | THE BUSINESS ENGINEERS INDIA | 36.92 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 29 nos AWC within Manbazar-I Block of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000975/2022-2023 | 80/PD | 17/01/2023 | 03/03/2023 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 16.11 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | SM/10252 | Anganwadi | Making Xerox copy of original DPR, Drawing, Mouza Map etc. |  |  | BILL/00248/2023-2024 | 27/2023-149 | 30/05/2023 | 30/05/2023 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
Total | [13 empty] | 1080.88 | 699.82 | 64.75