## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Barabazar Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000470/2021-2022 | 468/PD | 24/03/2022 | 08/05/2022 | MANATOSH SINGH | 23.56 | 14.17 | 60.15 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Barabazar Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000964/2022-2023 | 44/PD | 09/01/2023 | 23/02/2023 | THE BUSINESS ENGINEERS INDIA | 6.11 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Barabazar Block (Part-Q) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000974/2022-2023 | 57/PD | 10/01/2023 | 24/02/2023 | ANUP KUMAR SAHA | 206.73 | 152.06 | 73.56 | 90
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Barabazar Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000468/2021-2022 | 470/PD | 24/03/2022 | 08/05/2022 | PRAVAT SARKAR | 46.61 | 45.39 | 97.39 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Barabazar Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2021-2022 | 469/PD | 24/03/2022 | 08/05/2022 | KOUSHIK CHATTERJEE | 23.43 | 0 | 0 | 60
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Barabazar Block (Part-N) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000474/2021-2022 | 464/PD | 24/03/2022 | 08/05/2022 | SAIBAL SARKAR | 7.87 | 3.22 | 40.91 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Barabazar Block (Part-P) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000475/2021-2022 | 463/PD | 24/03/2022 | 08/05/2022 | ROY CONSTRUCTION | 7.66 | 7.04 | 91.86 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Barabazar Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000466/2021-2022 | 472/PD | 24/03/2022 | 08/05/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 47.13 | 44.63 | 94.69 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Barabazar Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000467/2021-2022 | 471/PD | 24/03/2022 | 08/05/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 47.14 | 30.51 | 64.72 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Barabazar Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000472/2021-2022 | 466/PD | 24/03/2022 | 08/05/2022 | PRAVAT SARKAR | 15.54 | 15.08 | 97.06 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Barabazar Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000471/2021-2022 | 467/PD | 24/03/2022 | 08/05/2022 | M/S ACHARJEE CONSTRUCTION | 15.77 | 14.67 | 93.03 | 100
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Barabazar Block (Part-F)of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000877/2022-2023 | 1855/PD | 13/12/2022 | 27/01/2023 | SANTANU BANERJEE | 74.42 | 27.48 | 36.93 | 100
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Barabazar Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | Assistant Engineer |  | ORD/000814/2022-2023 | 1707/PD | 22/11/2022 | 06/01/2023 | JYOTY SOLAR POWER | 91.77 | 75.24 | 81.99 | 0
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Barabazar Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 1708/PD | 22/11/2022 | 06/01/2023 | ABHIJIT MUKHERJEE | 91.69 | 65.37 | 71.29 | 100
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Barabazar Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 982/PD | 22/06/2022 | 06/08/2022 | ABHIJIT MUKHERJEE | 158.27 | 105.84 | 66.87 | 100
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Barabazar Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 37/2022-23 of EE/PD) |  |  | VCH/001085/2022-2023 | BP-2022-23-230 | 29/08/2022 | 29/08/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 12.95 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Withdrawing and relaying of DI pipes and Construction of shed for mobile laboratory vehicle & office vehicle at RWS Purulia sub Division office campus in connection with JJM under Purulia Division , PHE Dte. | Assistant Engineer |  | ORD/001487/2023-2024 | 1799/PD | 08/12/2023 | 06/02/2024 | KOUSHIK CHATTERJEE | 5 | 0 | 0 | 83
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Barabazar Block (Part-R) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000589/2022-2023 | 1156/PD | 01/08/2022 | 15/09/2022 | MANASH GHOSH | 197.96 | 154.81 | 78.2 | 100
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Barabazar Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2022-2023 | 1154/PD | 01/08/2022 | 15/09/2022 | GOENKA ENTERPRISE | 158.27 | 48.56 | 30.68 | 100
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 1 nos AWC within Barabazar Block (Part-S), of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000801/2022-2023 | 1728/PD | 22/11/2022 | 06/01/2023 | PRATIK SAHA | 8.27 | 0 | 0 | 100
21 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Barabazar Block (Part-O) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000473/2021-2022 | 465/PD | 24/03/2022 | 08/05/2022 | S PATHAK AND CO | 7.81 | 7.48 | 95.77 | 0
Total | [13 empty] | 1253.95 | 811.55 | 64.72