## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Execution of Electrical resistivity survey for searching ground water availability by experienced qualified geologist or applied geophysistat Anara, Bhowridih, Dubra, Bahara, Gram panchayats in PARA block and other areas for RBTW source creation in AWC withinPurulia district under PMD, PHE, Dte. |  |  | ORD/000103/2022-2023 | 217/PMSD (Drilling) | 05/08/2022 | 08/08/2022 | NUPUR CHANDRA HALDER | 4.93 | 0 | 0 | 0
2 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Para GP and Anara GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000160/2022-2023 | 710/PMD | 17/10/2022 | 16/11/2022 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 69.68 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Dubra GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000162/2022-2023 | 712/PMD | 17/10/2022 | 16/11/2022 | TAPAN KUMAR DEY | 66.5 | 0 | 0 | 0
4 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Jabara Jhapra-I GP and Jabara Jhapra -II GP Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000174/2022-2023 | 724/PMD | 19/10/2022 | 18/11/2022 | SANTANU BANERJEE | 72.8 | 0 | 0 | 0
5 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Udayespur GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000163/2022-2023 | 713/PMD | 17/10/2022 | 11/11/2022 | JYOTY SOLAR POWER | 44.32 | 0 | 0 | 0
6 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Bhowridih GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000161/2022-2023 | 711/PMD | 17/10/2022 | 11/11/2022 | PRINCE INDUSTRIES (INDIA) | 50.71 | 46.8 | 92.29 | 0
7 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200 X 165) mm by DTH method in different source less AWC at Deoli GP, Para Block under Purulia Mechanical Division, P.H.E Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000181/2022-2023 | 751/PMD | 07/11/2022 | 14/11/2022 | M/S KARUNAMOYEE CONSTRUCTION | 3.17 | 3.12 | 98.23 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Udayespur GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.230/EE/PMD of 2022-23) |  |  | VCH/001659/2022-2023 | BP-2022-23-530 | 09/01/2023 |  | JYOTY SOLAR POWER | 22.58 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Dubra GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.232/EE/PMD of 2022-23) |  |  | VCH/001654/2022-2023 | BP-2022-23-516 | 02/01/2023 |  | TAPAN KR. DEY | 49.6 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Execution of Electrical resistivity survey for searching ground water availability by experienced qualified geologist or applied geophysistat Anara, Bhowridih, Dubra, Bahara, Gram panchayats in PARA block and other areas for RBTW source creation in AWC withinPurulia district under PMD, PHE, Dte. (Tender No.202/EE/PMD of 2022-23) |  |  | VCH/001726/2022-2023 | BP-2022-23-457 | 02/12/2022 |  | NUPUR CHANDRA HALDER | 4.93 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Jabara Jhapra-I GP and Jabara Jhapra -II GP Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.231/EE/PMD of 2022-23) |  |  | VCH/001675/2022-2023 | BP-2022-23-507 | 22/12/2022 |  | SANTANU BANERJEE | 10.19 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Para GP and Anara GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.233/EE/PMD of 2022-23) |  |  | VCH/001710/2022-2023 | BP-2022-23-473 | 16/12/2022 |  | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 68.79 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Jabara Jhapra-I GP and Jabara Jhapra -II GP Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.231/EE/PMD of 2022-23) |  |  | VCH/001672/2022-2023 | BP-2022-23-505 | 22/12/2022 |  | SANTANU BANERJEE | 49.96 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 37 nos AWC within PARA Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000956/2022-2023 | 34/PD | 09/01/2023 | 23/02/2023 | SUBHAS CHANDRA MAHATO | 20.47 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Para Block (Part-M), 2 nos AWC within Para Block (Part-N) & 6 nos AWC within Para Block (Part-O) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000798/2022-2023 | 1725/PD | 22/11/2022 | 06/01/2023 | M/S KARUNAMOYEE CONSTRUCTION | 82.6 | 79.66 | 96.44 | 0
16 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Washing and developing of tube well for AWC programme at Para and other block under PMD, PHE, Dte.(2nd call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000028/2023-2024 | 415/PMD | 12/04/2023 | 27/04/2023 | SUMIT KR. CHAKRABORTY | 4.92 | 4.29 | 87.27 | 100
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 5 nos AWC within Para Block (Part-J), 3 nos AWC within Para Block (Part-K) & 3 nos AWC within Para Block (Part-L) of Purulia District under Purulia Division, PHE Dte. (Phase-I) | Assistant Engineer |  | ORD/000809/2022-2023 | 1701/PD | 22/11/2022 | 06/01/2023 | MS D.PALIT AND CO. | 91.69 | 49.94 | 54.47 | 0
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Para Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Without Tubewell) | Assistant Engineer | Junior Engineer | ORD/000597/2022-2023 | 1152/PD | 01/08/2022 | 15/09/2022 | PRADIP KUMAR DHABAL | 113.31 | 50.81 | 44.84 | 80
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Para Block of Purulia District under Purulia Division, PHE Dte.(Phase-III) (Part-A, C & P) | Assistant Engineer | Junior Engineer | ORD/000278/2022-2023 | 820/PD | 17/05/2022 | 01/07/2022 | JYOTY SOLAR POWER | 90.72 | 51.92 | 57.23 | 100
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within PARA Block (Part-D)& 5 nos Awc Within PARA block (Part-C-II) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000904/2022-2023 | 1866/PD | 13/12/2022 | 27/01/2023 | S.S CONSTRUCTION | 80.37 | 31.72 | 39.46 | 100
21 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Para Block (Part-F) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000887/2022-2023 | 1867/PD | 13/12/2022 | 27/01/2023 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 94.41 | 17.23 | 18.25 | 50
22 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 21 nos AWC within Para Block of Purulia District under Purulia Division, PHE Dte. (Phase-V) (Part-G, H and I) | Assistant Engineer | Junior Engineer | ORD/000265/2022-2023 | 824/PD | 17/05/2022 | 01/07/2022 | M DHARA & BROTHERS | 95.18 | 25.65 | 26.96 | 60
23 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Para Block of Purulia District under Purulia Division, PHE Dte.(Phase-I) (Part-E) | Assistant Engineer | Junior Engineer | ORD/000271/2022-2023 | 821/PD | 17/05/2022 | 01/07/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 90.51 | 42.34 | 46.78 | 80
Total | [13 empty] | 1282.32 | 403.47 | 31.46