## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply tap connection arrangement for 6 nos. AWC within Joypur block (Part-E) of Purulia District under Purulia Division, PHE Dte. (Tender No- 39/2022-23 of EE/PD) |  |  | VCH/001000/2022-2023 | BP-2022-23-237 | 05/09/2022 | 05/09/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 12.85 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. . (Tender No- 88/2022-23 of EE/PD) |  |  | VCH/001054/2022-2023 | BP-2022-23-402 | 21/10/2022 | 21/10/2022 | PARAMESWAR CHOWDHURY | 15.18 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Joypur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. (Tender No- 311/2022-23 of EE/PD) |  |  | VCH/001063/2022-2023 | BP-2022-23-414 | 28/10/2022 | 28/10/2022 | SUMIT KUMAR CHAKRABORTY | 7.57 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Joypur Block (Part-N) of Purulia District under Purulia Division, PHE Dte.(Phase-I) (Tender no- 655/2022-23 of EE/PD) |  |  | VCH/001070/2022-2023 | BP-2022-23-433 | 25/11/2022 | 25/11/2022 | SANTANU BANERJEE | 32.57 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Joypur Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000118/2022-2023 | 721/PD | 02/05/2022 | 16/06/2022 | RAKSHIT ENTERPRISE | 7.86 | 3.37 | 42.93 | 100
6 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Construction of Rigbored Tubewell (200mm X 165mm) by DTH method in different source less AWC at BAHARA GP and NADIHA GP, PARA Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000182/2022-2023 | 753/PMD | 07/11/2022 | 02/12/2022 | PREMNATH MITRA | 63.46 | 35.01 | 55.16 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 19 nos AWC within (Joypur Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000971/2022-2023 | 39/PD | 09/01/2023 | 23/02/2023 | SK ABBAS | 10.55 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000454/2021-2022 | 416/PD | 16/03/2022 | 30/04/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 47.13 | 34.28 | 72.73 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Joypur Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000120/2022-2023 | 722/PD | 02/05/2022 | 16/06/2022 | PRATIK SAHA | 7.85 | 7.7 | 98.03 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000114/2022-2023 | 728/PD | 02/05/2022 | 16/06/2022 | MUNNA AGROTECH ENTERPRISE | 47.35 | 45.5 | 96.1 | 100
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000116/2022-2023 | 726/PD | 02/05/2022 | 16/06/2022 | WRISHI ENTERPRISE | 23.6 | 21.03 | 89.13 | 0
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Joypur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000117/2022-2023 | 724/PD | 02/05/2022 | 16/06/2022 | SUMIT CHAKRABORTY | 15.71 | 4.31 | 27.43 | 100
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Joypur Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000119/2022-2023 | 723/PD | 02/05/2022 | 16/06/2022 | GOPAL ACHARJEE | 7.88 | 7.46 | 94.65 | 0
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Joypur Block (Part-N) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | Assistant Engineer |  | ORD/000604/2022-2023 | 1229/PD | 22/08/2022 | 06/10/2022 | SANTANU BANERJEE | 94.93 | 53.18 | 56.02 | 0
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Joypur Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | Assistant Engineer |  | ORD/000578/2022-2023 | 1033/PD | 25/07/2022 | 08/09/2022 | MEGA SOLAR ENERGY | 94.93 | 80.32 | 84.62 | 0
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 3 nos AWC within Joypur Block (Part-O), 1 nos AWC within Joypur Block (Part-P) of Purulia District under Purulia Division, PHE Dte." | Assistant Engineer |  | ORD/000802/2022-2023 | 1729/PD | 22/11/2022 | 06/01/2023 | SOUMITRA CHAKRABORTY | 33.06 | 33 | 99.8 | 100
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Joypur Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000115/2022-2023 | 727/PD | 02/05/2022 | 16/06/2022 | NATIONAL CONSTRUCTION | 23.6 | 22 | 93.22 | 0
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Joypur Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000511/2022-2023 | 983/PD | 22/06/2022 | 06/08/2022 | MEGA SOLAR ENERGY | 158.22 | 133.66 | 84.48 | 0
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Refreshment bill paid for office meeting. |  |  | BILL/00604/2023-2024 | BP-2023-24-368 | 10/08/2023 | 10/08/2023 | MATHUR DUTTA | 0.12 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Bill of the IEC programes done in 10 blocks during ARANYA SAPTAHA. |  |  | BILL/00676/2023-2024 | BP-2023-24-414 | 25/08/2023 | 25/08/2023 | M/S SAYAK BHATTACHARYA | 0.97 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Bill paid for submission of TDS certificate 24Q for the A.Y:2023-2024. |  |  | BILL/00618/2023-2024 | BP-2023-24-371 | 10/08/2023 | 10/08/2023 | NIGAM CONSULTANCY SERVICE | 0.35 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Joypur & Balarampur blocks under Purulia Division ,PHE,Dte. | Assistant Engineer | Junior Engineer | ORD/001363/2023-2024 | 1732/PD | 04/12/2023 | 03/01/2024 | VIVEKANANDA CONSTRUCTION | 12.4 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Joypur Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000536/2022-2023 | 1052/PD | 08/07/2022 | 22/08/2022 | SINGHA ENTERPRISE | 158.13 | 150.13 | 94.94 | 100
24 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000453/2021-2022 | 415/PD | 16/03/2022 | 30/04/2022 | PARAMESWAR CHOWDHURY | 46.89 | 16.45 | 35.09 | 100
Total | [13 empty] | 923.16 | 647.4 | 70.13