## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10256 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, 4 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within BAGMUNDI BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000083/2022-2023 | 620/PD | 20/04/2022 | 04/06/2022 | S N POLYMERS PVT LTD | 194.08 | 193.84 | 99.87 | 100
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10256 | School | Water supply Tap Connection Arrangement for 32 nos School upto 200 Students, within BAGMUNDI BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000408/2022-2023 | 939/PD | 16/06/2022 | 31/07/2022 | SUMIT KUMAR CHAKRABORTY | 134.63 | 58.26 | 43.27 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10256 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, within JHALDA-I BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000221/2022-2023 | 703/PD | 29/04/2022 | 13/06/2022 | WRISHI ENTERPRISE | 168.1 | 155.65 | 92.59 | 100
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10256 | School | Water supply Tap Connection Arrangement for Sourceless 4 nos School upto 200 Students within ARSHA Block ,16 nos School upto 200 Students, 1 nos School for 201-500 Students within BAGHMUNDI Block, 10 nos School upto 200 Students within JHALDA-I Block,1 nos School upto 200 Students,1 no School above 800 Students within JHALDA-II Block, 8 nos School upto 200 Students within JOYPUR Block , of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000224/2022-2023 | 704/PD | 29/04/2022 | 13/06/2022 | NATIONAL CONSTRUCTION | 172.42 | 135.7 | 78.7 | 100
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10256 | School | Water supply Tap Connection Arrangement for Sourceless 4 nos School upto 200 Students within ARSHA Block ,16 nos School upto 200 Students, 1 nos School for 201-500 Students within BAGHMUNDI Block, 10 nos School upto 200 Students within JHALDA-I Block,1 nos School upto 200 Students,1 no School above 800 Students within JHALDA-II Block, 8 nos School upto 200 Students within JOYPUR Block , of Purulia District under Purulia Division, PHE Dte. (Tender No- 24/2022-23 of SE/PMU/WBPWSP(P) ) |  |  | VCH/001066/2022-2023 | BP-2022-23-412 | 28/10/2022 | 28/10/2022 | NATIONAL CONSTRUCTION | 32.91 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10256 | School | Water supply Tap Connection Arrangement for 32 nos School upto 200 Students, within BAGMUNDI BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No- 41/2022-23 of SE/PMU) |  |  | VCH/001098/2022-2023 | BP-2022-23-166 | 05/08/2022 | 05/08/2022 | SUMIT KUMAR CHAKRABORTY | 76.04 | 0 | 0 | 0
Total | [13 empty] | 778.19 | 543.45 | 69.84