## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Raghunathpur-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No.222/EE/PD of 2022-23) |  |  | VCH/000466/2022-2023 | BP-2022-23-278 | 22/09/2022 | 22/09/2022 | M/S ACHARJEE CONSTRUCTION | 12.86 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Raghunathpur-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000124/2022-2023 | 736/PD | 02/05/2022 | 16/06/2022 | M/S ACHARJEE CONSTRUCTION | 47.43 | 12.25 | 25.84 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Raghunathpur-I Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000125/2022-2023 | 737/PD | 02/05/2022 | 16/06/2022 | NANIGOPAL DEY | 23.44 | 14.55 | 62.06 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Raghunathpur-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000123/2022-2023 | 735/PD | 02/05/2022 | 16/06/2022 | KHITISH CHANDRA PATHAK | 47.09 | 44.48 | 94.44 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Raghunathpur-I Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000126/2022-2023 | 738/PD | 02/05/2022 | 16/06/2022 | SUBHAS CHANDRA MAHATO | 8.29 | 7.31 | 88.17 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Raghunathpur-I Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000537/2022-2023 | 1048/PD | 08/07/2022 | 22/08/2022 | PRINCE INDUSTRIES ( INDIA) | 197.94 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Installation of Big-Dia D.T.H. Tube Well (200mm x 165mm) by Robotic DTH Rigs for drilling upto 1200 ft or small form factor trolly mounted rig with trolly mounted compressor suitable for narrow 68 inch wide roads considering 200mt Depth in diferent AWC of different Blocks (PHASE-2) of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000970/2022-2023 | 49/PD | 09/01/2023 | 23/02/2023 | ANUP KUMAR SAHA | 96.1 | 96.08 | 99.98 | 100
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Making Xerox copy of original DPR, Drawing, Mouza Map etc. |  |  | BILL/00248/2023-2024 | 27/2023-149 | 30/05/2023 | 30/05/2023 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. |  |  | BILL/00538/2023-2024 | BP-2023-24-335 | 02/08/2023 | 02/08/2023 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply tap connection arrangement for 25 nos AWC within Raghunathpur-I Block (Part-C) of Purulia District under Purulia Division PHE Dte. (Tender No.50/SE/PMU of 2022-23) |  |  | VCH/001734/2022-2023 | BP-2022-23-447 | 02/12/2022 | 02/12/2022 | PRINCE INDUSTRIES ( INDIA) | 197.74 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Raghunathpur-I Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000122/2022-2023 | 734/PD | 02/05/2022 | 16/06/2022 | BASANTA KUMAR SINGHADEO | 70.85 | 40.11 | 56.61 | 55
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 9nos AWC within Raghunathpur-I Block (Part-E), 2nos AWC within Raghunathpur-I Block (Part-J) & 2nos AWC within Raghunathpur-I Block (Part-K) of Purulia District under Purulia Division, PHE Dte. (Phase-III) (SL-10) | Assistant Engineer | Junior Engineer | ORD/001037/2022-2023 | 211/PD | 13/02/2023 | 30/03/2023 | PRAVAT SARKAR | 107.27 | 94.77 | 88.34 | 100
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 12nos AWC within Raghunathpur-I Block (Part-A) & 6 nos AWC within Raghunathpur-I Block (Part-D-I ) of Purulia District under Purulia Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001024/2022-2023 | 147/PD | 03/02/2023 | 20/03/2023 | SANTANU BANERJEE | 148.82 | 122.23 | 82.14 | 100
Total | [13 empty] | 958.89 | 431.78 | 45.03