## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Manguria Lalpur GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000155/2022-2023 | 705/PMD | 17/10/2022 | 24/10/2022 | SAIBAL SARKAR | 6.33 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Keshargarh GP is Hura block under Purulia Mechanical Division PHE Dte. (T/N 138/EE/PMD of 2022-23) |  |  | VCH/000417/2022-2023 |  | 13/08/2022 | 13/08/2022 | MS D.PALIT AND CO. | 38.15 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rig bored tube-well (200mmx165mm) by DTH method at Ludhurka GP at Hura Block under Purulia Mechanical Division PHE Dte. (Tender No.142/EE/PMD of 2022-23) |  |  | VCH/000453/2022-2023 | BP-2022-23-260 | 15/09/2022 | 15/09/2022 | RABINDRANATH KHAN | 10.46 | 0 | 0 | 0
4 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method at Keshargarh GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000081/2022-2023 | 453/PMD | 04/07/2022 | 19/07/2022 | M/S D. PALIT & CO. | 38.15 | 0 | 0 | 0
5 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method at Ladhurka GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia |  |  | ORD/000083/2022-2023 | 455/PMD | 04/07/2022 | 11/07/2022 | RABINDRA NATH KHAN | 12.72 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Hura Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000952/2022-2023 | 29/PD | 09/01/2023 | 23/02/2023 | CHANDAN CHATTERJEE | 6.66 | 0 | 0 | 0
7 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Execution of the yield test at Jabrrah, Manguria - Lalpur , Lakhanpur , Daldali GP in Hura Block within the district of Purulia under code SM10275 under PMD, PHE, Dte. |  |  | ORD/000328/2022-2023 | 20/PMSD(Drilling) | 31/01/2023 | 15/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0.98 | 100 | 0
8 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Execution of the yield test at different GP in Hura Block within the district of Purulia under code SM10275 under PMD, PHE, Dte. |  |  | ORD/000326/2022-2023 | 25/PMSD(Drilling) | 01/02/2023 | 16/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0.98 | 100 | 0
9 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Hura Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000274/2022-2023 | 69/PMD | 31/01/2023 | 20/02/2023 | KHITISH CH. PATHAK | 50.46 | 34.81 | 68.97 | 0
10 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Washing and developing of tube well for AWC programme at Hura and other block under PMD, PHE, Dte.(2nd call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000029/2023-2024 | 416/PMD | 12/04/2023 | 27/04/2023 | SUMIT KR. CHAKRABORTY | 3.58 | 0 | 0 | 0
11 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Supply & Delivery of 12 Volt Battery for Truck engine,supporting vehicle & 18D/AR Rig unit under Purulia Mechanical Division ,PHE Dte. |  |  | ORD/000004/2022-2023 | 108/PMSD(DRILLING) | 21/04/2022 | 28/04/2022 | M/S UJJAL DIESEL SERVICE | 0.65 | 0.65 | 100 | 0
12 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Repairing, general maintenance and all other allied works of rig mounted Truck AUT 5202 under PMD, PHE Dte. |  |  | ORD/000134/2021-2022 | 55/PMSD (Drilling) | 16/03/2022 | 31/03/2022 | M/S UJJAL DIESEL SERVICE | 1.88 | 1.88 | 100 | 0
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 9 no AWC within Hura Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2022-2023 | 763/PD | 02/05/2022 | 16/06/2022 | BISWESWAR CONSTRUCTION | 40.63 | 28.15 | 69.3 | 100
14 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Execution of Yield Test of R.B.T. Well at different sites under PMD,PHE, Dte. |  |  | ORD/000107/2022-2023 | 216/PMSD (Drilling) | 05/08/2022 | 08/08/2022 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 4.55 | 4.54 | 99.85 | 0
15 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Lakhanpur GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000158/2022-2023 | 708/PMD | 17/10/2022 | 01/11/2022 | SWAPAN MANDAL | 15.87 | 5.76 | 36.31 | 0
16 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Jabarrah GP Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000157/2022-2023 | 707/PMD | 17/10/2022 | 11/11/2022 | SUMIT KR. CHAKRABORTY | 41.18 | 1.61 | 3.9 | 0
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within HURA Block (Part-B-I) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000902/2022-2023 | 1856/PD | 13/12/2022 | 27/01/2023 | HI-LIGHT ELECTRONICS | 51.01 | 46 | 90.17 | 100
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 12 nos AWC within Hura Block (Part-A), 2 nos AWC within Hura Block (Part-C) & 1 no AWC within Hura Block (Part-D)of Purulia District under Purulia Division, PHE Dte.(Phase-I)" | Assistant Engineer | Junior Engineer | ORD/000808/2022-2023 | 1735/PD | 22/11/2022 | 06/01/2023 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 70.95 | 51.2 | 72.16 | 100
19 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Hura GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000156/2022-2023 | 706/PMD | 17/10/2022 | 16/11/2022 | M/S D. PALIT & CO. | 72.86 | 4.82 | 6.61 | 0
20 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Daldali GP and Rakhera-Bishpuria GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000137/2022-2023 | 678/PMD | 28/09/2022 | 23/10/2022 | KOUSHIK CHATTERJEE | 57.04 | 6.89 | 12.08 | 0
21 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within HURA Block (Part-B-II) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000879/2022-2023 | 1857/PD | 13/12/2022 | 27/01/2023 | MADHU SUDAN RAKSHIT | 51.93 | 26.3 | 50.65 | 100
22 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Keshargarh GP in Hura block under Purulia Mechanical Division PHE Dte. (Tender No 138/EE/PMD of 2022-23) |  |  | VCH/001094/2022-2023 | BP-2022-23-206 | 24/08/2022 | 24/08/2022 | MS D.PALIT AND CO. | 38.15 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Jabarrah GP Hura Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.214/EE/PMD of 2022-23) |  |  | VCH/001719/2022-2023 | BP-2022-23-455 | 02/12/2022 | 02/12/2022 | SUMIT KUMAR CHAKRABORTY | 33.76 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Hura GP Hura Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.215/EE/PMD of 2022-23) |  |  | VCH/001722/2022-2023 | BP-2022-23-454 | 02/12/2022 | 02/12/2022 | MS D.PALIT AND CO. | 46.16 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Lakhanpur GP, Hura Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.225/EE/PMD of 2022-23) |  |  | VCH/001728/2022-2023 | BP-2022-23-453 | 02/12/2022 | 02/12/2022 | SWAPAN MANDAL | 10.1 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of rigbored tubewell (200 mm x 165 mm) by DTH method in different sourceless AWC at Manguria-Lalpur GP, Hura Block under PMD, PHE Dte. in the District of Purulia [Tender No 216/2022-2023 of EE/PMD] |  |  | VCH/001678/2022-2023 | BP-2022-23-498 | 22/12/2022 | 22/12/2022 | SAIBAL SARKAR | 5.46 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Daldali and R - Bispuria GP, Hura Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.217/EE/PMD of 2022-23) |  |  | VCH/001730/2022-2023 | BP-2022-23-451 | 02/12/2022 | 02/12/2022 | KOUSHIK CHATTERJEE | 37.5 | 0 | 0 | 0
28 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Execution of the yield test at different GPs in Hura within the district of Purulia under PMD, PHE, Dte. |  |  | ORD/000489/2022-2023 | 128/PMSD(W/S) | 27/03/2023 | 11/04/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewells sinked at various Schools & AWCs of . Hura & Purulia-II Blocks under Purulia Division ,PHE,Dte. | Assistant Engineer |  | ORD/001364/2023-2024 | 1735/PD | 04/12/2023 | 03/01/2024 | CHATTERJEE CONSTRUCTION | 10.62 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Bamandiha Village(From node J-851 to J-864)(Part-B) | Assistant Engineer | Junior Engineer-3 | ORD/000004/2022-2023 | 150/PSD | 04/04/2022 | 29/04/2022 | CHATTERJEE CONSTRUCTION | 4.59 | 0 | 0 | 100
31 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Hura Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2022-2023 | 764/PD | 02/05/2022 | 16/06/2022 | BISWESWAR CONSTRUCTION | 27.08 | 0 | 0 | 100
32 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001025/2022-2023 | 146/PD | 03/02/2023 | 20/03/2023 | BALAJI UDDYOG | 164.99 | 0 | 0 | 100
33 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 9 no AWC within Hura Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000150/2022-2023 | 762/PD | 02/05/2022 | 16/06/2022 | NANIGOPAL DEY | 40.4 | 0 | 0 | 100
Total | [13 empty] | 996.81 | 214.58 | 21.53