## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTHmethod in different source less AWC at Serengdi GP and Birgram GP Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000167/2022-2023 | 717/PMD | 17/10/2022 | 16/11/2022 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 69.68 | 0 | 0 | 0
2 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Matha GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000164/2022-2023 | 714/PMD | 17/10/2022 | 01/11/2022 | GOENKA ENTERPRISE | 31.7 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Bagmundi GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000165/2022-2023 | 715/PMD | 17/10/2022 | 01/11/2022 | RABINDRA NATH KHAN | 28.52 | 0 | 0 | 0
4 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Supply and delivery of 200mm dia UPVC pipe for Baghmundi Block at Drilling Store/Site under Purulia Mechancial Division,P.H.E Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000184/2022-2023 | 756/PMD | 07/11/2022 | 07/12/2022 | NUPUR CHANDRA HALDER | 10.27 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Bagmundi WTP site of Bagmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000925/2022-2023 | 1931/PD | 22/12/2022 | 22/03/2023 | ROY CONSTRUCTION | 17.88 | 11.38 | 63.64 | 0
6 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Execution of the yield test at Matha & Bagmundi GP in Bagmundi Block within the district of Purulia under code SM10276 under PMD, PHE, Dte. |  |  | ORD/000322/2022-2023 | 31/PMSD(Drilling) | 03/02/2023 | 18/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0.98 | 100 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 33 nos AWC within Jhalda-II Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000961/2022-2023 | 41/PD | 09/01/2023 | 23/02/2023 | IKBAL CONSTRUCTION | 18.31 | 0 | 0 | 0
8 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Bagmundi Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE, Dte. In the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000299/2022-2023 | 68/PMD | 31/01/2023 | 20/02/2023 | S N POLYMERS (P) LIMITED | 50.44 | 31.33 | 62.12 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 104 nos AWC within Kashipur & Addl. Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000953/2022-2023 | 30/PD | 09/01/2023 | 23/02/2023 | MADHU SUDAN RAKSHIT | 57.8 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 5 nos AWC within Bagmundi Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000963/2022-2023 | 43/PD | 09/01/2023 | 23/02/2023 | ANUDIP SAHA | 2.78 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Installation of Big-Dia Odex-165 (Simultaneous driving of casing pipe) 165 mm dia Tube Well considering 120mt Depth in diferent schools, AWC of different blocks of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 836/PD | 26/06/2023 | 25/08/2023 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 94.03 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Kashipur Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000143/2022-2023 | 754/PD | 02/05/2022 | 16/06/2022 | AMITAVA CHAKRABORTY | 71.14 | 31.58 | 44.39 | 0
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | Assistant Engineer |  | ORD/000574/2022-2023 | 1129/PD | 25/07/2022 | 08/09/2022 | RAJ KUMAR MONDAL | 94.93 | 19.84 | 20.9 | 0
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Jhalda-II Block (Part-C), 2 nos AWC within Jhalda-II Block (Part-D) & 6 nos AWC within Jhalda-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | Assistant Engineer |  | ORD/000573/2022-2023 | 1128/PD | 25/07/2022 | 08/09/2022 | PRINCE INDUSTRIES ( INDIA) | 87.09 | 84.61 | 97.15 | 0
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 36nos school for 201-500 students, 2 no. school for 501-800 students and 2no school avove 800 students within Kashipur Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000595/2022-2023 | 1219/PD | 17/08/2022 | 01/10/2022 | PRAVAT SARKAR | 202.09 | 110.92 | 54.89 | 0
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | Assistant Engineer |  | ORD/000575/2022-2023 | 1130/PD | 25/07/2022 | 08/09/2022 | A ONE CONSTRUCTION | 94.93 | 35.05 | 36.92 | 0
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000596/2022-2023 | 1201/PD | 12/08/2022 | 26/09/2022 | MS D.PALIT AND CO. | 197.96 | 101.64 | 51.35 | 0
18 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Sindri GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000168/2022-2023 | 718/PMD | 17/10/2022 | 01/11/2022 | SUMIT KR. CHAKRABORTY | 38.02 | 1.61 | 4.23 | 0
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Acceptance cum Work Order For Water supply Tap Connection Arrangement for 2 nos AWC within Kashipur Block (Part-N), 1 nos AWC within Kashipur Block (Part-O) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000799/2022-2023 | 1726/PD | 22/11/2022 | 06/01/2023 | SUBODH PRAMANIK | 24.68 | 24.68 | 99.98 | 0
20 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rig bore tube well (200mm X 165mm) by DTH method in different source less AWC at Burda-Kalimati G.P, Baghmundi Block under Purulia Mechanical Division, P.H.E Dte. in the District of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000186/2022-2023 | 752/PMD | 07/11/2022 | 02/12/2022 | CHAKRABORTY MINING AND ENGINEERING | 50.66 | 22.85 | 45.11 | 0
21 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Tanturi-Suisa GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000166/2022-2023 | 716/PMD | 17/10/2022 | 01/11/2022 | NUPUR CHANDRA HALDER | 12.7 | 2.07 | 16.3 | 0
22 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000941/2022-2023 | 22/PD | 05/01/2023 | 19/02/2023 | WATER TECH | 165.38 | 70.45 | 42.6 | 100
23 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Jhalda-II Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000456/2021-2022 | 418/PD | 16/03/2022 | 30/04/2022 | PRINCE INDUSTRIES ( INDIA) | 71.01 | 67.93 | 95.66 | 0
24 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Bagmundi GP, Bagmundi Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.228/EE/PMD of 2022-23) |  |  | VCH/001689/2022-2023 | BP-2022-23-488 | 22/12/2022 | 22/12/2022 | RABINDRANATH KHAN | 15.23 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Matha GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.229/EE/PMD of 2022-23) |  |  | VCH/001656/2022-2023 | BP-2022-23-531 | 09/01/2023 | 09/01/2023 | GOENKA ENTERPRISE | 18.36 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Tanturi-Suisa GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.227/EE/PMD of 2022-23) |  |  | VCH/001682/2022-2023 | BP-2022-23-489 | 22/12/2022 | 22/12/2022 | NUPUR CHANDRA HALDER | 8.69 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Supply and delivery of 200mm dia UPVC pipe for Baghmundi Block at Drilling Store/Site under Purulia Mechancial Division, P.H.E Dte. (Tender No.263/EE/PD of 2022-23) |  |  | VCH/001658/2022-2023 | BP-2022-23-529 | 09/01/2023 | 09/01/2023 | NUPUR CHANDRA HALDER | 10.25 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Sindri GP Bagmundi Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.221/EE/PMD of 2022-23) |  |  | VCH/001725/2022-2023 | BP-2022-23-456 | 02/12/2022 | 02/12/2022 | SUMIT KUMAR CHAKRABORTY | 28.21 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Bagmundi GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.228/EE/PD of 2022-23) |  |  | VCH/001687/2022-2023 | BP-2022-23-487 | 22/12/2022 | 22/12/2022 | RABINDRANATH KHAN | 4 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Serengdi GP and Birgram GP Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.236/EE/PMD of 2022-23) |  |  | VCH/001708/2022-2023 | BP-2022-23-474 | 16/12/2022 | 16/12/2022 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 68.49 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000588/2022-2023 | 1155/PD | 01/08/2022 | 15/09/2022 | BINGAS ELECTRICAL ELECTRONICS AND SOLAR SYSTEM | 158.22 | 56.94 | 35.99 | 80
32 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within JHALDA -II Block (Part-G)&2 nos Awc Within JHALDA-II block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000882/2022-2023 | 1860/PD | 13/12/2022 | 27/01/2023 | HARI NARAYAN YADAV CONSTRUCTION CO | 41.31 | 9.54 | 23.09 | 100
33 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Bagmundi Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000486/2021-2022 | 497/PD | 29/03/2022 | 13/05/2022 | SUNRISE ENGINEERING CORPORATION | 71.04 | 22.66 | 31.9 | 100
Total | [13 empty] | 1916.8 | 706.08 | 36.84