## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000586/2022-2023 | 1153/PD | 01/08/2022 | 15/09/2022 | JYOTY SOLAR POWER | 158.35 | 64.2 | 40.54 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000576/2022-2023 | 1131/PD | 25/07/2022 | 08/09/2022 | SINGHA ENTERPRISE | 94.88 | 0 | 0 | 100
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000596/2022-2023 | 1201/PD | 12/08/2022 | 26/09/2022 | MS D.PALIT AND CO. | 197.96 | 53.51 | 27.03 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Providing Functional Household Tap Connection (FHTC) at different AWC, School and other allied works of Keliathole -Palashkola Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000390/2022-2023 | 348/RNP | 01/06/2022 | 21/06/2022 | SUBHAS CHANDRA MAHATO | 1.48 | 1.48 | 99.85 | 100
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000599/2022-2023 | 1151/PD | 01/08/2022 | 15/09/2022 | WATER TECH | 158.37 | 139.65 | 88.18 | 100
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000590/2022-2023 | 1159/PD | 01/08/2022 | 15/09/2022 | PRINCE INDUSTRIES ( INDIA) | 197.96 | 197.6 | 99.82 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Kashipur Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000143/2022-2023 | 754/PD | 02/05/2022 | 16/06/2022 | AMITAVA CHAKRABORTY | 71.14 | 22.79 | 32.04 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | Assistant Engineer |  | ORD/000574/2022-2023 | 1129/PD | 25/07/2022 | 08/09/2022 | RAJ KUMAR MONDAL | 94.93 | 35.09 | 36.96 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-P) of Purulia District under Purulia Division, PHE Dte.(Phase-IV) | Assistant Engineer |  | ORD/000577/2022-2023 | 1132/PD | 25/07/2022 | 08/09/2022 | PRINCE INDUSTRIES ( INDIA) | 95.01 | 89.68 | 94.39 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | Assistant Engineer |  | ORD/000575/2022-2023 | 1130/PD | 25/07/2022 | 08/09/2022 | A ONE CONSTRUCTION | 94.93 | 35.91 | 37.82 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Kashipur Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000142/2022-2023 | 753/PD | 02/05/2022 | 16/06/2022 | RABIN CHANDRA CHAIL | 70.52 | 53.76 | 76.23 | 0
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 65/2022-23 of SE/PMU/WBPWSP(P) ) |  |  | VCH/001057/2022-2023 | BP-2022-23-404 | 20/10/2022 | 20/10/2022 | JYOTY SOLAR POWER | 88.84 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001026/2022-2023 | 145/PD | 03/02/2023 | 20/03/2023 | S N POLYMERS PVT LTD | 206.54 | 82.63 | 40 | 100
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000941/2022-2023 | 22/PD | 05/01/2023 | 19/02/2023 | WATER TECH | 165.38 | 0 | 0 | 100
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001025/2022-2023 | 146/PD | 03/02/2023 | 20/03/2023 | BALAJI UDDYOG | 164.99 | 48.64 | 29.48 | 100
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10277 | Anganwadi | Making Xerox copy of original DPR, Drawing, Mouza Map etc. |  |  | BILL/00248/2023-2024 | 27/2023-149 | 30/05/2023 | 30/05/2023 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
Total | [13 empty] | 1861.66 | 824.93 | 44.31