## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within NETURIA Block (Part-C-II) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000886/2022-2023 | 1864/PD | 13/12/2022 | 27/01/2023 | KHITISH CHANDRA PATHAK | 51.93 | 44.48 | 85.65 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Neturia Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000037/2022-2023 | 608/PD | 19/04/2022 | 03/06/2022 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 15.77 | 15.58 | 98.79 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Neturia Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000036/2022-2023 | 607/PD | 19/04/2022 | 03/06/2022 | MD AAMIR KHAN | 47.36 | 38.34 | 80.96 | 100
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Neturia Block (Part-G) of Purulia District under Purulia Division, PHE Dte. (Phase-IV) | Assistant Engineer | Junior Engineer | ORD/000563/2022-2023 | 1118/PD | 25/07/2022 | 08/09/2022 | JYOTY SOLAR POWER | 54.44 | 16.97 | 31.17 | 100
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within NETURIA Block (Part-C-I) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000885/2022-2023 | 1863/PD | 13/12/2022 | 27/01/2023 | SUNRISE ENGINEERING CORPORATION | 52.05 | 33.12 | 63.63 | 100
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within NETURIA Block (Part-F) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000903/2022-2023 | 1865/PD | 13/12/2022 | 27/01/2023 | BASHUDEV DUTTA | 94.34 | 75.1 | 79.61 | 100
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 21 nos AWC within Neturia Block of Purulia District under Purulia Division, PHE Dte.(Phase-I) (Part-A and B) | Assistant Engineer | Junior Engineer | ORD/000268/2022-2023 | 819/PD | 17/05/2022 | 01/07/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 95.03 | 67.02 | 70.52 | 100
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Neturia Block (Part-E) of Purulia District under Purulia Division, PHE Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/000602/2022-2023 | 1228/PD | 22/08/2022 | 06/10/2022 | WATER TECH | 90.73 | 75.33 | 83.04 | 100
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Neturia Block (Part-D)of Purulia District under Purulia Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000562/2022-2023 | 1117/PD | 25/07/2022 | 08/09/2022 | WATER TECH | 90.73 | 61.01 | 67.24 | 100
Total | [13 empty] | 592.38 | 426.95 | 72.07