## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Providing Hired Driver and man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte . | Assistant Engineer |  | ORD/000193/2022-2023 | 433/BMSD(D) | 13/06/2022 | 29/09/2022 | CHAKRABORTY MAINING & ENGINEERING. | 2.37 | 0 | 0 | 0
2 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of DTH Hammer for different Rig unit for sinking of 200mmX165mm RBTW in over burden range at B.M.S.D(D) under B.M.D, P.H.E Dte in connection to JJM programme. | Assistant Engineer |  | ORD/000047/2021-2022 | 170/BMSD(D) | 29/03/2022 | 08/04/2022 | SUDIP ENGINEERING CO | 0.98 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Puncha Block (Part-E) of Purulia District under Purulia Division, PHE Dte. (Tender No.133/EE/PD of 2022-23) |  |  | VCH/001024/2022-2023 | BP-2022-23-325 | 29/09/2022 | 29/09/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 18.21 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Puncha Block (Part-I) of Purulia District under Purulia Division, PHE Dte. (Tender No. 334/2022-23 of EE/PD)) |  |  | VCH/000998/2022-2023 | BP-2022-23-236 | 05/09/2022 | 05/09/2022 | M/S ACHARJEE CONSTRUCTION | 6.2 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Puncha Block (Part-F) of Purulia District under Purulia Division, PHE Dte. (Tender No- 103/2022-23 of EE/PD) |  |  | VCH/001071/2022-2023 | BP-2022-23-432 | 25/11/2022 | 25/11/2022 | JYOTY SOLAR POWER | 25.18 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Puncha Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 156/2022-23 of EE/PD) |  |  | VCH/001010/2022-2023 | BP-2022-23-268 | 20/09/2022 | 20/09/2022 | SWAPAN MANDAL | 17.44 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Balarampur Block (Part-A) & 9 nos AWC within Balarampur Block (Part-D) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000567/2022-2023 | 1122/PD | 25/07/2022 | 08/09/2022 | WRISHI ENTERPRISE | 95.12 | 0 | 0 | 60
8 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of different fast moving spares fpr compressor of KLR Rig vehicle in connection to JJM programme at B.M.S.D(D) under B.M.D, P.H.E Dte | Driller-in-Charge |  | ORD/000421/2022-2023 | 439/BMSD(D) | 13/06/2022 | 03/07/2022 | M/S SWAPAN BANERJEE | 1.66 | 0 | 0 | 0
9 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of Tyre for Different Rig Vehicle at B.M.S.D(D) in connection to JJM Programme. | Driller-in-Charge |  | ORD/000422/2022-2023 | 442/BMSD(D) | 13/06/2022 | 03/07/2022 | RAJIB COMPANY | 2.32 | 0 | 0 | 0
10 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Providing Hired Driver and man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit 7D at B.M.S.D(D) under B.M.D, P.H.E Dte . | Driller-in-Charge |  | ORD/000420/2022-2023 | 435/BMSD(D) | 13/06/2022 | 29/09/2022 | PRADIP KUMAR DHABAL | 2.94 | 0 | 0 | 0
11 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Providing Manpower engagement for construction of R.B.T.W. in connection to JJM programme in Purulia district by Rig Unit 7D at BMSD(D)) under BMD, P.H.E.Dte | Assistant Engineer |  | ORD/000419/2022-2023 | 436/BMSD(D) | 13/06/2022 | 29/09/2022 | PRADIP KUMAR DHABAL | 3.39 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Puncha Block (Part-A) of Purulia District under Purulia Division, PHE Dte. (Phase-I) | Assistant Engineer |  | ORD/000811/2022-2023 | 1703/PD | 22/11/2022 | 06/01/2023 | SWAPAN MANDAL | 91.55 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 15 nos AWC within Puncha Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000972/2022-2023 | 31/PD | 09/01/2023 | 23/02/2023 | S. S. ENTERPRISE | 8.34 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Puncha Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000033/2022-2023 | 604/PD | 19/04/2022 | 03/06/2022 | SWAPAN MANDAL | 23.62 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Puncha Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000035/2022-2023 | 606/PD | 19/04/2022 | 03/06/2022 | M/S A.D.CONCERN | 7.88 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Puncha Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000031/2022-2023 | 602/PD | 19/04/2022 | 03/06/2022 | JYOTY SOLAR POWER | 47.36 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Puncha Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000034/2022-2023 | 605/PD | 19/04/2022 | 03/06/2022 | M/S ACHARJEE CONSTRUCTION | 15.77 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 20nos AWC within Puncha Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000535/2022-2023 | 1051/PD | 08/07/2022 | 22/08/2022 | B.K. ENTERPRI SE | 158.35 | 0 | 0 | 100
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Puncha Block (Part-D) of Purulia District under Purulia Division, PHE Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/000812/2022-2023 | 1704/PD | 22/11/2022 | 06/01/2023 | RABIN CHANDRA CHAIL | 91.55 | 0 | 0 | 100
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Supply of Fuel & lubricant bill for AWC Puncha Block. |  |  | BILL/00349/2022-2023 | BP-2022-23-849 | 31/03/2023 | 31/03/2023 | M/S SHANKAR AUTO SERVICE | 4.74 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Puncha Block (Part-F) of Purulia District under Purulia Division, PHE Dte. (Tender No. 103/22-23 of EE/PD) |  |  | VCH/001083/2022-2023 | BP-2022-23-222 | 29/08/2022 | 29/08/2022 | JYOTY SOLAR POWER | 14.8 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Balarampur Block (Part-H)of Purulia District under Purulia Division, PHE Dte.(Phase-V) | Assistant Engineer | Junior Engineer | ORD/000570/2022-2023 | 1125/PD | 25/07/2022 | 08/09/2022 | BALAJI UDDYOG | 90.51 | 0 | 0 | 70
23 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Balarampur Block (Part-I)of Purulia District under Purulia Division, PHE Dte.(Phase-VI) | Assistant Engineer | Junior Engineer | ORD/000571/2022-2023 | 1126/PD | 25/07/2022 | 08/09/2022 | BALAJI UDDYOG | 90.51 | 0 | 0 | 40
24 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Puncha Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000030/2022-2023 | 601/PD | 19/04/2022 | 03/06/2022 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 70.71 | 0 | 0 | 100
25 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Puncha Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000032/2022-2023 | 603/PD | 19/04/2022 | 03/06/2022 | RABINDRANATH KHAN | 23.45 | 0 | 0 | 100
26 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Puncha Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000593/2022-2023 | 1200/PD | 12/08/2022 | 26/09/2022 | BALAJI UDDYOG | 197.48 | 0 | 0 | 100
27 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Puncha Block (Part-K) & 2 nos AWC within Puncha Block (Part-L) of Purulia District under Purulia Division, PHE Dte. (Phase-III) | Assistant Engineer | Junior Engineer | ORD/000813/2022-2023 | 1705/PD | 22/11/2022 | 06/01/2023 | MUNNA AGROTECH ENTERPRISE | 91.67 | 0 | 0 | 100
28 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10280 | Anganwadi | Work of Vendoring service service relating to E-return for Income-Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f 01.10.2023 to 30.09.2024) |  |  | BILL/00706/2024-2025 | BP-2024-25-356 | 11/09/2024 | 11/09/2024 | NIGAM CONSULTANCY SERVICES | 0.77 | 0 | 0 | 0
Total | [13 empty] | 1204.86 | 0 | 0