## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 37nos School upto 200 Students, within Arsha Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000462/2021-2022 | 442/PD | 22/03/2022 | 06/05/2022 | MEGA SOLAR ENERGY | 155.9 | 132.88 | 85.23 | 0
2 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Arsha G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000166/2022-2023 | 1124/BMD | 12/09/2022 | 04/10/2022 | M/S D. PALIT AND CO. | 64.49 | 44.12 | 68.42 | 0
3 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Sirkabad G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000169/2022-2023 | 1127/BMD | 12/09/2022 | 27/09/2022 | M DHARA AND BROTHERS | 36.98 | 16.14 | 43.66 | 0
4 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Puara G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000174/2022-2023 | 1137/BMD | 13/09/2022 | 28/09/2022 | M DHARA AND BROTHERS | 40.06 | 31.08 | 77.58 | 0
5 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Beldih, Hensla & Mankiyesari G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000167/2022-2023 | 1125/BMD | 12/09/2022 | 02/10/2022 | M DHARA AND BROTHERS | 43.69 | 37.52 | 85.88 | 0
6 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Chatuhansa & Hetgugui G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000168/2022-2023 | 1126/BMD | 12/09/2022 | 02/10/2022 | M/S D. PALIT AND CO. | 58.04 | 37.25 | 64.18 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 20 nos AWC within Arsha Block (Part-D) of Purulia District under Purulia Division, PHE Dte." | Assistant Engineer |  | ORD/000806/2022-2023 | 1733/PD | 22/11/2022 | 06/01/2023 | M/S. BADAL GHOSH | 94.63 | 60.12 | 63.54 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 24 nos AWC within Arsha Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000977/2022-2023 | 82/PD | 17/01/2023 | 03/03/2023 | THE BUSINESS ENGINEERS INDIA | 13.34 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 12 nos AWC within Arsha Block (Part-B) of Purulia District under Purulia Division, PHE Dte." | Assistant Engineer |  | ORD/000805/2022-2023 | 1730/PD | 22/11/2022 | 06/01/2023 | CHATTERJEE CONSTRUCTION | 56.76 | 21.62 | 38.1 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 12 nos AWC within Arsha Block (Part-A) & 1 nos AWC within Arsha Block (Part-E)of Purulia District under Purulia Division, PHE Dte." | Assistant Engineer | Junior Engineer | ORD/000803/2022-2023 | 1731/PD | 22/11/2022 | 06/01/2023 | SEN BROTHERS | 61.5 | 51.12 | 83.13 | 100
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001294/2022-2023 | 145_/PD | 03/02/2023 | 20/03/2023 | S N POLYMERS PVT LTD | 206.54 | 111.29 | 53.88 | 100
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 13 nos AWC within Arsha Block of Purulia District under Purulia Division, PHE Dte.(Phase-II) (Part-C, H & I) | Assistant Engineer | Junior Engineer | ORD/000281/2022-2023 | 818/PD | 17/05/2022 | 01/07/2022 | MEGA SOLAR ENERGY | 58.91 | 27.88 | 47.33 | 100
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Arsha Block (Part-F),9 nos Awc Within Arsha block (Part-G) & 2nos AWC within Arsha Block (Part-J) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000874/2022-2023 | 1852/PD | 13/12/2022 | 27/01/2023 | KAMAKHYA ENTERPRISE | 94.65 | 64.68 | 68.34 | 100
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Arsha & Bagmundi blocks under Purulia Division ,PHE,Dte. | Assistant Engineer | Junior Engineer | ORD/001362/2023-2024 | 1731/PD | 04/12/2023 | 03/01/2024 | VIVEKANANDA CONSTRUCTION | 12 | 0 | 0 | 100
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 13 nos AWC within Arsha Block of Purulia District under Purulia Division, PHE Dte.(Phase-III) (Part-A, B & C) | Assistant Engineer | Junior Engineer | ORD/000283/2022-2023 | 826/PD | 17/05/2022 | 01/07/2022 | KAMAKHYA ENTERPRISE | 81.25 | 39.5 | 48.62 | 100
Total | [13 empty] | 1078.73 | 675.21 | 62.59