## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of Drilling Materials for Hard Rock formation Drilling for sinking of RBTW in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. Dist: Bankura. | Assistant Engineer |  | ORD/000151/2022-2023 | 950/BMD | 29/07/2022 | 28/08/2022 | SUDIP ENGINEERING CO | 17.87 | 0 | 0 | 0
2 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and delivery of different types of Drilling Materials for sinking of 200mm x165mm DTH type RBTW by Departmental Rig of B.M.S.D (D) in Balarampur Block in the Distric of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. |  |  | ORD/000141/2022-2023 | 851/BMD | 05/07/2022 | 04/08/2022 | M/S NABIN GOPAL SENGUPTA | 36.79 | 0 | 0 | 0
3 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of DTH drilling tools at Bankura Mechanical Division for different Rig unit in over burden range for sinking of 200mmX165mm RBTW in connection to JJM programme. in the district Purulia under PHE Dte | Assistant Engineer |  | ORD/000142/2022-2023 | 852/BMD | 05/07/2022 | 04/08/2022 | CHAKRABORTY MAINING & ENGINEERING. | 14.3 | 0 | 0 | 0
4 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of 4 1/2 "(114 mm approx) x 10 ' long Drill Tube for 7D Drilling Rig Machine of BMSD(D), for sinking of RBTW in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000150/2022-2023 | 949/BMD | 29/07/2022 | 28/08/2022 | AHALYA ENGINEERING WORKS | 24.34 | 0 | 0 | 0
5 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Providing Hired skilled Labour for construction of R.B.T.WIn the district of Purulia in connection to JJM Programme by Rig unit 7D/others under B.M.D, P.H.E Dte . | Assistant Engineer |  | ORD/000203/2022-2023 | 311/BMSD(D) | 13/05/2022 | 12/06/2022 | SUTRADHAR TRADERS | 0.94 | 0.94 | 100 | 0
6 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply & Delivery of UPVC Casing and others for sinking of 200mm x 165mm DTH type RBTW by KLR Rig at B.M.S.D (D) under B.M.D. P.H.E. Dte. in connection to JJM Program. | Assistant Engineer |  | ORD/000045/2021-2022 | 154/BMSD(D) | 24/03/2022 | 08/04/2022 | M/S DAS & SARKAR ENTERPRISE | 4.25 | 4.25 | 100 | 0
7 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of 150Amh , 180Amh and 100 Amh Batteries for different Rig and respective Supporting Vehicles at B.M.S.D(D), under B.M.D, P.H.E Dte in connection to JJM Programme. | Assistant Engineer |  | ORD/000206/2022-2023 | 257/BMSD(D) | 22/04/2022 | 02/05/2022 | SUTRADHAR TRADERS | 0.81 | 0.81 | 100 | 0
8 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte . | Assistant Engineer |  | ORD/000198/2022-2023 | 366/BMSD(D) | 31/05/2022 | 14/06/2022 | BASUDEV DEY | 0.75 | 0.75 | 100 | 0
9 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Gerua G.P of Balarampur Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000214/2022-2023 | 1383/BMD | 23/11/2022 | 08/12/2022 | SINGHA ENTERPRISE | 63.66 | 63.48 | 99.73 | 0
10 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of Drilling Accessories and others for sinking of 200mmX165mm DTH type RBTW by 7D Rig at B.M.S.D(D) under B.M.D, P.H.E Dte in connection to JJM programme. | Assistant Engineer |  | ORD/000044/2021-2022 | 153/BMSD(D) | 24/03/2022 | 08/04/2022 | UNICON | 4.25 | 4.25 | 100 | 0
11 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of different fast moving spares for compressor of KLR Rig vehicle in connection to JJM programme at B.M.S.D(D) under B.M.D, P.H.E Dte | Assistant Engineer |  | ORD/000184/2022-2023 | 439/BMSD(D) | 13/06/2022 | 03/07/2022 | M/S SWAPAN BANERJEE | 1.66 | 1.66 | 100 | 0
12 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Providing man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte . | Assistant Engineer |  | ORD/000194/2022-2023 | 431/BMSD(D) | 10/06/2022 | 26/09/2022 | CHAKRABORTY MAINING & ENGINEERING. | 3.39 | 3.36 | 99.07 | 0
13 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and delivery of 4 ½¿ (114 mm approx.) x 10¿ long Drill Tube for 7D Drilling Rig Machine at BMSD (D), under B.M.D. P.H.E. Dte. in connection to JJM Program. | Assistant Engineer |  | ORD/000043/2021-2022 | 152/BMSD(D) | 24/03/2022 | 03/04/2022 | CHAKRABORTY MAINING & ENGINEERING. | 4.86 | 4.86 | 100 | 0
14 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of DTH drilling tools (Bit) for KLR Rig in over burden range for sinking of 200mmX165mm RBTW at B.M.S.D(D) under B.M.D, P.H.E Dte in connection to JJM programme. | Assistant Engineer |  | ORD/000048/2021-2022 | 178/BMSD(D) | 31/03/2022 | 10/04/2022 | SUDIP ENGINEERING CO | 0.94 | 0.94 | 100 | 0
15 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of DTH drilling tools (Hammer) for KLR Rig in over burden range for sinking of 200mmX165mm RBTW at B.M.S.D(D) under B.M.D, P.H.E Dte in connection to JJM programme. | Assistant Engineer |  | ORD/000046/2021-2022 | 179/BMSD(D) | 31/03/2022 | 10/04/2022 | SUDIP ENGINEERING CO | 0.98 | 0.98 | 100 | 0
16 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Darda, Ghatbera & Gerua G.P of Balarampur Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000179/2022-2023 | 1208/BMD | 23/09/2022 | 08/10/2022 | SUNRISE ENGINEERING CORPORATION | 64.87 | 57.72 | 88.98 | 0
17 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Ghatbera G.P of Balarampur Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000180/2022-2023 | 1209/BMD | 23/09/2022 | 08/10/2022 | M/S D. PALIT AND CO. | 93.51 | 85.16 | 91.07 | 0
18 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Providing Hired Driver and man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit 7D at B.M.S.D(D) under B.M.D, P.H.E Dte . | Assistant Engineer |  | ORD/000187/2022-2023 | 435/BMSD(D) | 13/06/2022 | 29/09/2022 | PRADIP KUMAR DHABAL | 2.94 | 2.48 | 84.26 | 0
19 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Providing Hired Driver(WB37D 8040) for construction of R.B.T.WIn the district of Purulia in connection to JJM Programme by Rig unit 7D/others under B.M.D, P.H.E Dte | Assistant Engineer |  | ORD/000199/2022-2023 | 310/BMSD(D) | 13/05/2022 | 12/06/2022 | SUTRADHAR TRADERS | 0.82 | 0.82 | 100 | 0
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube well in AWC Balarampur Block. |  |  | BILL/00073/2022-2023 |  | 16/12/2022 | 16/12/2022 | M/S SHANKAR AUTO SERVICE | 3.96 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube Well in Purulia District related to JJm work. |  |  | VCH/000731/2022-2023 |  | 13/10/2022 | 13/10/2022 | M/S NABIN GOPAL SENGUPTA | 36.79 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube well in Purulia District related to JJM work. |  |  | VCH/000719/2022-2023 |  | 13/10/2022 | 13/10/2022 | M/S SHANKAR AUTO SERVICE | 28.78 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube Well in Purulia District related to JJm work. |  |  | VCH/000730/2022-2023 |  | 13/10/2022 | 13/10/2022 | CHAKRABORTY MINING AND ENGINEERING | 32.18 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Submission of bill in connection with the work of rising of Tube Well under Balarampur W/s Scheme in Purulia District. |  |  | VCH/000304/2022-2023 |  | 27/07/2022 | 27/07/2022 | LALJI RAJA AND SONS | 10.79 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | FHTC Connetion for Anganwari Balarampur W/s Scheme. |  |  | VCH/000291/2022-2023 |  | 18/07/2022 | 18/07/2022 | SADHAN GORAIN | 27 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube Well in Purulia District related to JJm work. |  |  | VCH/000687/2022-2023 | BP-2022-23-369 | 30/09/2022 | 30/09/2022 | M/S SHANKAR AUTO SERVICE | 10.27 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Balarampur Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000481/2021-2022 | 492/PD | 29/03/2022 | 13/05/2022 | SADHAN GORAIN | 70.98 | 51.93 | 73.16 | 0
28 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Balarampur Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000482/2021-2022 | 493/PD | 29/03/2022 | 13/05/2022 | SADHAN GORAIN | 70.98 | 52.18 | 73.51 | 0
29 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Balarampur Block (Part-P),2 nos Awc Within Balarampur block (Part-Q) & 2nos AWC within Balarampur Block (Part-R) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000876/2022-2023 | 1854/PD | 13/12/2022 | 27/01/2023 | PRATIK SAHA | 57.83 | 29.05 | 50.24 | 50
30 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Repairing of Yard lighting at BMD office premises & Store for keeping different martials under JJM Program under Bankura Mechanical Division P.H.E. Dte. | Assistant Engineer |  | ORD/000416/2022-2023 | 1652/BMSD | 28/12/2022 | 07/01/2023 | M/S NABIN GOPAL SENGUPTA | 0.97 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Balarampur Block (Part-O) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000485/2021-2022 | 496/PD | 29/03/2022 | 13/05/2022 | SEN BROTHERS | 23.44 | 14.57 | 62.14 | 0
32 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Balarampur Block (Part-N) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000484/2021-2022 | 495/PD | 29/03/2022 | 13/05/2022 | BOSE CONSTRUCTION | 23.57 | 14.84 | 62.97 | 0
33 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Installation of Big-Dia D.T.H. Tube Well (200mm x 165mm) by Robotic DTH Rigs for drilling upto 1200 ft or small form factor trolly mounted rig with trolly mounted compressor suitable for narrow 68 inch wide roads considering 200mt Depth in diferent Schools of different Blocks (PHASE-2) of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000851/2022-2023 | 1755/PD | 22/11/2022 | 06/01/2023 | S N POLYMERS PVT LTD | 96.12 | 95.52 | 99.37 | 0
34 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Balarampur Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000483/2021-2022 | 494/PD | 29/03/2022 | 13/05/2022 | GOENKA ENTERPRISE | 47.32 | 41.15 | 86.96 | 0
35 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Installation of Big-Dia Odex-165 (Simultaneous driving of casing pipe) 165 mm dia Tube Well considering 120mt Depth in diferent schools, AWC of different blocks of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001255/2023-2024 | 1520/PD | 16/10/2023 | 15/12/2023 | S N POLYMERS PVT LTD | 94.53 | 94.51 | 99.97 | 100
36 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Supply of Fuel & lubricant bill for AWC Balarampur Block. |  |  | BILL/00347/2022-2023 | BP-2022-23-848 | 31/03/2023 | 31/03/2023 | M/S SHANKAR AUTO SERVICE | 5.78 | 0 | 0 | 0
37 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Submission of bill in connection with the work of sinking of Tube well in Purulia District related to JJM work. |  |  | VCH/001099/2022-2023 | BP-2022-23-161 | 05/08/2022 | 05/08/2022 | LALJI RAJA AND SONS | 6.89 | 0 | 0 | 0
38 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Fuel bill in connection with work of sinking tube well in Purulia District related to JJM work |  |  | VCH/001691/2022-2023 | BP-2022-23-500 | 22/12/2022 | 22/12/2022 | LALJI RAJA AND SONS | 3.96 | 0 | 0 | 0
39 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | SUPPLY AND DELIVERY OF DTH DRILLING TOOLS AT BANKURA MECHACINCAL DIVISION FOR DIFFERENT RIG UNIT IN OVER BURDEN RANGE FOR SINKING OF 200MM X 165MM RBTW IN CONNECTION WITH JJM PROGRAMME IN THE DISTRICT OF PURULIA UNDER PHE DTE. [TENDER NO-166/2022-2023 OF EE/BMD] |  |  | VCH/001703/2022-2023 | BP-2022-23-481 | 16/12/2022 | 16/12/2022 | CHAKRABORTY MINING AND ENGINEERING | 14.3 | 0 | 0 | 0
40 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | SUPPLY AND DELIVERY OF DRILLING MATERIALS FOR HARD ROCK FORMATION DRILLING FOR SINKING OF RBTW IN THE DISTRICT OF PURULIA IN CONNECTION WITH JJM PROGRAMME UNDER BANKURA MECHACINCAL DIVISION, PHE DTE. [TENDER NO-179/2022-2023 OF EE/BMD] |  |  | VCH/001699/2022-2023 | BP-2022-23-482 | 16/12/2022 | 16/12/2022 | SUDIP ENGINEERING CO, | 17.87 | 0 | 0 | 0
41 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube well in Purulia District related to JJM work. |  |  | VCH/000720/2022-2023 | BP-2022-23-162 | 05/08/2022 | 05/08/2022 | LALJI RAJA AND SONS | 3.9 | 0 | 0 | 0
42 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Proposal for laying of water pipeline along NH-32 in the stretches -i) from Km 114.979 to Km 119.324 (RHS), ii) from Km 111.800 to Km 116.200 (LHS), iii) from Km 111.800 to Km 112.844 (RHS) & vross NH-32 at Km 112.844, Dist- Purulia, West Bengal. |  |  | BILL/00044/2022-2023 | BP-2022-23-477 | 09/01/2023 | 09/01/2023 | NATIONAL HIGHWAY AUTHOTITY OF INDIA (NHAI) | 5.34 | 0 | 0 | 0
43 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | SUPPLY AND DELIVERY OF DIFFERENT TYPES OF DRILLING MATERIALS FOR SINKING OF 200MM X 165 MM DTH TYPE RBTW BY DEPARTMENTAL RIG OF B.M.S.D (D) UNDER BMD PHE DTE. IN BALARAMPUR BLOCK IN THE DISTRICT OF PURULIA IN CONNECTION WITH JJM PROGRAMME UNDER BANKURA MECHACINCAL DIVISION, PHE DTE. [TENDER NO-24/2022-2023 OF EE/BMD] |  |  | VCH/001696/2022-2023 | BP-2022-23-485 | 16/12/2022 | 16/12/2022 | M/S NABIN GOPAL SENGUPTA | 36.79 | 0 | 0 | 0
44 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | SUPPLY AND DELIVERY OF 4 1/2 "(114 MM APPROX) X 10 LONG DRILL TUBE FOR 7D DRILLING RIG MACHINE OF BMSD(D) FOR SINKING OF RBTW IN THE DISTRICT OF PURULIA IN CONNECTION TO JJM PROGRAM UNDER BANKURA MECHANICAL DIVISION, PHE DTE. [TENDER NO-189/2022-2023 OF EE/BMD] |  |  | VCH/001677/2022-2023 | BP-2022-23-486 | 22/12/2022 | 22/12/2022 | AHALYA ENGINEERING WORKS | 24.34 | 0 | 0 | 0
45 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Balarampur Block (Part_C) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000566/2022-2023 | 1121/PD | 25/07/2022 | 13/05/2025 | JYOTY SOLAR POWER | 90.73 | 77.1 | 84.98 | 100
Total | [13 empty] | 1187.32 | 703.28 | 59.23